## Sheet9
Land Acquisition issue
Active Before 2014 | 26 /80
Active 2014-19 | 6/56
Active 19-24 | 37/136
j

## Active before 2014
S.N | Rly | PH | Name of Project | Sanctioned Year | DE Sanction Year | Length of project (Km) | Original TDC | Anticipated TDC as given by Rly | Time overrun | Reasons for Time overrun | TIME OVERRUN REASON | Forest Clearance & Wildlife | Land Acquisition | Phase wise Sanctioning | Law & Order issue | Utility Shifting | No delay | Original Sanctioned Cost (in Cr) | Anticipated Cost (in Cr) | Cost overrun (in Cr) | Reasons for Cost Over run | COST OVERRUN REASON | Remarks
30 | NR | NL | Rishikesh-Karanprayag | 2009-10-01 | 2016 | 125 | 2026-12-28 | 2026-12-28 | 0 year | • Delay due to NGT case (2016-2019) - LOA for civil work including E/W, Major and Minor bridges from KM 98 to 135 was issued -19.07.2016. However, Case is filed in NGT court in Dec’16 due to which ongoing works were to be suspended. NGT case was disposed on 29.04.2019. • Delay in forest clearance (2014-2018) - Registration of forest proposal was completed in June 2014. However, Stage-I clearance was obtained in 26.02.2018 and Stage-II clearance was obtained in 07.06.2018 • Delay due to Introduction of Wildlife passes as per MoEF requirement - 7 Nos EOPs/EUPS were finalized by CCF Bilaspur in April’2018. Accordingly, L-section were revised and 7 Nos EOPs/EUPs were incorporated in Aug’2020. Further, PCCF advised to construct 22 Nos EOPs/EUPS in Oct’21. L-section has been revised and EOPs/EUPS were incorporated in Dec’21. • Non-performance of contractor- Non-performance of contractor M/s RMN (Civil work from Km 29-67) and termination of contract of Pkg 2B on 19.05.2025 Delay in finacial closure Financial closure on 04.09.2020.Covid-19 Delay in handing over of hindrance free site . Surakachar Siding - Handed over on 24.05.2024 Removal of encroachment on SECL Land in Surakachar - Removed on 31.01.2024 Removal of encroachments in Krishnanagar - Removed on 10.08.2024 Non-closing of SECL Road in Urga – Kusmunda section - Closed on 09.11.2024 Non –removal of toilet block in Urga - Kusmunda section - Removed on 06.11.2024 Stoppage of work in Krishna Nagar area for demand of their rehabilitation & resettlement (156 Nos.) Introduction of Elephant under passes Modification /Shifting of overhead electrical lines. Changes in OHE alongwith size of bridges due to site requirement & by Railways. Changes in GSS to TSS supply of 220 KV in Jan’25 As per MoF circular dated:29.04.2026 followed by MoR circular dated:22.05.2026, Force Majeure invoked on 27.02.2026, with repercussions of 02 -04 months of extension. | No Delay | [5 empty] | ND | 16216.31 | 37447.7 | 21231.39 | 1.The primary reason is that the time value of money is not accounted for in the sanctioned railway estimate. Therefore, the impact of time is inevitable, even within the anticipated construction period. 2.The project primarily involves tunnelling, and the geological conditions encountered during construction were more fragile and challenging than those anticipated during the planning and estimation stage. | Uncertainity in Geological Condition, Market Inflation increase in cost of raw material | All efforts are being made to commission the project within the stipulated timeline, despite the significant challenges posed by the complex geological conditions of the Himalayan region.
2 | CR | NL | Baramati-Lonand | 1998-99 | 2002 | 64 | 2026-03-27 | 2026-03-28 | 1 year | 1. Land Acquisition Delays: Land acquisition was initially estimated under the earlier provisions. Subsequently, implementation of the RFCTLARR Act, 2013, revised compensation provisions, increased land requirement and acquisition formalities affected the availability of encumbrance-free land. | Land Acquisition |  | LA |  |  |  |  | 653 | 5942 | 5289 | 1.Increase in unit land rate. 2. Increased formation width to 7.85 mts. from 6.85m 3. The price escalation of Material, fuel, labor, etc increased the cost. 4. Increase in quantities of earthwork, bridges, station building, yards as per as on date design, Drawings, ESP, Project sheet etc all,. as per, technical & safety requirements and latest policy guidelines. 5. Adoption of USSOR-2021 rates for Phaltan-Baramati section. | Change in Scope of Work based on Actual Field requirement, Escalation in Land Acquisition value, Uncertainity in Geological Condition
71 | ECoR | DL | Brundamal-Jharsuguda- flyover connection for joining DN | 2009-10-01 | 2014 | 7 | Feb'26 | 2026-02-27 | 1 year | Delay in land acquisition and change of scope of work from earth work to providing viaduct in 1.1km length. | Land Acquisition |  | LA |  |  |  |  | 94.06 | 296.51 | 202.45 | Cost over run as per sanctioned revised estimate due to change of scope from flyover line in earth work formation to 2 nos of viaducts(1.1km length) and increase in land cost over period of time. | Change in Scope of Work based on Actual Field requirement, Escalation in Land Acquisition value
13 | ECR | NL | Seohar-Sitamarhi | 2006-07-01 | 2023 | 28 | 2026-03-27 | 2026-03-28 | 1 year | A. Land acquisition under progress. 1. Payment made to Sitamarhi District for land= Rs. 135 Crores(Rs. 100 Cr. on 25.09.2023 & Rs. 35 Cr. on 21.10.2023) 2. Payment made to Sheohar District for land= Rs. 266 Crores(Rs. 100 Cr. on 25.09.2023; Rs. 27 Cr. on 21.10.2023 & Rs. 139 Cr. on 11.08.2026) 3. Land acquisition completed in Sitamarhi District. Land acqusition for missed plots is in progress. 4. Since payment of Rs. 139 crore was made to Sheoahar on 11.08.2026, land acqusition is thus under progress. B. Tender floated for Sitamarhi- Rewasi(11.7 km) on 08.07.2025. Tender got discharged on and Tender was re-floated on 26.08.2026. C. After land acquisition for 95 % of core land in Rewasi-Sheohar Section, tender will be initiated. | Land Acquisition | [6 empty] | 0 | 0 | 0
28 | NR | NL | Chandigarh-Baddi © | 2007-08-01 | 2018 | 28 | 2026-12-26 | 2026-12-27 | 1 year | Due to NGT court case. Hon’ble Court of NGT on 10.12.2024 directed for use of minerals including earth from the sources that have the environmental clearances from the concerned State Authorities of Govt. of Himachal Pradesh and Haryana. Compliance on the directions have been ensured by M/o Railways | Law and Order Issue |  |  |  | LO |  |  | 150.14 | 150.14 | 0 |  | No Cost overrun | Work is in progress. The land acquisition in the State of Haryana and Himachal Pradesh completed (97.4422 Ha). Overall physical progress is about 50%
29 | NR | NL | Bhanupalli-Bilaspur-Beri © | 2007-08-01 | 2019 | 63 | 2026-12-26 | 2026-12-27 | 1 year | 1) Land acquisition in Himachal delayed. Still one patch affcting Major Bridge not acquired till Bilaspur Land acquisition from Bilaspur to Beri still not done. Sec 11 notifications were extended three times by GoHP and extension of sec 11 notification quashed by Hon'ble HC Shimla on 07.10.2026 2) Frequent troubles by locals to stop the work in Punjab, Tree cutting in Paharpur stopped by locals on payment issue.600 trees yet to be cut 3) Due to geology well foundation in 3 No Major bridges stuck and the design was changed to pile foundation abandoning the wells 4) Funds paucity and non cost sharing deposite by GoHP | Forest & Wildlife Clearance, Land Acquisition, Law and Order Issue | FC | LA |  | LO |  |  | 2400 | 13770 | 11370
26 | NFR | NL | Murkongselek-Pasighat | 2010-11-01 | 2016 | 27 | Nov-2025 | 2026-01-27 | 1.2 year | 1. Delay in land acquisition. EPC tender could be invited in the year 2022 only after completion of 90% land acquisition. LOA for composite EPC tender issued on 06.03.2023. 2. Climatic and local conditions: heavy and prolonged rainfall during the long monsoon season of the North-East region, which shortens the available working season; floods affecting bridge sites, borrow areas and access roads; and frequent hindrances and stoppage of work due to local disturbances and local bandhs. 3. For the approaches of Road Over Bridge No. 68 at Pasighat, land free from encumbrace handed over by the State Government on 12.06.2026. | Law and Order Issue |  |  |  | LO |  |  | 414.85 | 1249.35 | 834.5 | Cost increased from ₹414.85 crore (Detailed Estimate, 2016) to ₹1249.35 crore (1st Revised Estimate, April 2025), i.e. by ₹834.50 crore (201.15%): ₹540.70 crore (130.33%) due to price escalation and ₹293.80 crore (70.82%) due to reasons other than price escalation. A. Price escalation – ₹540.70 crore 1. Land – ₹298.35 crore: land cost revised from ₹31.48 crore to ₹317.07 crore at current land rates of Deputy Commissioner, Dhemaji (Assam) and Government of Arunachal Pradesh, with compensation under the Right to Fair Compensation and Transparency in Land Acquisition, Rehabilitation and Resettlement Act, 2013 (100% solatium and additional amount at 12% per annum). 2. Formation, Permanent Way, Bridges, Stations and Buildings – ₹218.23 crore: unit rates updated from 2016 rates to latest accepted rates. 3. Departmental charges, Electrical (General), Signal and Telecommunication and Mechanical – ₹24.12 crore. B. Other than price escalation – ₹293.80 crore 1. Road crossings and Permanent Way – ₹118.35 crore: new Road Over Bridge No. 68 for the road connecting National Highway 515 with Pasighat township; Road Over Bridges No. 1 and 11 changed from prestressed concrete girders to composite girders with longer length; Road Under Bridges/Limited Height Subways increased from 6 to 13; underpass at Sille station (₹91.54 crore). Loop line length increased from 4.8 km to 12.22 km and points and crossings from 14 to 33 as per approved yard plans; ballast cushion increased from 300 mm to 350 mm (₹25.64 crore). 2. Bridges – ₹81.55 crore: hydrological survey after sanction of Detailed Estimate required larger waterways – major bridges from 682.98 m to 1048.45 m (30.48 m spans changed to 45.70 m steel girders); minor bridges from 35 to 60, including 20 boxes for irrigation channels demanded by public representatives. 3. Formation – ₹44.25 crore: formation width increased from 6.85 m to 7.85 m (Advance Correction Slip No. 26 dated 10.01.2019 to Indian Railways Schedule of Dimensions); ground improvement (2.34 lakh cum) added as per latest Railway Board guidelines; catch water drains and breast walls in cutting increased from 3250 m to 6000 m. 4. Railway Electrification – ₹22.08 crore: new provision (31 km) as per Railway Board's instructions for 100% electrification. 5. Electrical (General) – ₹14.56 crore: high mast towers, solar lighting, shifting of 33 kV, 11 kV and low tension lines and underground cable crossings. 6. Stations and Buildings – ₹8.16 crore: high level platform area increased from 8226 sqm to 25200 sqm (platforms 630 m × 10 m at Sille and Pasighat), additional quarters, and Pasighat developed as a major station with rest houses, Railway Institute and health unit. 7. Signal and Telecommunication – ₹4.18 crore: additional lines at Pasighat and items left out in Detailed Estimate. 8. Departmental charges and hiring of vehicles – ₹14.97 crore; partly offset by reduction in land area (–₹12.76 crore) and Mechanical (–₹1.54 crore). | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value | 1. Project sanctioned in 2010-11; Detailed Estimate sanctioned in 2016 for ₹414.85 crore. 2. Work awarded on Engineering, Procurement and Construction mode to M/s Tracks & Towers Infratech Pvt. Ltd.; Agreement dated 08.05.2023 for ₹580.04 crore (₹685.01 crore after Change of Scope); Scheduled Completion Date 21.11.2025, presently extended to 31.12.2026. 3. Phase-I, Murkongselek–Sille (14.82 km): commissioned on 17.02.2026 after inspection by Commissioner of Railway Safety on 12-13.02.2026. 4. Phase-II, Sille–Pasighat (11.46 km): bridges, track linking, station buildings and Road Over Bridge No. 68 in progress.TDC of completion -January 2027 5. 1st Revised Estimate for ₹1249.35 crore (April 2025); Financial Internal Rate of Return 0.36%, Economic Internal Rate of Return 13.18%.
53 | WCR | NL | Ramganjmandi-Bhopal | 1999-00 | 2003 | 277 | 2026-12-25 | 2026-02-27 | 1.3 year | Work sanctioned in different Part Estimates, section wise from 2003 to 2019. Land acquisition delays, pending forest clearances and site-related constraints have adversely affected the progress of works, Land acquisition and possession finally completed in 2025. Forest permission in Rajasthan delayed Tunnel work . Less allottment of funds during intial years delayed the project and COVID -19 pandemic stalled works for almost 2 years. GAIL Pipe line crossing approval also took considerable time and finaly resolved and NOC given by GAIL on Sept 2026. | Phase wise Sanctioning, Land Acquisition, Utility Shifting |  | LA | PS |  | US |  | 675 | 5075 | 4400
68 | WR | GC | Miyagam-Karjan-Dabhoi-Samalaya NG | 2011-12-01 | 2017 | 91 | Dec'26 | 2026-06-28 | 1.6 year | Major factors for time and cost overruns since sanction of the project in April-2011. RECTS was approved April 2011. Fund allotted for FLS was limited, hence tender for only Geotechnical studies and preliminary exercise was called for in Dec’ 2011. The DE was prepared and processed in 2014 based on PE activities. DE was sanction in 2017. The delay due to (i) Part DE except FO & B/Pass was processed (ii) change of SOR and implementation of USSOR 2011. (ii) Finally decided whole estimate i.e Ground connection, FO & B/Pass. Inordinate delays/ time taken in Private Land Acquisitions by State Authority. Inadequate allotment of funds resulting in phase wise execution of project. In initial 04 years upto 2014-15, yearly allotment of fund was Rs 1 cr to 5 cr only. | Land Acquisition, Phase wise Sanctioning |  | LA | PS |  |  |  | 844.1 | 1015.07 | 170.97 | As the Detailed estimate vetted in 2017. Now Due to escalation and as the tenders are now being awarded in 2026, the cost of tenders has increased. Therefore the original sanctioned estimate of 844cr will now have to be revised. | Market Inflation increase in cost of raw material
14 | ER | NL | Tarakeshwar-Bishnupur (82.46 Km) with Ext up to Dhaniakhali(19 km) , Arambagh-Irphala (18.3 km) & new MM for Irphala-Ghatal (11.2 km) & Arambagh-Champadanga (23.3 km), Mayonapur-Kamarpukur (19 km) & Bishnupur – Uparsol (31.80 Km | 2000-01-01 | 2009 | 82 | Aug'16 | 2026-03-27 | 10.5 year | Work stopped at a stretch of 900m at Bhaba Dighi Pond between Goghat-Kamarpukur section since 2016, due to Law & Order issue. Case resolved on Dec'2025. | Law and Order Issue |  |  |  | LO |  |  | 1542 | 1680 | 138 | Excess expenditure due to revised scope of work | Change in Scope of Work based on Actual Field requirement
50 | SWR | NL | Tumkur-Chitradurg-Davangere © | 2010-11-01 | 2013 | 182 | 2019-03-01 | 2026-12-29 | 10.9 year | Delay in land acqusition - Land acqusition proposals submitted during 2012, 2013 & 2014. However the major portion of land was handed over in 2023-24 in strteches. Accodingly works are in progress wherever land is made available.249.76 A of land is yet to be handed over by GoK. | Land Acquisition |  | LA |  |  |  |  | 913 | 1801 | 888 | Rs.1801 cr is the detailed estimate sancctioned based on the FLS conducted. | Administrative reason
47 | SWR | NL | Kadur-Chickmagalur-Sakleshpur © | 1996-97 | 2014 | 68 | 2026-01-17 | 2026-12-28 | 11.6 year | Kadur -chikmagalur (46km) Land acquisition proposals were submitted to GoK in stages between Dec-1997 to 2009 based on allotment of funds by the Railway Board for Kadur -Chikmagalur section. The land was handed over by GoK in stages between 2000 to 2012. Accordingly the section was commisioned during 2013 Chikmagalur -Belur -(22Km) The Railway Board has frozen the project from the year 2007-13 • Delay in handing over of land between Chikmagalur (46Km) to Haddihalli (54.30 Km) to the extent of 70.28 Ha which falls in Chikmagalur district even though land acquisition requisition submitted during 2009-13.Land was hande d over in June 2022 only. Stage -II clearance for Forest land to the extent of 1.08 Ha is accorded in 05.07.2023 only, • Delay in handing over of land between Haddihalli (54.30 Km) to Belur (68 Km) to the extent of 61.01 Ha which falls in Hassan district even though land acquisition requisition submitted during 2013. Major portion of land was handed over in March 23. • Accordingly work was taken up as per land availability and Chikmagalur -hadihalli was commissioned in March 2025 and BAlance section Hadihalli -Belur was pllaned for commissioning during this year. Belur -Sakleshpur - dropped by State Govt and frozen by Railays. | Land Acquisition, Forest & Wildlife Clearance, Phase wise Sanctioning | FC | LA | PS |  |  |  | 546 | 825 | 279 | 1. General inflation i.e. the price escalation of Material, fuel, labor, etc increased the cost ( Basically due to delay in execution which is caused due to delay in land acqusition) 2. Increase in land cost and enhanced compensation due to court decrees. 3. Change in specifications as per latest guidelines, 4. Inlcusion of electrification 5. inclusion of new items due to public demand | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
51 | SWR | NL | Marikuppam-Kuppam | 2011-12-01 | 2013 | 24 | 2016-03-01 | 2026-03-28 | 12 year | Delay in land acqusition - Land acqusition proposals were submitted on 2014 & 2019. However complete land was handed over in 2023 and accordingly work is in progress . | Land Acquisition |  | LA |  |  |  |  | 99.64 | 279.54 | 179.9 | Rs.279.54 cr is the detailed estimate sancctioned based on the FLS conducted. | Administrative reason
56 | WR | NL | Chhota Udepur-Dhar (Tirla) | 2006-07-01 | 2012 | 147 | Sept.'18 | Feb 31 | 12.5 year | Delay due to complex geographical locations involving mountain terrain in Seismic Zone-V, sloping valleys, long detours, 50% project length in reserved forest area, where various specific conditions imposed by MoEF in stage-II approval given in July-25 are to be observed, intricate construction of viaducts, bridges and tall piers with heights ranging upto 52 m, high banks and deep cuttings upt 35 m in basalt rock involving technical challenges and complex issues of design. | Forest & Wildlife Clearance | FC | [5 empty] | 1347.26 | 4993.65 | 3646.39 | Detailed estimate sanction on 17.09.2012. Revision in cost due to following reason: 1. Quantity variation due to site conditions. 2. Due to change in specifications, instruction from Railway Board/Division. 3. Due to Award of Contracts. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material
21 | NFR | NL | Sivok-Rangpo | 2008-09-01 | 2015 | 44 | 2026-05-15 | 2026-12-27 | 12.6 year | Details given in the remark column | Forest & Wildlife Clearance, Land Acquisition | FC | LA |  |  |  |  | 4085 | 17125 | 13040 |  |  | Reasons for Time Overrun of Sivok–Rangpo New BG Railway Line Project Based on the contents of the last column of the attached document, the major reasons for time overrun are: 1. Delay in forest land diversion and statutory clearances: Additional forest land became necessary during execution due to mandatory ADITs for tunnel safety, expansion of Rangpo Yard, revised slope geometry at Riyang Yard, construction access roads and other ancillary facilities. Processing of additional proposals and statutory approvals delayed the availability of work fronts. 2. Unprecedented flash flood and closure of NH-10: The GLOF/flash flood of 04.10.2023 and subsequent road damage, landslides, road collapses and traffic restrictions disrupted construction activities. The assessed cumulative delay attributable to the flood and NH-10 restrictions during 2023–2025 was 311 days, affecting transportation of manpower, construction materials, explosives, fuel, machinery and muck. 3. Unforeseen adverse geological conditions in tunnels: Actual geological conditions differed substantially from tender-stage investigations, with a significant increase in weaker rock classes, fractured and weathered rock, squeezing ground, groundwater ingress and deformation. These conditions necessitated heavier support systems, additional rock bolting, steel ribs, shotcrete, fore-poling, re-support, re-excavation and stabilization, reducing tunnel excavation progress. 4. Increase in scope of work at Rangpo Yard: Railway-approved expansion from three to four lines necessitated additional track infrastructure, formation widening, retaining structures, slope protection, drainage, platforms, goods yard facilities, pit line, signalling, electrical works and additional land. The revised scope also required redesign, fresh approvals and additional forest land diversion. 5. Additional land requirement and site constraints at Riyang, Melli and Rangpo Yards: Unfavourable geotechnical conditions at Riyang necessitated flatter slopes and additional forest land. At Melli, additional land was required for staff quarters, muck dumping and Bridge No. 09 access road. At Rangpo, poor ground strata and deeper RE wall foundations required land beyond the available railway Right of Way. 6. Delay in yard works and associated infrastructure: Progress of slope protection at Riyang was affected by pending forest land diversion. Melli Yard works were affected by RE wall construction requirements and NH-10 restoration issues following the flood. At Rangpo, a portion of the RE wall fell outside the existing Right of Way, necessitating additional land acquisition and handover. 7. Extended duration of critical tunnel, bridge and yard works: Adverse geology, additional support requirements, land constraints, statutory approvals and revised scope have affected completion of Tunnel T-10, yard infrastructure, slope protection, track linking and bridge works, resulting in revised completion schedules extending into 2027. Conclusion: The time overrun is attributable to a combination of unforeseen geological conditions, extraordinary natural events and NH-10 disruptions, additional land and statutory clearance requirements, Railway-approved changes in scope, and consequent delays in critical tunnel, bridge and yard works. These factors have adversely affected construction progress and the overall project completion schedule.
48 | SWR | NL | Rayadurg-Tumkur via Kalyandurg © | 2006-07-01 | 2009 | 207 | Sept 2015 | 2026-05-28 | 12.8 year | Delay in land acqusition -Land acqusition proposals submitted in 2010,2011,2012,2013,2016,2017,2018 & 2019 in stages . However complete land was handed over in 2022,2024 & 2025 in stages.Work was taken up as per land availability and accordingly 83 Km out of 206 was commissioned . Work is in progress for the balance sections | Land Acquisition |  | LA |  |  |  |  | 857.3 | 4443.54 | 3586.24 | 1. General inflation i.e. the price escalation of Material, fuel, labor, etc increased the cost ( Basically due to delay in execution which is caused due to delay in land acqusition) 2. Increase in land cost and enhanced compensation due to court decrees. 3. Change in specifications as per latest guidelines, 4. Inlcusion of electrification 5. inclusion of new items due to public demand | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
24 | NFR | NL | Jogbani-Biratnagar(Nepal) | 2010-11-01 | 2010 | 19 | 28.01.2013 | 2026-12-26 | 13 year | Due to non-availability of Land of Biratnagar Yard (Nepal) and Fund from Ministry of External Affairs | Land Acquisition |  | LA |  |  |  |  | 239 | 467 | 228 | Slope protection: About 6 km on landslide-prone stretches. | Uncertainity in Geological Condition | Revised Project Estimate has been approved by Railway Board and forwaded to MEA for fruther sanction and release of fund.
55 | WR | NL | Dahod-Indore via Sardarpur, Jhabua & Dhar | 2007-08-01 | 2012 | 205 | June'17 | 2026-12-30 | 13.5 year | Allotment of inadequate funds for the project from 2007-08 to 2017-18. The Project was kept on hold between May-2020 & Dec-21 as advised by the Railway Board. Work was also delayed due to delay in land acquisition, change of alignment, Forest land issue and tunnal works. | Land Acquisition, Forest & Wildlife Clearance | FC | LA |  |  |  |  | 1640.04 | 9217.23 | 7577.19 | 1. Change in formation width from 6.85 m to 7.85 m & increase in formation height upto 30 m at different locations. 2. Reason for the cost escalation is the substantial increase in land rates from 2006–07 to 2024–25 3. 52 kg rails revised to 60 kg as per the new RB guidelines. Ballast cushion increase from 250mm to 350 mm as per the new RB guidelines. 4. All LC eliminate ap per RB policy. 5. Steel composit bridge provisioned now in place of PSC girder & Viaducts also from 2 to 20 as per latest instructions to keep formation height upto 15m. 6. High level P/F has been proposed as per latest Railway Board policy minimum Passanger aminities as per latest Railway Board policy. 7. Due to increae in length due to track numbers, bank height and increase in width from 2.44 to 6.1m. 8. As per Railway Brd policy Ty-I quarters have been replaced by Ty-II quarters and plinth area of Ty-II, Ty-III and Ty-IV increased. | Change in Scope of Work based on Actual Field requirement, Escalation in Land Acquisition value
57 | ECR | GC | Jaynagar-Bijalpura, incl. extn. Bet, Bijalpura-Bardibas (Nepal) | 2010-11-01 | 2015 | 69 | 2026-10-14 | 2026-05-29 | 14.7 year | Due to delayed Land Acquistion from Bijalpura to Bardibas,16.42Km by Govt. of Nepal, Land has been handed over in January 2026. | Land Acquisition | [6 empty] | 548 | 900.03 | 352.03 | Cost Over Run due to: 1. Price Escalation of various items 2. Use of 60 Kg Rails, Sleepers & fastening instead of 52 Kg as per latest Railway Guidelines. 3. Provision of Electronic Interlocking in place of Panel Interlocking. etc. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material
67 | WR | GC | Ratlam-Mhow-Khandwa-Akola and MM of Fatehabad-Chandrawati Ganj-Ujjain | 2007-08-01 | 2019 | 525 | March'13 | 2026-12-30 | 17.9 year | Due to difficult Geographical terrain detour alignment and delay in land acquisition including forest land. It Tunnel work and many Major and Minor bridges. | Land Acquisition |  | LA |  |  |  |  | 1656.25 | 13314.4666 | 11658.2166 | Change in Alignment mainly in Hilly areas and change in Bridge scheme. Also due to increase in width of embankment as per latest guidelines. | Change in Scope of Work based on Actual Field requirement
15 | ER | NL | Sultanganj-Katuria via Asarganj, Tarapur & Belhar | 2007-08-01 | 2008 | 77 | Aug'11 | 2026-03-31 | 19.5 year | Project is kept in abeyance vide Railway Board Letter No. 2019/W-1/Genl/Budget/1,New Delhi 24.09.2019 and De-freezing this Project vide Railway Board Letter No. 2025/W-II/Genl/ER/NL/08(e-3508749) Dated 26.09.2025. Alignment revision due to upcoming airport at Sultanganj, new road network and habitations has been done. Detailed estimate accordingly is under peparation. | Phase wise Sanctioning |  |  | PS |  |  |  | 291 | 291 | 0 |  | No Cost overrun
8 | ECR | NL | Koderma-Tilaiya | 2001-02-01 | 2004 | 65 | Feb'25 | 2026-02-27 | 2 year | Construction of 4 nos. tunnels (1175 m) and a Major Bridge No. 106 (30.5X 24 m Composite Girder) | Phase wise Sanctioning |  |  | PS |  |  |  | 599 | 2433 | 1834
27 | NR | NL | Nangal Dam-Talwara & Taking over siding of Mukerian-Talwara (29.16 km) | 1982-83 | 1985, 2001, 2003, 2008, 2019 | 123 | 2026-12-25 | 2026-12-27 | 2 year | Project remained frozen due to exorbitant land cost demanded by State Govt. from 1991 to 1996. The project was de-freezed on the assurance given by Himachal Government for providing the Govt. land free of cost. Then it was decided to continue the project block section wise. Formal re-start of work on the project by Hon’ble MR on 13.06.1998. | Land Acquisition, Phase wise Sanctioning |  | LA | PS |  |  |  | 72.49 | 4076.15 | 4003.66
33 | SCR | NL | Manoharabad-Kotapalli © | 2005-06-01 | 2016 | 151 | 2026-07-01 | 2026-06-29 | 2.11 year | State Govt of Telangana vide letter No.1261/Tr.(S&V) 12006, Dt.16.09 .2014, has given consent for the Payment of annuity for the first five years after commissioning of the Project in addition to sharing 1/3rd cost of construction of project and providing the land free of cost. The issues relating to land acquisition have been through continuous coordination and monitoring under the PRAGATI and Project Monitoring Group (PMG) mechanisms. The required private land (79.423 ha) in Karimnagar (38.173 Ha) and Rajanna Siricilla (42.35 Ha), has been handed over to Railways in May-26 and June-26 respectively. Stage-II Forest Clearance for 15.2105 ha of forest land in Rajanna Sircilla district has also been obtained in May-26 and at present, the reimbursement by the Government of Telangana of ₹10.10 crore towards additional forest clearance and other statutory charges initially borne by the Railways is still outstanding. The revised estimate amounting to ₹2,780.78 crore has been submitted to RB on 12.03.2024 and after compliances to the RB’s comments, the same has been sanctioned by RB on 10.07.2026. SCR has spent Rs.2221.37 Crs. up to end of Sep-2026. Corresponding share of State Govt. comes to Rs. 740.457 Crs. TS Govt. has deposited only Rs 431.15 Cr till date (Last deposit in Jan-2026). TS Govt. has overdue share of Rs. 309.307 Cr. CAO/C/SC vide Lr dt. 19.05.23 addressed to CS, Govt. of Telangana, for deposition of funds. Even after repeated requests by SCR to Telangana government for acceptance of enhanced cost, the latest being on 22.07.2026, as on date, the Government of Telangana has neither officially replied nor accepted the revised cost-sharing liability corresponding to the sanctioned Revised Estimate. | Forest & Wildlife Clearance, Land Acquisition, Phase wise Sanctioning | FC | LA | PS |  |  |  | 1160 | 2781 | 1621 | The increase in the project cost is predominantly due to additional scope and quantities arising from actual site conditions, incorporation of revised technical guidelines, changes in alignment and additional infrastructure requirements. These provisions were considered essential to ensure operational safety, compliance with prevailing Railway standards, adequate infrastructure facilities and long-term operational efficiency. The cost variation is therefore attributable mainly to changes in scope and technical requirements during execution and are elaborated as below; Formation Works: Increase in bank and cutting widths as per latest guidelines, provision of additional formation due to yard gradient requirements, and additional walling, retaining walls and side drains based on actual site conditions and topography. Permanent Way: Additional provisions for service tracks, SEJs, re-railing ramps and SEJ sleepers; revision in points and crossings from 1:8.5 to 1:12; and increase in points, crossings and loop lines as per site requirements. Road Crossings / ROBs / RUBs: Increase in the number of ROBs from 7 to 27, including additional ROBs introduced at the request of the State Government to avoid habitation areas near newly formed district headquarters. Bridge Works: Changes in bridge alignment and design due to developments such as the MI tank and Manair reservoir on the downstream side. Additional major and minor bridges necessitated by new irrigation systems and site requirements in Telangana. Station Buildings: Additional provisions for station buildings, subways, HLPFs, PF shelters, approach roads, circulation areas and Goods platforms/sheds in accordance with contemporary guidelines. Other Service & Residential Buildings: Provision of RBGE rooms at crossing stations, adoption of latest prescribed building rates and additional officers' rest houses at Manoharabad, Siddipet and Vemulawada. Transportation & Miscellaneous: Additional provision of vehicles for officers and inspection/supervision requirements, along with miscellaneous works based on actual site requirements. General Charges: Proportionate increase in general charges consequent to the increase in the overall project cost. | Change in Scope of Work based on Actual Field requirement
16 | ER | NL | Pirpainti-Jassidih © | 2013-14 | 2018 | 97 | 2026-07-27 | 2026-03-29 | 2.6 year | 1. The project was sanctioned in 2013-14 on cost sharing (50:50) basis with Govt. of Jharkhand and Ministry of Railways. MOU for the project was signed by Eastern Railway and Govt. of Jharkhand on 17.02.2017. 2. In Sept'2019, Govt of Jharkhand communicated Railway to postpone the project between Godda - Pirpainti vide letter No.21/2012, dated.18.09.2019 due to coal block in the alignment between Mahgama to Meherama. 3. In Nov'2022, part of this project was re-sanctioned for execution by Railway themselves from its own resources i.e 100% vide Railway Board Letter No.2013/W- 2/ER/NL/15(MOU) Dated.16.11.2022 on revised alignment with change in alignment for 21.58 Km (CH 63.700 to CH 85.280) owing to avoiding coal blocks. 4. Section between Mohanpur-Hansdiha (38.11 Km) has been commissioned in March'2023. 5. For section Godda(31.892 Km) to Mahgama (58.415 Km), required Private land (168.825 Ha) received in June'2026 and the work is in progress. Transfer of 11.68 Ha Govt land is pending. 6. For section Mahgama(58.415 Km) to Pirpainti(94.298 km), 20F of required private land (179.89 Ha) in Jharkhand has been completed in Oct'2026. Transfer of 26.78 Ha Govt land is pending. For Bihar portion, required private land (34.816 Ha) received in July'26 and transfer of 2.545 Ha Govt land is pending. 7. Issue of transfer of Govt land from Govt of Jharkhand is being discussed in PMG meetings also. | Land Acquisition |  | LA |  |  |  |  | 2138 | 2138 | 0 |  | No Cost overrun
19 | NFR | NL | Jiribam-Imphal | 2003-04-01 | 2005-13 | 111 | 2026-12-26 | 2026-12-28 | 24 months | Geological challenges, law and order issues, road blockades, have reasoned the aforementioned delay. | Law and Order Issue |  |  |  | LO |  |  | 4454 | 21886 | 17432 | 1. Basis of the original estimate: The original sanctioned estimate for the Tupul–Imphal section was based on the per-RM cost of the Jiribam–Tupul section. The cost later changed in line with the rates for each item in the contract agreements. 2. Tunnelling: Weak geological strata were encountered, so the tunnelling methods were changed on the advice of the DDC. This caused a cost overrun. 3. Track structure: 52 kg rails were replaced with 60 kg rails, and more loop lines were added. 4. Ruling gradient: The ruling gradient was changed from 1 in 80 to 1 in 70. This changed the length of the tunnels and the number of other civil engineering structures. 5. Realignment at Tupul: Because of the landslide at Tupul, the alignment was changed and a tunnel was added. 6. Adit lining: The original estimate had no provision for adit lining. It was added in the RE. 7. Upgrading of bridges: Some minor bridges were converted to major bridges on the recommendation of the TAG. 8. Land acquisition: More land was acquired to meet site requirements. 9. Tunnel portal and protection works: Tunnel portal extensions and protection works were added in the RE. | Change in Scope of Work based on Actual Field requirement, Uncertainity in Geological Condition, Escalation in Land Acquisition value, Market Inflation increase in cost of raw material
1 | CR | NL | Ahmednagar-Beed-Parle Vaijnath © | 1996-97 | 2008 | 261 | The first block secton Ahmednagar to Narayandoho was authorized by Commissioner of Railway safety for opening of the section for passenger traffic on 21.03.2017 | 2026-03-27 | 3 year | 1. Part Detailed Estimate sanctioned for Ahmednagar-Narayandoh Section (First 15 km) (13.85 Cr) only. Part Detailed Estimate sanctioned on 02.05.2008 for remaining section of Narayandoh-Parli(448.81 Cr) with a total sanctioned cost of Rs 462.67 Cr for the whole project Ahmednagar Beed Parli vaijnath. 2. Railway Board advised to review the revised estimate in light of Railway Board guidelines on elimination of Level Crossings and also advised to eliminate those facilities which are not directly linked to the project. Earlier Revised Estimate of Rs 2747.82 Cr for Narayandoh-Parli section has been reviewed and modified cost of Rs 2271.5 Cr (Rs 72.05 Cr sanctioned cost +Rs 2199.45 Cr proposed cost) & Revised Detailed estimate sanctioned at the total cost of Rs 2271.5 Cr on 06.11.2015. Further, Material Modification estimate for railway electrification sanctioned at a cost Rs 267.17 Cr with total cost of project Rs 2538.67 Cr. 3. Land acquisition delays & due to court stay in 1.48 Ha & 0.27 Ha in Hatola village. Land Acquisition was also affected during the COVID-19 pandemic period. 4. Forest land of 17.60 Ha was involved for which final approval conveyed by GOI, MoEC on 17.06.2022. Further, additional forest land of 0.20Ha was involved for which final approval conveyed by GOI, MoEC on 26.09.2024. 5. Court litigations & disputes: Multiple ongoing legal cases and land compensation disputes. 6. Local agitation & protests: Recurring public resistance and work stoppages by displaced villagers demanding settlement and compensation. 7. Utility Shifting Obstacles. | Phase wise Sanctioning, Forest & Wildlife Clearance, Land Acquisition, Law and Order Issue, Utility Shifting | FC | LA | PS | LO | US |  | 462.67 | 5800 | 5337.33 | 1. Heavy increase in rates of material, land purchasing rate and labour. 2. Land acquisition rates are increased due to new land acquisition act-2013. The original provision of land was 1407.52 Ha but as of now total land acquired is 1837.01 Ha. 3. As per Railway board guideline from time to time providing the RUB/Limited height subway in lieu of Level crossing gates, the formation level was to be revised to accommodate the RUB's. after revision of ruling gradient the length of high banks & deep cuttings, are increased which has resulted in increase in quantity as well as recent guideline the width of formation has been increased and also change in gradient in Yard limit. 4. As per Railway board guidelines from time to time level crossings gates are eliminated. Hence, the Nos. of RUB and ROB's has been increased. As of now total ROBs are 67 Nos. & total RUBs are 136 Nos. as compared to 20 Nos. ROBs and 16 Nos. RUBs in survey report. 5. Based on the prevailing geological conditions encountered at the site, the number of minor bridges has increased from 198 nos., as envisaged in the original survey report, to 302 nos. as of date, resulting in an addition of 104 nos. of minor bridges. 6. Cost of side drain exceeded due to concrete/stone masonary drains as per revised specification of Para 6.5 of guidelines for earthwork in Rly projects July 2003 of RDSO in place of Kuttcha drain as proposed earlier. 7. Heavy increase in Royalty charges by State Government from Rs.200 per brass to Rs. 400 per brass vide Notification dated 11.05.2015 from Revenue and Forest Department. Further, it was increased from Rs. 400 per brass to Rs. 600 per brass vide Notification dated 04.06.2021 from Revenue and Forest Department. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value, Uncertainity in Geological Condition |  | It looks like you didn't include a specific question or prompt. Please let me know what calculation, lookup, or formula you would like to create based on your sheet data!
20 | NFR | NL | Dimapur-Kohima | 2006-07-01 | 2015 | 82 | 2026-03-26 | 2026-12-29 | 3.8 year | The time overrun is mainly due to extremely poor geology: predominantly shale and shale-sandstone strata with geological faults. Heavy rainfall during an extended monsoon triggered landslides at Ch 39300–39650, Pherima yard, Piphema yard, Zubza yard and other locations, so slope protection measures have had to be designed and executed. Severe squeezing and water ingress have slowed underground excavation in Tunnels. Progress in Tunnel 7 (6520 m), the most critical tunnel in this phase, is slow because no adit is available and there is high water ingress at multiple locations. Work at its Portal 1 could start only in February 2024, after villagers’ land objections to the 12.5 km approach road were resolved in October 2023 through the Government of Nagaland. Frequent local hindrances to working, vehicle movement and night work also arise because, under Article 371(A), land and forest belong to individuals or communities. | Land Acquisition, Law and Order Issue |  | LA |  | LO |  |  | 2315 | 15607 | 13292 | The cost over run is mainly due to: 1. Tunnels: Rock was much weaker than in the GIR, with faults and squeezing. This necessitated increased support (SDR anchors, pipe roofing, variable ribs), thicker reinforced lining and waterproofing. 2. New tunnel scope: Adits , cross passages and cut-and-cover tunnels had to be constructed for safety during construction and long term safety. 3. Slope protection: About 8 km on landslide-prone stretches required to be protected by elaborate slope protection measures. 4. Bridges: Five minor bridges converted to major bridge due to erodible strata, new Br. No. 172A, and an extra span on Br. No. 171 had to be provided as per site requirement. | Change in Scope of Work based on Actual Field requirement, Uncertainity in Geological Condition
54 | WCR | NL | Lalitpur-Satna, Rewa-Singrauli & Mahoba-Khajuraho | 1997-98 | 2023 | 541 | 2026-03-27 | Feb 31 | 3.9 year | Work sanctioned in different stages section wise from 2001 for land and upto January 2023. Land acquisition and possession delayed the Project considerably, work stopped for Job against Land also. Forest clearance for Sidhi-Singraulli recievd in February 2025. Less allottment of funds during intial years delayed the project and CORONA stalled works for almost 2 years. Panna-Ajaygarh section gradient and alignment finalisation took considerable time. | Phase wise Sanctioning, Land Acquisition, Forest & Wildlife Clearance | FC | LA | PS |  |  |  | 1755 | 8914 | 7159 | Due to acquisition of additional land & increase in the number of minor bridges. Length of project increased from 262.00 Kms. to 276.596 Kms. & Formation width of 7.85 meters instead of the originally planned 6.85 meters. Length of project from 262.00 Kms. to 276.596 Kms., upgrading of three D-class stations to B-class stations, the use of 60 kg rails instead of the sanctioned 52 kg rails, as approved in the Material Modification, additionally, the ballast cushion has been increased to 350 mm from the originally planned 300 mm. Earlier there was no cost of electrification of track is included in the estimate, the increase in cost is due to cost towards 2x25 KV OHE electrification.Due to increase in number of power line crossings to be modified and increase in cost for modification of power line crossing. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
11 | ECR | NL | Araria-Supaul | 2008-09-01 | 2018 | 96 | 2026-03-24 | 2026-03-28 | 4 year | 1. Whole stretch lies in the Kosi River belt. Very limited working season due to frequent rain and flooding in Borrow area. Also, this belt has very high water table. 2. Insufficient fund to this project in the initial day due to COVID. 3. Acquisition of Land delayed due to unavailabilty of fund. | Land Acquisition |  | LA |  |  |  |  | 1605.17 | 4020.63 | 2415.46 | 1. Cost land increased significantly. 2. Due to increase in height of embankment throughout the section so that potential Level crossing can be eliminated. Bank height increased to provide the vertical clearance for NH & RCD for RUBs with minimum clear height of 5.50m. 3. Increase in scope of major bridges & LHS at the places where Pucca/Bituminous road already available during construction, 4. Increase in blanket thickness from 300mm to 550mm as per latest RDSO guidelines, 5. Increase in road network in the project length which ultimately increases the scope of RUBs significantly. | Change in Scope of Work based on Actual Field requirement, Escalation in Land Acquisition value
58 | NCR | GC | Gwalior-Sheopurkalan with extension to Kota | 2009-10-01 | 2021 | 284 | Dec'24 | 2026-12-28 | 4 year | Sanction received in 2021 and permission for closure of GC line. Further, revised estimate is pending of sanction. | Phase wise Sanctioning |  |  | PS |  |  |  | 2294.63 | 2912.96 | 618.33
79 | SWR | DL | Hospet-Hubli-Londa-Tinaighat-Vasco-de-Gama | 2009-10-01 | 2019 | 312 | Sept 2024 | 2026-12-28 | 4.3 year | Total length 311.48 km, Commissioned length 260.83 km , Work in progress 12.6 km , Balance 38 km is passing through Wildlife sanctuary. Forest/Wildlife clearance is not received. Hence work is on hold. | Forest & Wildlife Clearance | FC | [5 empty] | 2127 | 5028 | 2901 | 1. Hubli byepass 12km Double line is newly added in the scope of work 2. Land acquisition cost increased due to enhancement by Courts 3. Formation width increased from 6.85 to 7.85 km as per policy 4. Track spacing increased at Major Bridge approaches 5. No of loop lines increased in approved ESP as compared to Abstract Estimate. 6. Increase in sleeper cost from Rs1422 to Rs2669 and Rail cost from Rs58811 to Rs 79431 7. Ballast cushion increased from 300 to 350 mm 8. Construction 9 RUBs to eliminate LCs | Change in Scope of Work based on Actual Field requirement, Escalation in Land Acquisition value, Market Inflation increase in cost of raw material
23 | NFR | NL | Balurghat-Hilli | 2009-10-01 | 2010 | 30 | 2026-03-27 | 2026-08-27 | 5 month | Work was stooped since 2013 due to paucity of fund and then it was freezed on 24.09.2019 by Railway Board vide D.O. Letter No. 2019/W-1/Genl./Budget/1 dated 24.09.2019. | Phase wise Sanctioning |  |  | PS |  |  |  | 171.01 | 1181.09 | 1010.08 | 1. The project was sanctioned vide Rly Board's letter no. 2007/W1/NL/NF/Balurghat – Hili dtd.29.12.2010, at a total sanctioned Detailed Estimate cost of ₹242.22 crore. 2. Project was kept in abeyance vide Railway Board L.No.2019/W-1/Genl./Budget/1 Dt. 24.09.2019. 3. De-freezing of project has been done vide Rly. Board order no. 2022/W-1/NFR/NL/Hili– Balurghat dt. 08.03.2022. The major reasons for the cost overrun are detailed below: 1. Price Escalation: Increase in the cost of materials, labour, machinery and other construction inputs since the original sanction in 2010. 2. Land Acquisition: Increase in formation width from 6.85 m to 7.85 m, additional land requirements due to revised formation levels, and increase in land acquisition rates. 3. Formation and Earthwork: Substantial increase in earthwork quantities due to revised formation width, higher formation levels considering the High Flood Level (HFL) in flood-prone areas, additional sand filling in marshy stretches, and provision of drainage and protection works. 4. Permanent Way: Additional provisions for 60 kg rails, wider sleepers, increased loop and siding lengths, 22 Road Under Bridges (RUBs) in lieu of level crossings, increased ballast cushion, additional points and crossings, and other track-related requirements as per revised Railway Board guidelines. 5. Bridges: Increase in bridge dimensions due to revised formation width, modification of minor and major bridge spans based on site requirements, provision of a Road Over Bridge (ROB) in lieu of Level Crossing No. 1, and adoption of revised bridge design provisions. 6. Station Buildings and Passenger Amenities: Additional provisions for high-level platforms, station buildings, passenger shelters, subways, circulating areas, approach roads, goods facilities and other infrastructure as per approved Engineering Scale Plans (ESPs). 7. Signalling and Telecommunication: Provision of Multi Aspect Colour Light Signalling (MACLS), Electronic Interlocking (EI), UFSBI, HASSDAC, MSDAC, fire alarm systems, IP-MPLS, VOIP and other modern signalling and telecommunication facilities as per revised Railway Board guidelines. 8. Electrical Works and Railway Electrification: Additional provisions for 33 kV underground cable crossings, electrical installations, equipment and railway electrification, which were not adequately covered in the original estimate.. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value, Administrative reason | 1.BLGT- HILLI New BG line was sanctioned vide Rly Board's letter no. 2007/W1/NL/NF/Balurghat – Hili dtd.29.12.2010. 2.Project was kept in abeyance vide Railway Board L.No.2019/W-1/Genl./Budget/1 Dt. 24.09.2019. 3.De-freezing of project has been done vide Rly. Board order no. 2022/W-1/NFR/NL/Hili– Balurghat dt. 08.03.2022. 4.Total LA processed for 156.38 Ha land and total ₹ 334.91 Cr paid to Distt. Authority. Total 156.38Ha (100%) land has been handed over to Railway. Planning for commissioning :- (a) Balurghat - Kamarpara (13.787km) – EPC tender for Civil, Electrical (Gen and TRD) and S&T works combined has been awarded on 04.03.25. Work is in progress. TDC for commissioning: May, 27. (b) Kamarpara –Hili (15.187km) – EPC tender of Civil, S&T and Electrification works was awarded on 15.10.25. Work is in progress. TDC- Aug, 27.
76 | NR | DL | Anand Vihar-Tilak Bridge 3rd & 4th line | 2012-13 | 2016 | 20 | 2026-03-23 | 2026-06-28 | 5.3 year | Delay in approval for Tree felling Permission | Forest & Wildlife Clearance | FC | [5 empty] | 296 | 702 | 406 | Cost increased due to revision in Yamuna Bridge Design/Drawing as per new Inland waterway Authority guidelines and site soil condition, inclusion of CA Land cost, formation retaining wall (constructed for restricting formation width to minimize tree | Change in Scope of Work based on Actual Field requirement, Uncertainity in Geological Condition, Escalation in Land Acquisition value
4 | ECoR | NL | Khurda Road-Bolangir © | 1994-95 | 2002-2016 | 301 | 2026-07-21 | 2026-02-27 | 5.8 year | 1. Detailed survey & Sanction of Detailed Estimate in Phases: a. Khurda Bolangir Project was included in budget (Pink Book) in 1994-95 with token fund allocation. b. Subsequently, detailed survey was taken up and interim report was submitted in September-1998. c. Part detailed estimate were sanctioned in 4 stages commencing from Jun-2002, last being in Jun-2016. 2. Delay in handing over of Pvt. Land a. Only 30% of private land handed over till 2014-15 b.Land Acquisition got momentum after signing of MOU with Govt. of Odisha in 2015-16 c. Major land was made available from 2018-19 onwards. 3. Delay in receiving forest clearance: a. Last forest clearance was received in May-2023 for Km.112-180 (Daspalla-Purunakatak). 4. Fund Allocation: a.Inadequate fund allocation in the initial years up to 2013-14. | Forest & Wildlife Clearance, Land Acquisition, Phase wise Sanctioning | FC | LA | PS |  |  |  | 353.38 | 6100 | 5746.62 | 1. Inclusion of 7 nos of Tunnels between Daspalla to Purunakatak of total length 12687mtr which were not in the sanctioned detailed estimate. 2. Increase in formation width i.e. 6.85m to 7.85m as per Railway Board guideline. 3. Increase in nos. of ROBs from 32 to 44nos to avoid level crossings in new line. 4. Introduction of viaduct over Brutang reservoir of length 4741m viz. Br.302 (182x24.4m) i.e. viaduct throughout the Brutang reservoir to keep the hydraulics of the reservoir unaffected as per the direction of water resource dept. Inclusion of another 3nos of Viaducts viz. 338A (11x24.4m), 430A (21x24.40m) & 435A (48x24.4m) to avoid earth filling in bank upto a height 25m (max) and to protect forest cover. 5. Increase in major bridge length from 4156m to 13470m including Elephant passages w.r.t last sanctioned estimate. 6. Provision of Electronic Interlocking with MACLS as against MLQ signaling and integrated communication for Tunnel. 7. Number of Powerline crossing has been increased. 8. Adoption of latest accepted rates such as USSOR-2019, CPWD-2018 in most of the contract which enhance the cost. | Market Inflation increase in cost of raw material, Change in Scope of Work based on Actual Field requirement
73 | ECoR | DL | Bhadrak-Nergundi 3rd line (80 km) | 2011-12-01 | 2015 | 92 | Oct'2020 | 2026-04-27 | 6.6 year | 1. Delay in land acquisition and handing over of the required land to the contractor. 2. Non-availability and shortage of essential construction materials, such as earth, moorum and sand. 3. Termination of the existing contract due to non-performance/delay in execution of the work. 4. Time consumed in the process of preparation, invitation and finalization of a fresh tender and award of the new contract. 5. Unfavourable weather conditions and monsoon-related interruptions affecting earthwork and other construction activities. | Land Acquisition |  | LA |  |  |  |  | 558.67 | 1600 | 1041.33 | Due to an increase in the scope of work beyond the originally approved provisions and price escalation in construction materials, labour, machinery and other inputs during the execution period. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material
65 | WR | GC | Bhuj-Naliya with extn. From Naliya to Vayor (24.65 km) | 2008-09-01 | 2008 | 126 | 2026-08-19 | 2026-02-27 | 6.7 year | Detailed estimate for Bhuj - Naliya (101.25 kms) costing Rs. 321.62 crores sanctioned by Rly Board on 07.08.2014. Railway Board , vide letter No. 2014/Infra/12/18 Dated 05.08.2016 decided that the project will be implemented through joint venture route with RITES under participative Model Policy 2012. However, in terms of Railway Board’s letter No.99/W-1/GC/Bhuj- Naliya/Part Dated 02.09.2016, Railway Board allowed the Western Railway to execute the targeted section i.e. Bhuj-Desalpur section (First 30 Km.) of the project. Accordingly, Western Railway executed Bhuj-Desalpur section and the CRS inspection was done on 16.08.2017. Due to failure of the concessionaire M/s BNV Gujarat Rail Pvt. Ltd. to take up the work forward, M/s G-RIDE was identified this work for further development. - G-RIDE vide letter No. G-RIDE/Bhuj-Naliya Project/Dir MTP/2020-1007 Dated 05.08.2020 expressed their inability to undertake the above project. - Bhuj-Desalpar (30 Km) section was already commissioned in the year 2017 by Western Railway. - The Gauge conversion Project between Bhuj – Naliya (for 72.50 Kms) was allotted back to Western Railway on 28.04.2022. - Desalpar-Naliya was commissioned in Oct'24. - Naliya-Vayor as extension was sanctioned in 2023-24. | Phase wise Sanctioning |  |  | PS |  |  |  | 321.62 | 1696.0324 | 1374.4124 | Delay in finalisation of executing agency. Sanction of Naliya-Vayor as extension to main Project. | Administrative reason, Change in Scope of Work based on Actual Field requirement
69 | CR | DL | Kalyan-Kasara - 3rd line | 2011-12-01 | 2015 | 68 | 2026-03-21 | 2026-03-28 | 7 year | Reasons for Delay of Kalyan-Kasara 3rd Line Project 1. Alignment Change: o As per CTPM & COM letter no. TW/KYN-KSRA 3rd line/194-N, dated 02.06.2015, the track alignment was shifted from the west to the east in four sections to prevent surface crossings that would disrupt train operations and suburban punctuality 2. Land Acquisition Challenges: o The project was impacted by the implementation of The Right to Fair Compensation and Transparency in Land Acquisition, Rehabilitation and Resettlement Act, 2013 instead of the Railway Act, 2008. o Delay in Land acquisition from State Govt. particularly forest land. 3. Revision in Track Centre: o The track center between existing line to 3rd line was revised from 6.8m to 7.8m as per Railway Board’s letter no. 2011/CE-II/From/misc dated 11.09.2015. o This required modifications to project sheets, ESPs, and increased land acquisition. 4. Provision of 4th line between Kalyan to Asangaon o Due to Provision of 4th line between Kalyan to Asangaon which necessitated revision of the ESPs and project sheets of the Kalyan–Asangaon 3rd line project, resulting in further delay. | Land Acquisition, Forest & Wildlife Clearance, Phase wise Sanctioning | [6 empty] | 792.89 | 1421.84 | 628.95 | 1. Change in the Alignment 2. Increase in Track centre 3. Increase in Land cost 4. Major bridges increased from 7 to 8 5. New 3 ROBs are to be constructed 6. Increase of minor bridge opening from 900 mm to 1200 mm | Change in Scope of Work based on Actual Field requirement, Escalation in Land Acquisition value
5 | ECoR | NL | Talcher-Bimlagarh | 2003-04-01 | 2007 | 154 | 2026-03-22 | 2026-03-29 | 7 year | (i) Land acquisition delays. (ii) Fragmented land possession: Patch-wise land availability prevents continuous track laying and earthwork by contractors. (iii) Court litigations & disputes: Multiple ongoing legal cases and land compensation disputes. (iv) Local agitation & protests: Recurring public resistance and work stoppages by displaced villagers demanding settlement and compensation. (v) Utility Shifting Obstacles. | Land Acquisition, Law and Order Issue, Utility Shifting |  | LA |  | LO | US |  | 726.96 | 4754.52 | 4027.56 | (i) Market Inflation of Construction Materials & Fuel. (ii) Escalation in Land Acquisition Compensation. (iii) Contractual Price Variations. (iv) Technical Scope creep & Engineering Revisions. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
72 | ECoR | DL | Kirandul-Jadgalpur (150 km) | 2011-12-01 | 2013 | 150 | Mar'2020 | 2026-04-27 | 7.1 year | Most of the works in the section have been completed. However, delay in land acquisition has affected the execution of the balance works. The project passes through Naxalite-affected areas of Bastar and Dantewada districts of Chhattisgarh, where restricted working hours and security-related constraints have adversely affected the progress of works. Further, execution involves hard-rock excavation and blasting in the proximity of the existing running track, necessitating traffic and power blocks, which has also constrained the working time and contributed to the delay in completion of the balance works. | Land Acquisition, Law and Order Issue |  | LA |  | LO |  |  | 1143 | 1798 | 655 | The excess over the approved deposit is mainly due to cost overrun on account of frequent interruptions by anti-social elements, delay in tree cutting permission/felling by Forest Dept., land ownership issue w.r.t. FCA 1980, reduction in working hours, inaccessibility, difficult hilly terrain, delay in establishing CORAS camps by State Govt. of C.G., getting land from State Govt. for CORAS multiple times cancellation of tenders due to poor response to open tenders, as well as price escalation over the period | Administrative reason
52 | SWR | NL | Gadag-Wadi © | 2013-14 | 2017 | 257 | 2026-05-23 | 2026-03-31 | 7.10 year | The time overrun in the Gadag–Wadi New BG Railway Line Project is primarily attributable to delayed and phased handover of land, pending forest clearance, local issues and other site-related constraints. Land was handed over to the Railways in phases, as detailed below: Koppal District: Out of the total 1,374.00 acres of land required, 1,213.12 acres have been acquired and handed over, with possession received during 08.03.2017 to 14.06.2019 and 13.12.2019 to 29.05.2020. The balance land of 160.88 acres is yet to be handed over. Raichur District: Out of the total 1,155.00 acres of land required, 1,101.37 acres have been acquired and handed over, with possession received on 24.08.2023. The balance land of 53.63 acres is yet to be handed over. Yadgir District: Out of the total 1,398.425 acres of land required, 1,323.07 acres have been acquired and handed over, with possession received during 20.04.2018 to 20.06.2019, and on 26.05.2020 and 06.07.2020. The balance land of 75.355 acres is yet to be handed over. Kalaburagi District: Out of the total 328.50 acres of land required, 303.925 acres have been acquired and handed over, with possession received during 16.12.2017 to 18.09.2019. The balance land of 24.575 acres is yet to be handed over. Forest Land – Koppal: 9.25 acres of forest land is required, for which Stage-I Forest Clearance is awaited. Forest Land – Raichur: 39.275 acres of forest land, lease agreement was signed on 23.08.2023 and working permission obtained. Overall Land Status: Against the total land requirement of 4,304.450 acres, including forest land, 3,980.760 acres have been acquired/handed over, while the balance 323.690 acres is yet to be handed over. Further, several critical issues persist in certain sections where land has already been handed over to Railways, affecting the progress and execution of project works. Land acquisition delays, pending forest clearances and site-related constraints have adversely affected the progress of works, resulting in time overrun in the project. | Forest & Wildlife Clearance, Land Acquisition, Law and Order Issue | FC | LA |  | LO |  |  | 1922 | 7000 | 5078 | 1. General inflation i.e. the price escalation of Material, fuel, labor, etc increased the cost ( Basically due to delay in execution which is caused due to delay in land acqusition) 2. Increase in land cost and enhanced compensation due to court decrees. 3. Change in specifications as per latest guidelines, 4. Inlcusion of electrification 5. inclusion of new items due to public demand 6. Inculsion of Tunnel length of 7575m in the Gurgunta Shorapur section as per the Ruling Graient of 1 in 150 | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
9 | ECR | NL | Hajipur-Sagauli via Vaishali | 2003-04-01 | 2007-2008 | 151 | Mar'20 | 2026-06-27 | 7.3 year | 1. Project was sanctioned in the year 2003-04..The work for new line between HJP-SGL was started in Dec’08 after DE sanction. But, allocation of fund was not sufficient to cater the demand of land cost along with contractual expenditure till year 2014-15. 2. Inconsistent fund allotment in initial year i.e. up to year 2015 led to delay in land aquisition. Apart from above, delay in handing over of land under Dist.-Motihari (East Champaran) in spite of payment made for all land to be acquired up to year 2017. Handing over of Land under Dist.-Motihari by State Govt started since year 2022 and complete handover done in year 2025. Also during execution a lot of obstruction was faced from land looser due to their non-payment of land cost, dispute etc. which was subsequently resolved by police force deployment. 3. Further lot of time taken in exchange of land in around one Km from Canal Division, Muzaffarpur which falls between section Deoria Sahebganj. Due to this delay in exchange of land with Canal Division (approval by Bihar Cabinet), handed over in January 2025 with work permitted in March 2025, which was subsequently stopped due to canal land area being Protected Forest, progress of work hampered. Forest clearance proposal applied on 03.04.2025, Stage 1 clearance granted on 31.12.25, and subsequntly tree cutting permission issued in June 2026. | Forest & Wildlife Clearance, Land Acquisition, Law and Order Issue | FC | LA |  | LO |  |  | 528.65 | 3991.33 | 3462.68 | 1. Due to increase in cost of Land Acquisition as per prevailing Land Acquisition Act. 2. Initially it was planned to provide LCs, accordingly embankment height was fixed as average height of 3.0m. The section from Hajipur to Vaishali was commissioned with provision of LCs. Meanwhile, due to change in policy, LCs are eliminated by providing the RUBs between Vaishali & Sagauli section. Subsequently, embankment height was revised as average 5.7m from Vaishali to Sagauli. Also, as per the revised IRSOD, the minimum formation width has been changed from 6.85m to 7.85m. 3. Initially, in Hajipur-Vaishali (35.0Km) section, 300mm blanketing layer was considered. Meanwhile, due to revision of RDSO guidelines (RDSO specification no.-RDSO/2020/GE:IRS-0004, Sept'20), 550mm thick blanket layer has been considered in Vaishali-Sagauli (115.763Km) section. 4. Due to raising of embankment height to provide RUB/LHS to eliminate LCs in line with Rly Board policy, additional land acquisition was involved as there are only 40m land width was acquired in the HJP-SGL section. To overcome the tedious & time taking (about 1.5 to 2 yrs) procedure of land acquisition and in view of target for opening of the section, it is planned to provide retaining wall in approx. 24.40Km route length (Total 48.80 Km) in Vaishali - Sagauli section. 5. Due to change in specification of track structure per IRPWM. 6. Due to change in policy, various passenger amenities work has been considered as per minimum essential amenities guidelines issued by the Rly Board. Also conversion of Harauli Fatehpur from 3-Line Xing to 5-Line xing Station which has been sanctioned as 2nd MM. 7. Scope of minor bridges including RUBs has been increased from 215 nos. to 493 nos. (minor br.-267nos., RUBs- 218nos. & Subway-08nos.). Scope of minor bridges has been increased due to increase in irrigation network system during past 10 years and scope of RUBs has been increased mainly due to consideration of LC elimination policy of Rly Board and due to rapid development of rural road network in past 10 years, the scope of road crossing has been increased which ultimately increases the scope of RUBs/LHS. 8. The scope of major bridges has been increased from 16nos. to 35 nos. (Br.-30nos. & RUB-05nos.). Scope of Major Bridges has been increased mainly due to change of span from minor br. to major br. during process of getting NOC from concerned state authorities. Also, due to development in canal distributary system, some major bridges have been considered. 9. Due to material modification for Electrical/TRD work. 10. Also an impact of time over run resulting price escalation. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
3 | CR | NL | Wardha-Nanded (via Yevatmal-Pusood) © | 2007-08-01 | 2015 | 284 | 2021 | 2026-03-29 | 8 year | 1. Land Acquisition Delays: Land acquisition was initially estimated under the earlier provisions. Subsequently, implementation of the RFCTLARR Act, 2013, revised compensation provisions, increased land requirement and acquisition formalities affected the availability of encumbrance-free land. 2. Change in Alignment and Project Length: The project length increased from 284 km to 291.50 km due to approved alignment modifications, requiring additional land acquisition and execution of additional works. 3. Additional Tunnel Works: Construction of six tunnels involving 10.364 km length required detailed geotechnical investigations, geological assessment, specialised excavation and tunnel lining. 4. Unforeseen Ground Conditions: Actual soil strata, presence of BC soil, hard rock and variations in groundwater conditions necessitated additional excavation, ground improvement and modifications in construction methodology. 5. Increase in Bridge Works: The number of major bridges increased from 79 to 133, with additional requirements of pile foundations, composite girders, viaducts and revised structural designs. 6. Increase in ROB/RUB Works: The number of RUBs increased from 51 to 193 due to development of road infrastructure and revised policies for elimination of level crossings, resulting in additional construction activities. 7. Revision of Technical Specifications: Changes in formation width, vertical clearances, bridge designs, tunnel provisions and track standards as per updated Railway Board, RDSO and other applicable guidelines required additional execution time. 8. Additional Railway Infrastructure: Additional provisions for crossing stations, passenger amenities, electrification, electronic interlocking, tunnel ventilation and communication systems increased the scope of work. 9. Extended Scope of Civil Engineering Works: Additional earthwork, ground improvement, drainage, protection works, diversion roads and associated bridge approaches increased the volume of construction activities. | Land Acquisition, Phase wise Sanctioning |  | LA | PS |  |  |  | 697.19 | 10644.48 | 9947.29 | i) Earthwork:- Quantity of total Earth work increased from 164 lakh cum. to 335 lakh cum. due to a) Change in FLs to keep the minimum vertical clearance at RUBs which have been increased from 36 nos. to 162 nos. from DE to RE2 due to rapid development of Road network in this area. b) Increase in formation width to 7.85m against original planned 6.85 m. c) Incraese in width by 2 meter on either side as per GE 002 for catch drain dicthes in deep cutting. d) Ground improvement to replace BC soil with SQ2 soil whereever BC soil is encountered. ii) Concrete and allied items: Quantity of concrete, cement, providing and fabricating steel, structural steel etc. increased primarily due to a) Increase in overall bridges from 350 nos. to 500 nos. (aaditional 150 nos.) with increase in RUBs from 36 nos. to 162 nos. (additional 126 nos.) Introduction of 2 Km. of viaducts. b) Incraese in No of RUBs also increased FLs thus barell length of bridges. c) Railway advised to propose mostly composite girder bridges in place of PSC thus increase in CG bridges from 4 to 83 nos. increasing the structural steel quantity. iii) Increase in length of section: Increase in overall length of section from 206 km. to 213.5 km. due to joining at Maltekdi and also conversion of Yelegaon station from Halt to X-ing with major yard modification at Maltekdi. iv) Provision of ballastless track: As per the RB policy tunnels are planned with BLT. v)Protection Measures for NG line(Shakuntala line): 20 km parallel alignment with NG line – Central Railway mandated protection of NG line, leading to increased elevation levels and associated earthwork and bridge construction ,costs, retaining walls etc. vi) Major P.Way changes: Use of wide-based sleepers instead of conventional 60kg sleepers, use of thick web switches & Weldable CMS crossings, adoption of mechanized track linking, change from AT welding to Flash Butt welding etc. vii) Increase in PA works: With change from RL/LL PF to HL PFs in all stations, increase in platform length, increase in COP's, introdcution of FOBs, additional loop lines in stations etc. viii) Other changes in Board's policy guidelines w.r.t increse in plinth area of Quarters, introduction of transition system at bridge approaches, speed potential of new lines to 160 kmph, making of substructure for double line etc. ix) Changes in S&T work: (i) Based on Railway Board policy S&T interlocking system changed from Panel interlocking to Electronic interlocking. (ii) In the route, 10.364 km tunnel is under construction hence necessary telecommunication equipment for tunnel communication is incorporated. x) Changes in ELectrical works: a) RE portion: Changes in scope from 1 X 25 KV to 2 X 25 KV (OHE arrangments) with corresponding increase in transmission line cost, SP/SSP/TSS costs. b) GE Works: i) Huge increase in costs due to Tunnel ventilation arrangement (106 Cr.) ii) Incraese in power line crossings due to recent rapid development of area. | Change in Scope of Work based on Actual Field requirement, Uncertainity in Geological Condition
32 | SWR | NL | Munirabad-Mahabubnagar | 1998-99 | 2013 | 247 | Nov'2019 | 2026-12-28 | 8.11 year | Delay in land acqusition - Land acqusition proposals submitted in stages during 2009-10, 2010-11 & 2017-18. However land was handed over in stretches in 2008-09, 2013-14, 2014-15 & 2024 in stages. Work was taken up as per land availability and accordingly 84 Km out of 165 Km was commissioned. Work is in progress for balance section | Land Acquisition |  | LA |  |  |  |  | 1350.91 | 4767.29 | 3416.38 | 1. General inflation i.e. the price escalation of Material, fuel, labor, etc increased the cost ( Basically due to delay in execution which is caused due to delay in land acqusition) 2. Increase in land cost and enhanced compensation due to court decrees. 3. Change in specifications as per latest guidelines, 4. Inlcusion of electrification 5. inclusion of new items due to public demand | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
70 | CR | DL | Wardha(Sewagram)-Nagpur 3rd line | 2012-13 | 2015 | 76 | 2026-08-18 | 2026-03-27 | 8.5 year | 1) delay in aquisition of Land , the new land aquisition The Right to Fair Compensation and Transparency in Land Acquisition, Rehabilitation and Resettlement Act, the procedure for procurement of land was finalized by stated govt in 2018 there after land aquisition work was started. As there was in ordinate delay in aquisition, in 2021 acquistion by Railway Act 2008 was started. and complete land was aquired in 2025. 2. delay in finalization of ESP , out of total 10 ESP's last i.e wardha, Nagpur etc. was finalized in 2024 i.e after 9 years. 3) in 2018-19 4 th line was sanctioned and it was decided to execute 3rd and 4th line together, thus new plan were made to incorporate both 3rd and 4th line. | Land Acquisition, Phase wise Sanctioning |  | LA | PS |  |  |  | 297.85 | 899.518 | 601.668 | 1) including 3rd and 4th line, total turnout increased from a) 1/12 from 136 nos to 392 nos b) 1/8.5 from 86 to 146 nos c) derailing switch from 41 to 69 nos d) total loop and siding from 22.08 km to 58.80 km e) building from 5798 sqm to 14862 sqm | Change in Scope of Work based on Actual Field requirement
49 | SWR | NL | Bagalkot-Kudachi © | 2009-10-01 | 2013 | 142 | 2020-03-01 | 2026-03-29 | 9 year | Delay in land acqusition - Land acquisition proposals were submitted in 2010,2011 and 2015. However, the major portion of the land was handed over in 2022 & 2023 in stages. Work was taken up as per land availability and accordingly 37 Km out of 142 Km was commissioned. Work is in progress for the balance sections wherever land is made available. 111.27 A of land is yet to be handed over to Railways. | Land Acquisition |  | LA |  |  |  |  | 816.14 | 3128.35 | 2312.21 | 1. General inflation i.e. the price escalation of Material, fuel, labor, etc increased the cost ( Basically due to delay in execution which is caused due to delay in land acqusition) 2. Increase in land cost and enhanced compensation due to court decrees. 3. Change in specifications as per latest guidelines, 4. Inlcusion of electrification 5. inclusion of new items due to public demand | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
66 | WR | GC | Ahmedabad-Himmatnagar-Udaipur including Modasa - Shamlaji Road | 2007-08-01 | 2012, 2017, 2023 | 320 | 2026-06-17 | 2026-12-26 | 9.6 year | The work sanctioned in year 2012. Due to inadequate funds, work not started till 2015. In year 2015 work started after FLS, technical checks, detailed drawings and acceptance of tender. Work also delayed due to change in policies, change in scope of works, various instructions from competent authorities, better facilities to passengers. Modasa-Shamlaji sanctioned in year 2023 | Phase wise Sanctioning |  |  | PS |  |  |  | 742.88 | 2837.7999 | 2094.9199 | Inclusion of LHS in scope of work led to change in L-section. Change of formation width from 6850 to 7850mm. Change in rates of Pway materials during the time period. Changes in Foot over bridges policy. Signalling change from PI to EI. Sanction of Modasa-Shamlaji. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material
6 | ECR | NL | Sakri-Hasanpur | 1996-97 | 2007-2008 | 76 |  | 2026-12-29 |  | 1. From Sakri-End i.e from Sakri to Biraul (36 Km) was opened for passenger traffic in Dec, 2008. From Biraul to Harnagar (8Km) was opened for passage traffic in Aug, 2018. 2. From Hasanpur-End ie. From Hasanpur to Bithan (10 Km) was commissioned by CRS on 28.03.2023 3. For the balance part of the project, the alignment near Kusheshwar Asthan lied in notified bird sanctuary zone and work was stopped by Forest Authority since Dec, 2008 4. Ministry of Environment has given clearance for construction of railway line through the bird sanctuary zone with provision of Animal Passage costing more than 400Cr along with imposing Speed Restriction and restriction on using Electric Engine. Hence it was decided for adopting alternate alignment avoiding Bird Sanctuary. 5. Feasibility of alternate alignment was explored and has been finalised by Railway Board in Dec, 2023 6. Due to new detour alignment, Kuseshwar Asthan Staion has been shifted out of bird sanctuary zone. | Forest & Wildlife Clearance | FC | [5 empty] | 175.69 | 735.21 | 559.52 | (i) Market Inflation of Construction Materials & Fuel. (ii) Escalation in Land Acquisition Compensation. (iii) Contractual Price Variations. (iv) Technical Scope creep & Engineering Revisions. | Change in Scope of Work based on Actual Field requirement, Escalation in Land Acquisition value
7 | ECR | NL | Khagaria-Kusheshwarsthan | 1997-98 | 2002-2003 | 42 |  | 2026-06-29 |  | 1. The patch of Khagaria to Alauli (19KM) has been completed in year 2022 and the section was commissioned for goods traffic on 04.05.2022. Further CRS done & commissioned for passenger traffic on 13.03.2025 2. From Alauli to next 15 km stretch towards Kusheshwar Asthan, the alignment passes through the marginal bund of two embankment of rives Kareh, Kosi and Kamla Balan which causes heavy flood and erosions in those patches. Hence, after floods of 2018-19, Special Hydrological study were done by RITES Ltd. in this patch to ascertain proper design of the embankment and bridge. 3. Based on these study, additional 2 Nos Important Bridges (Span-8x61m & 11x61m), 4 Nos Major Bridges (Span-6x45.7m, 1x30.5M, X2& 3x61m), 8 Nos Minor Bridges & 8 Nos RUB & Formation protection measures were advised for adoption. Accordingly, fresh estimation was been done and sanctioned by Railway Board. 4. Further the location of Kusheshwar Asthan station location got changed to due detouring in aligment of Hasanpur-Kueshwar Asthan-Sakri Project due to notified bird sanctuary. | Forest & Wildlife Clearance, Phase wise Sanctioning | FC |  | PS |  |  |  | 614.45 | 1384.16 | 769.71 | 1. From Alauli to next 15 km stretch towards Kusheshwar Asthan, the alignment passes through the marginal bund of two embankment of rives Kareh, Kosi and Kamla Balan which causes heavy flood and erosions in those patches. Hence, after floods of 2018-19, Special Hydrological study were done by RITES Ltd. in this patch to ascertain proper design of the embankment and bridge. 2. Based on these study, additional 2 Nos Important Bridges (Span-8x61m & 11x61m), 4 Nos Major Bridges (Span-6x45.7m, 1x30.5M, X2& 3x61m), 8 Nos Minor Bridges & 8 Nos RUB & Formation protection measures were advised for adoption. Accordingly, fresh estimation was been done and sanctioned by Railway Board. 3. Further estimate has csot over run due to market inflation of construction material & fuel, Contractual Price Variation etc. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material
10 | ECR | NL | Sitamarhi-Jayanagar-Nirmali via Susand | 2008-09-01 | NS | 189 | Mar'20 |  |  | 1. The Sitamarhi–Jaynagar–Nirmali via Sursand New Line Project (188.90 km) was sanctioned during 2008–09. Subsequently, the project was placed under the list of frozen works, restricting its execution and incurrence of expenditure. The Railway Board subsequently de-froze the project vide letter No. 2015/W-2/ECR/NL/12 dated 29.09.2025. 2. Thereafter, a fresh tender was awarded for conducting an aerial topographical survey using DGPS-based integrated drone technology, traffic studies, calculation of EIRR and FIRR, preparation of revised L-section, DPR, ESP, SIP and GAD, soil exploration, preparation of reports, Bill of Quantities (BOQ), EPC tender documents and other ancillary works in connection with the project under Samastipur Division of East Central Railway. The Letter of Acceptance (LOA) was issued on 06.03.2026. However, the agency failed to submit the Performance Guarantee within 60 days from the date of issue of the LOA. Consequently, the tender was terminated vide notice No. ECR/CAO/CON/WT/E-Tender/North/32/25-26/655 dated 29.05.2026. 3. Subsequently, a fresh tender for Final Location Survey (including geotechnical studies, design and preparation of drawings) and other preliminary activities for preparation of the DPR, including electrical, signalling, operating/traffic works and preparation of the EPC bid package, was floated on 07.10.2026 on a Quality and Cost Based Selection (QCBS) basis. | Phase wise Sanctioning |  |  | PS |  |  |  | 678.62 | 4988.46 | 4309.84 | The Sitamarhi–Jaynagar–Nirmali via Sursand New Line Project (188.90 km) was sanctioned during 2008–09. Subsequently, the project was placed under the list of frozen works, restricting its execution and incurrence of expenditure. The Railway Board subsequently de-froze the project vide letter No. 2015/W-2/ECR/NL/12 dated 29.09.2025. Now the cost increased due to - 1. Land cost increased significantly. 2. Due to increase in height of embankment throughout the section so that potential Level crossing can be eliminated. Bank height increased to provide the vertical clearance for NH & RCD for RUBs with minimum clear height of 5.50m. 3. Increase in scope of major bridges & LHS at the places where Pucca/Bituminous road already available during construction, 4. Increase in blanket thickness from 300mm to 550mm as per latest RDSO guidelines, 5. Increase in road network in the project length which ultimately increases the scope of RUBs significantly. | Change in Scope of Work based on Actual Field requirement, Escalation in Land Acquisition value
12 | ECR | NL | Kursela-Bihariganj | 2007-08-01 | 2024-25 | 58 |  |  |  | 1. It's 1st Part-Detailed estimate amounting to Rs. 42.99 Cr for Civil Engineering portion for preliminary expenses, land acquisition, formation and minor bridges for stretch Kursela-Rupauli section (19.9km) was sanctioned by Rly Bd. on 21.08.2008. 2. Application for land acquisition for 11 nos. villages for 150 acre land for initial 8.7 km stretch from Kursela side of Katihar district was filed in 2008-09. To which, State Government demanded Rs. 6.77 Cr for payment. 3. Further, State Government demanded the escalated cost as Rs. 8.88 Cr in year 2011-12 but fund couldn’t be transferred due to insufficient allotment. 4. Since then, no sufficient fund allotment has been made in any of the financial year and land acquisition couldn’t be completed. Rs. 0.10 Cr is allotted for year 2024-25 which is insufficient for land acquisition. 5. Railway Board vide its letter D.O. no. 2019/W-1/Genl./Budget/1, dated: 24.09.2019 has instructed to have no further expenditure till further orders 6. Railway Board vide its letter 2023/W-2/ECR/Misc./07 (E-Office 3422595) dated 18.03.2025 has agreed to defreezing of the proposal provided that a Fresh DPR duly updating the Cost Estimate, Traffic Projections and Financial viability is prepared and DE to be got sanctioned by the competent authority | Land Acquisition, Phase wise Sanctioning |  | LA | PS |  |  |  | 42.99 | 192 | 149.01 | 1. Railway Board vide its letter D.O. no. 2019/W-1/Genl./Budget/1, dated: 24.09.2019 has instructed to have no further expenditure till further orders 2. Railway Board vide its letter 2023/W-2/ECR/Misc./07 (E-Office 3422595) dated 18.03.2025 has agreed to defreezing of the proposal provided that a Fresh DPR duly updating the Cost Estimate, Traffic Projections and Financial viability is prepared and DE to be got sanctioned by the competent authority | Administrative reason
59 | NCR | GC | Dholpur-Sirmuttra with extension to Gangapur City | 2010-11-01 | 2022 | 145 |  | 2026-12-29 |  | Land Acquisition and slow disbursment of compention due to dispute of ownership & court Cases. Another aspect of delay occurred due to Rajasthan Govt. desired to retain NG line as heritage railway. Railway Board vide letter no. 2012/W-2/NCR/GC/01 dated 15.03.2017 instructed to stop the work on the project till the issue of retention of the NG line as a heritage railway is resolved with Government of Rajasthan. Railway Board vide letter no. 2012/W-2/NCR/GC/01 dated 16.02.2018 communicated to retain NG alignment. Thus the project was stopped. Subsequently, Railway Board vide letter no. 2012/W-2/NCR/GC/01 dated 11.10.2019 instructed to recast DE which was submitted to Railway Board on 24.01.2020. DE of GC of Dholpur – Sirmuttra section (69.1 Km) at a total cost of Rs. 746.83 Cr. was sanctioned as a part of project - Dholpur – Sirmuttra GC with extension up to Gangapur City (144.60Km) - vide Railway Board letter No. 2012/W-2/NCR/GC/01pt (e-office – 3338768) dated 11.03.2022. | Land Acquisition, Phase wise Sanctioning |  | LA | PS |  |  |  | 212.23 | 746.83 | 534.6
17 | NER | NL | Chhitauni-Tumkuhi Road | 2006-07-01 | 2008 | 59 | OCT" 14 | 2026-12-29 |  | Due to delay in land acquisition, the project was kept in abeyance from 2019 to 2024. | [7 empty] | 242 | 1881 | 1639
74 | NER | DL | Chhapra-Ballia Patch Doubling (65 km) | 2012-13 | 2015 | 65 |  | 2026-10-26 |  | The project has been kept in abeyance since 24.09.2019 by Railway Board vide DO L/No 2019/W-1/Genl./Budget/1 Dated 24.09.2019 | [7 empty] | 324 | 1010 | 686
18 | NFR | NL | Eklakhi–Balurghat (86.76Km), MM of NL (Raiganj–Itahar=22.16 Km) (Gazole-Itahar=27.20 Km ) , (Itahar-Buniadpur=27.09 Km) | 1984-85 | 2008 | 163 |  |  |  | The project has been kept in abeyance since 24.09.2019 by Railway Board vide DO L/No 2019/W-1/Genl./Budget/1 Dated 24.09.2019 | Phase wise Sanctioning |  |  | PS |  |  |  | 37 | 351 | 314 | The project has been kept in abeyance since 24.09.2019 by Railway Board vide DO L/No 2019/W-1/Genl./Budget/1 Dated 24.09.2019 | Administrative reason | (a) The project has been kept in abeyance by Railway Board vide DO L/No 2019/W-1/Genl./Budget/1 Dated 24.09.2019. (b) The project has been de-freezed vide Railway Board L/No. 2025/W-I/NFR/Misc./15 (E-3495405) dated 19.01.2026. (c) Tender for fresh survey and preparation of revised/detailed estimates was awarded on 16.06.2026. Survey work is in progress for the Gazole–Itahar, Itahar–Raiganj and Itahar–Buniadpur New BG Line Projects.
22 | NFR | NL | Jalalgarh-Kishanganj | 2007-08-01 |  | 51 |  |  |  | The delay was primarily attributable to the construction of the important bridge over the Ghaghra River, owing to the river's complex hydrological conditions and its constantly shifting course. The outbreak of the COVID-19 pandemic further compounded the delays and adversely affected the progress of construction activities. | Phase wise Sanctioning |  |  | PS |  |  |  | 359 | 1754 | 1395 | 1. The project was sanctioned vide Pink Book item No. 10 b of 2008-09, at a total cost of ₹282.92 crore. 2. Project was kept in abeyance vide Railway Board L.No.2019/W-1/Genl./Budget/1 Dt. 24.09.2019. 3. De-freezing of project has been done vide Rly. Board order no. 2024/W-1/NFR/NL/Jalalgarh-Kishanganj/14 (E-3457936) dated 13.06.2024. It was also advised to submit fresh DPR. The major reasons for the cost overrun are detailed below: 1. Price Escalation: Increase in the cost of materials, labour, machinery and other construction inputs since the original sanction in 2010. 2. Land Acquisition: Increase in formation width from 6.85 m to 7.85 m, additional land requirements due to revised formation levels, and increase in land acquisition rates. 3. Formation and Earthwork: Substantial increase in earthwork quantities due to revised formation width, higher formation levels considering the High Flood Level (HFL) in flood-prone areas, additional sand filling in marshy stretches, and provision of drainage and protection works. 4. Permanent Way: Additional provisions for 60 kg rails, wider sleepers, increased loop and siding lengths, 51 nos. Road Under Bridges (RUBs) in lieu of level crossings, increased ballast cushion, additional points and crossings, and other track-related requirements as per revised Railway Board guidelines. 5. Bridges: Increase in bridge dimensions due to revised formation width, modification of minor and major bridge spans based on site requirements, provision of Road Over Bridge (ROB) in lieu of 02 no.Level Crossings, and adoption of revised bridge design provisions. 6. Station Buildings and Passenger Amenities: Additional provisions for high-level platforms, station buildings, passenger shelters, subways, circulating areas, approach roads, goods facilities and other infrastructure as per approved Engineering Scale Plans (ESPs). 7. Signalling and Telecommunication: Provision of Multi Aspect Colour Light Signalling (MACLS), Electronic Interlocking (EI), UFSBI, HASSDAC, MSDAC, fire alarm systems, IP-MPLS, VOIP and other modern signalling and telecommunication facilities as per revised Railway Board guidelines. 8. Electrical Works and Railway Electrification: Additional provisions for 33 kV underground cable crossings, electrical installations, equipment and railway electrification, which were not adequately covered in the original estimate. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value, Administrative reason | 1. Detail Estimate of ₹ 359.86 Cr. was submitted to Rly. Bd. vide letter no. W/98/CON/Kishanganj-Jalalgarh dated 22.01.2009. 2. Only part estimate of ₹13.68 crore for 1st 7.5 km was sanctioned vide Railway Board letter No. 2005/WI/NF/NL/17 dated 25.02.2009. 3. The project was kept in abeyance vide Railway Board letter No. 2019/W-1/Genl./Budget/1 dated 24.09.2019. 4. It was de-frozen vide Railway Board letter No. 2024/W-1/NFR/NL/Jalalgarh-Kishanganj/14 (E-3457936) dated 13.06.2024. It was also instructed to submit fresh DPR of the project. 5. A fresh DPR at a total cos of ₹ 1852.32 Cr. was submitted to Railway Board on 17.06.2025. 6. After PEC meeting on 01.07.2025, revised DPR at a cost of ₹ 1794.69 Cr. was submitted to Railway Board on 7. The estimate was again reviewed at Railway Board on 13.07.2026, and the revised DPR at the estimated cost of ₹1754.29 Cr. has been submitted vide letter no. W/362/Con/S-2/FLS/KNE-JAG dtd 05.10.2026. with completion period of 3 years
25 | NFR | NL | Kaliyaganj-Buniadpur | 2009-10-01 |  | 33 | 2026-12-29 |  |  | Work was stooped since 2013 due to paucity of fund and then it was freezed on 24.09.2019 by Railway Board vide D.O. Letter No. 2019/W-1/Genl./Budget/1 dated 24.09.2019. | Phase wise Sanctioning |  |  | PS |  |  |  | 205.41 | 997.09 | 791.68 | 1. The project was sanctioned by Railway Board vide Letter No. 2009/W1/NL/NF/Kaliaganj-Buniadpur dated 29.12.2010, at a total sanctioned Detailed Estimate cost of ₹222.22 crore. 2. Project was kept in abeyance by Railway Board vide Letter No. 2019/W-1/Genl./Budget/1 dated 24.09.2019. 3. Project was thereafter de-freezed by Railway Board vide Order No. 2024/W1/NFR/NL/Kaliaganj-Buniadpur/11(E-3456638) dated 29.02.2024 Reason for Cost overrun is as follows: 1) Land Acquisition: Land cost increased from ₹45.57 Cr to ₹342.40 Cr due to increased land requirements arising from elimination of level crossings through RUBs/ROB and enhancement of formation width from 6.85 m to 7.85 m. Consequently, land requirement increased from 378.40 acres to 407.083 acres. Revision of land rates also contributed to the increase 2) Formation Works: The quantity of earthwork in filling increased from 14.74 lakh cum to 45.59 lakh cum, resulting in a variation of ₹84.11 Cr. This was mainly due to enhancement of formation width from 6.85 m to 7.85 m as per prevailing guidelines and increased embankment height necessitated by the provision of RUBs in place of level crossings. 3) Permanent Way: Cost increased from ₹58.40 Cr to ₹118.54 Cr due to provision of 60 kg new rails in place of 52 kg rails, increase in ballast cushion from 300 mm to 350 mm on the main line and from 250 mm to 300 mm on loop lines, increase in points and crossings from 11 to 12 Nos., increase in loop lines from 11 to 12 Nos., and provision of one additional siding at Kushmandi station. 4) Bridge Works: Cost increased from ₹18.52 Cr to ₹180.41 Cr due to updated rates based on USSOR 2021, CPWD DSR 2021 and relevant LARs, provision of 6 Major Bridges including 1 ROB and 1 RUB, 24 Minor Bridges and 24 additional RUBs. Six level crossings were replaced by RUBs, one additional level crossing was replaced by an RUB, three previously omitted level crossings were provided with RUBs, and two additional RUBs were proposed as per approved L-section and field requirements. Further, RCC Box Bridges having spans exceeding 3 m were replaced by PSC Slab Bridges as per latest guidelines. 5) Station and Building Works: Increase in cost was due to adoption of updated USSOR/DSR rates, conversion of medium-level platform into high-level platform at Kushmandi, provision of 8 water booths against 3 tube wells/water booths in the Detailed Estimate, adoption of pile foundations instead of open/shallow foundations based on soil strata, and provision of one camp office for project execution and monitoring. 6) Electrical General Works: Cost increased from ₹7.51 Cr to ₹19.63 Cr due to conversion of LT/11 kV/33 kV overhead electrical lines into underground cables, increase in cable quantities, additional electrical provisions and revision of rates. 7) Railway Electrification: Provision of ₹26.14 Cr was included for Railway Electrification to meet the requirement of 100% electrification of the railway network.. 8) Signalling and Telecommunication Works: Cost increased from ₹21.86 Cr to ₹36.45 Cr due to provision of MACLS with centralized Electronic Interlocking at Kaliyaganj, Kushmandi and Buniadpur stations, UFSBI with BPAC using HASSDAC, track circuiting with MSDAC and DC track circuits, updated earthing and bonding arrangements, signalling and power cables, IPS, DG sets, fire alarm systems, and laying, jointing and splicing of 6-quad and OFC cables. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value, Administrative reason, Uncertainity in Geological Condition | 1. KAJ-BNDP New BG line was sanctioned vide Rly Board's letter no. 2009/W1/NL/NF/Kaliaganj-Buniadpur dtd.29.12.2010. 2. Project was kept in abeyance vide Railway Board L.No.2019/W-1/Genl./Budget/1 Dt. 24.09.2019. 3. De-freezing of project has been done vide Rly. Board order no. 2024/W1/NFR/NL/Kaliaganj - Buniadpur/ 11(E- 3456638) dt. 29.02.2024. 4. 1st Revised estimate sanctioned by Rly Bd on 27.02.2025 at cost ₹ 997.09 cr. 5. Revised LA Proposal for 113.47 acre of land under Uttar Dinajpur was submitted to DM/Uttar Dinajpur on dt. 27.12.2024. Gazette notifications u/s 20A already published in local Newspaper on Dt. 18/08/2025 & 19/08/2025 and Notification u/s 20E has been published in Gazette of India on dated 09.07.2026 for entire 113.47 Acre land and published in local newspaper on dated 01.08.2026. During District Coordination meeting on 25.09.2026 at Raiganj, it was informed by DM/ Uttar Dinajpur that final estimate would be given to railway by 06.10.2026. TDC for estimate has been further extended to 31.10.2026. 6. Revised LA Proposal for entire 301.04 acre of land (31 mouza) under Dakshin Dinajpur Distt. was submitted on 30.01.2025. (i) Notification u/s 20E for 108.0575 Acre (10 mouza) under District Dakshin Dinajpur has been published in the Gazette of India on Dt. 30.07.2026. Estimate is awaited. (ii) Notification u/s 20A for 85.6077 Acres of land (9 mauza) has been published in the Gazette of India on dated 30.07.2026 & in local Newspaper on 17/08/2026. TDC for Draft notification U/s 20E has been given by DM/ Dakshin Dinajpur as 31.10.2026. (iii) Draft Notification of 20A for balance 107.37 acre of land (12 mouza) is still awaited from DM/ Dakshin Dinajpur. TDC for Draft notification U/s 20A has been given by DM/ Dakshin Dinajpur as 30.11.2026.
60 | NFR | GC | New Jalpaiguri– Siliguri– New Bongaigaon including Branch line(419.17Km) and MM of (Chalsa-Naxal) (19.85Km) New line and Rajabhatkhawa – Jayanti New line (15.13Km) | 1998-99 |  | 454 |  | 2026-04-30 |  | New Jalpaiguri– Siliguri– New Bongaigaon Project Commisioned in 2010. Projects (a. Chalsa-Naxal & b. Rajabhatkhawa-Jayanti) sanctioned (as Material Modification to NJP-NBQ GC Project) by RB on 28.04.2011, freezed by RB in 2019 and defreezed on 19.01.2026. a. Chalsa-Naxal : The NOC has been obtained from Tea garden, NOC applied from Forest deaprtment for Survey permission, tender for Topographical Survey opened on 20.07.2026, discharged on 28.08.2026, Retender floated on 22.09.2026, openedon 13.10.2026, under finalsiation. b. Rajabhatkhawa-Jayanti: After defreezing, Railways requested Forest Department to grant survey permission. Forest department has advised to review feasibility of project vide its letter dated 09.06.2026, due to following reasons: Forest Department is shifting all villages from Buxa Tiger Reserve to outside. No commercial mining is permitted inside BTR due to various court judgements. Tourism is planned to be reduced systematically. The feasibility of project is under review. | Forest & Wildlife Clearance, Phase wise Sanctioning | FC |  | PS |  |  |  | 405 | 1578 | 1173
61 | NFR | GC | Katihar- Jogbani–Barsoi– Radhikapur–Teznarayanpur (236.14Km) and MM of New BG line Raiganj – Dalkhola (43.43Km) | 2001-02-01 | 2011 | 280 |  |  |  | The work of "Construction of new line from Raiganj to Dalkhola (43.43 Km) as Material Modification to Jogbani-Katihar-Barsoi-Radhikapur Gauge Convsersion Project" was Sanctioned on 09.05.2011 with estimated cost of Rs. 291.53 cr. Work was stooped since 2013 due to paucity of fund and then it was freezed on 24.09.2019 by Railway Board vide D.O. Letter No. 2019/W-1/Genl./Budget/1 dated 24.09.2019. The project was freezed and the project has been De-freezed vide Railway Board's L. No. 2025/W-1/NFR/Misc./15 (E-3495405) Dtaed 19.01.2026. | Phase wise Sanctioning |  |  | PS |  |  |  | 107 | 1006 | 899 | The project was sanctioned by Railway Board vide Letter No. 2011/W1/NF/WP 11-12/Raiganj-Dalkhola (MM) dated 09.05.2011, at a total sanctioned Detailed Estimate cost of ₹291.53 crore. Subsequently, the project was kept in abeyance by Railway Board vide Letter No. 2019/W-1/Genl./Budget/1 dated 24.09.2019. The project was thereafter de-freezed by Railway Board vide Order No. 2024/W1/NFR/NL/Kaliaganj-Buniadpur/11(E-3456638) dated 19.01.2026 | Administrative reason
31 | NR | NL | Qadian-Beas | 2011-12-01 | 2026 | 40 |  |  |  | FLS of new line between Qadian and Beas was sanctioned in year 2011-12. The FLS was thereafter completed in Dec'17. Subsequently the DE at a cost of Rs. 1047.96 Cr was submitted to RB. Railway Board vide DO letter n0. 2019/W-1/Genl.Budget/1 dated 24.09.25 kept this work in abeyance. The project was De-freezed in on 28.11.2025 and DE was sanctioned on 13.08.26. | [7 empty] | 205 | 1419 | 1214
75 | NR | DL | Mansa-Bhatinda (52 Km) Ph.I including new MM for Rama Mandi( Raman)-Maur Mandi(Maur) via Talwandi Sabo( 29.11 km) © | 2009-10-01 | 2010 | 80 |  |  |  | Doubling from MSZ to BTI commissioned & handed over to open line in 2019. New line project from Rama Mandi to Sadda singhwala was sanctioned as MM. The revised estimate (for doubling and MM combined work) costing Rs.1330.83 Cr has been sanctioned by Railway board on 06.03.2026. | [7 empty] | 118 | 212 | 94
62 | NWR | GC | Ajmer-Chittaurgarh-Udaipur (300 km), incl. Material Modifications for extension from Udaipur to Umra (11 km), Mavli- Nathdwara (16 km) NL , Mavli Jn.-Bari Sadri (82.01 km) GC and Nathdwara-New Nathdwara (10.80 km) new line. | 1996-97 | 2.0002e+19 | 420 |  | 2026-12-27 | [9 empty] | 274 | 800 | 526 | Reason for Cost overrun is as follows:
34 | SCR | NL | Nadikude-Srikalahasti | 2012-13 | 2016, 2021 | 309 |  | Feb 29 | [9 empty] | 2288.7 | 6101.29 | 3812.59
35 | SECR | NL | Kharsia-Dharamjaygarh with spur line ( Raigarh(Mand Colliery)-Bhudeopur) | 2012-13 | 2025 | 122 | 21.05.2021 (as per PEA, 182 weeks from the date of approval by CERL to go ahead the award of contract, Financial closure-24.11.2017) | 2026-03-27 |  |  | Phase wise Sanctioning |  |  | PS |  |  |  | 3407 | 3798 | 391 | Increase in Cost in spur line Cost due to increase in quantity of earthwork in filling with borrow soil in rerouted alignment, Cost due to increase in hard rock quantity Cost due to change in design of RCC drain from 600x450mm to 1000x1000mm. Cost due to change in type of foundation of bridges no.28 from open foundation to pile foundation. Cost due to change in design of approach road to ROB No.37 from RE Wall construction to U-trough Wall constructions. Cost due to additional bridge no. 21 (ROB), 39A, 41A & 45 as per site requirement. Cost towards Non-schedule items to be executed as per site requirement. Cost towards construction of pathways to be provided on Girder bridges. Increase in Cost in Durgapur Feeder Line Cost towards additional bridges required as per site condition (Bridge 1, 5, 7, 8 & 9). Cost towards providing retaining walls for execution of works within acquired Land/ ROW. Cost provisioned under USSOR schedule for unforeseen works incidental to completion of Durgapur feeder line. Cost of additional GST due to change in rate of GST from 12% to 18%. Increase in Cost due to Price Escalation | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Uncertainity in Geological Condition
36 | SECR | NL | Wadsa-Gadchiroli © | 2011-12-01 | 2017 | 52 |  | 2026-03-27 |  | Delay due to land/ forest/ wildlife issues and state's 50% share issue. | Land Acquisition, Forest & Wildlife Clearance | FC | LA |  |  |  |  | 117 | 1880 | 1763
37 | SECR | NL | Gevra Road-Pendra Road | 2012-13 | 2018 | 135 | 01.03.2024 (as per PEA, 182 weeks from the date of approval by CERL(SPV of IRCON SECL & GoCG) to go ahead the award of contract, Financial closure-04.09.2020) | 2026-03-27 |  | • Delay due to NGT case (2016-2019) - LOA for civil work including E/W, Major and Minor bridges from KM 98 to 135 was issued -19.07.2016. However, Case is filed in NGT court in Dec’16 due to which ongoing works were to be suspended. NGT case was disposed on 29.04.2019. • Delay in forest clearance (2014-2018) - Registration of forest proposal was completed in June 2014. However, Stage-I clearance was obtained in 26.02.2018 and Stage-II clearance was obtained in 07.06.2018 • Delay due to Introduction of Wildlife passes as per MoEF requirement (2018-21)- 7 Nos EOPs/EUPS were finalized by CCF Bilaspur in April’2018. Accordingly, L-section were revised and 7 Nos EOPs/EUPs were incorporated in Aug’2020. Further, PCCF advised to construct 22 Nos EOPs/EUPS in Oct’21. L-section has been revised and EOPs/EUPS were incorporated in Dec’21. • Non-performance of contractor- Non-performance of contractor M/s RMN (Civil work from Km 29-67) and termination of contract of Pkg 2B on 19.05.2025 • Delay in award of S&T tender- As approved by SECR on 30.04.2024, Inclusion of various signalling and telecom items in compliance to the latest policy guidelines of SECR has resulted in delayed invitation of tenders of S&T works which was further delayed S&T tenders for CEWRL was floated on 11.06.2024 but discharged on 14.12.2024 due to administrative reason. Retender for the same was floated on 08.01.2025 but delayed due to court litigation by L-2 bidders, Final verdict was awarded by Delhi High court on 08.08.2025 and LOA was awarded on 13.08.2025 resulting in delay in time line for completion of project. • Shortage of funds - During the working period from March’25 to June’25, the progress of works slowed down because of insufficient cash flow with the contractors. • Financial closure on 04.09.2020.Covid-19 Delay in handing over of hindrance free site . • Surakachar Siding - Handed over on 24.05.2024 • Removal of encroachment on SECL Land in Surakachar - Removed on 31.01.2024 • Removal of encroachments in Krishnanagar - Removed on 10.08.2024 • Non-closing of SECL Road in Urga – Kusmunda section - Closed on 09.11.2024 • Non –removal of toilet block in Urga - Kusmunda section - Removed on 06.11.2024 • Stoppage of work in Krishna Nagar area for demand of their rehabilitation & resettlement (156 Nos.) • Introduction of Elephant under passes • Modification /Shifting of overhead electrical lines. • Changes in OHE alongwith size of bridges due to site requirement & by Railways. • Changes in GSS to TSS supply of 220 KV in Jan’25 • As per MoF circular dated:29.04.2026 followed by MoR circular dated:22.05.2026, Force Majeure invoked on 27.02.2026, with repercussions of 02 -04 months of extension. | Forest & Wildlife Clearance, Land Acquisition, Phase wise Sanctioning, Law and Order Issue, Utility Shifting | FC | LA | PS | LO | US |  | 4970 | 7448 | 2478 | Introduction of EUPs & EOPs as per Wildlife requirement suggested by Forest Department Introduction of Additional Bridges as per Site Requirement Deficient Provision of Track Linking Items Deposit Works Increase in Cost on account of PVC Increase in Cost due to Change in Design, Size, Type and Span of bridges as per Site requirement Increase in Cost due to Variation in Earthwork Quantities Increase in cost of DPR due to GST rate change from 12 % to 18 % Upgradation/ Modification/ Deletion/ Change in scope of items covered in DPR like Telecom System Upgraded with IP-MPLS, IBS Upgraded with EI Communication, Traction transformer and SCADA as instructed by SECR, Change in cost of 132 KV DC Transmission line by utility Company CSPTCL based upon site conditions and surveys by the utility companies, Change in cost of Power Line Modification by Utility Companies, depending upon the site conditions, encroachments, R&R, ROW issues, forest etc. Introduction of 2x25 KV system of OHE as per Railway Boards Instructions (not covered in original DPR) Yard Electrification works of Pendra, Gevra, Urga, Korba/TSS, Pendra/TSS, TPC Control (not covered in original DPR) New Power Line Crossings not covered in DPR (not covered in original DPR) | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material
38 | SER | NL | Tamluk-Digha (88.90 Km) , Deshpran-Nandigram (18.50 km) with new MM for Kanthi-Egra (26.2 km); Nandakumar-Bolaipanda (28 km) NL & Nandigram-Kandhimari (Nayachar) (7 km) NL | 1984-85 | 2000,2009, 2011, 2012 | 18 |  | 2026-02-28 |  | Tamluk-Digha (88.90 Km): Commissioned Other MM projects were kept in shelved by Railway Board dated 24.09.2019 due to land acquisition constraint in West Bengal. | Land Acquisition |  | LA |  |  |  |  | 293.97 | 1291.13 | 997.16 | The reason for cost overrun due to shelving of projects and timeoverrun from the original sanctioned of work. | Administrative reason, Market Inflation increase in cost of raw material | Tamluk-Digha (88.90 Km): Commissioned Deshpran-Nandigram (18.50 km): 38% Kanthi-Egra (26.2 km): Defreezed on 19.01.26. Nandakumar-Bolaipanda (28 km) NL:Defreezed on 19.01.26. Nandigram-Kandhimari (Nayachar) (7 km) NL: Defreezed on 19.01.26.
39 | SER | NL | (Digha) Chandaneshwar-Jaleswar (41 Km) with new MM for Digha-Egra (31 Km) | 2010-11-01 | 2012, 2026 | 41 |  | 2026-12-29 |  | Project was kept in abeyance due to land acquisition constraints in West Bengal portion by Railway Board letter dated 24.09.19. | Phase wise Sanctioning |  |  | PS |  |  |  | 352.65 | 1206.61 | 853.96 | The reason for cost overrun due to shelving of projects and timeoverrun from the original sanctioned of work. | Administrative reason, Market Inflation increase in cost of raw material | Project was kept in abeyance due to land acquisition constraints in West Bengal portion. Railway board de-froze the project on 19.07.2023. The alignment has been revised, for new line from Jaleshwar to Chandanewar within Odisha state. MM for Digha-Egra (31 Km): Shelved by Railway Board letter dated 24.09.19
40 | SR | NL | Tirunnavaya-Guruvayur | 2002-03-01 | 2011 | 35 |  |  |  | Project was kept in abeyance in 2019 due to public protests. Project defreezed in Jan 2021 and FLS is in progress. | [7 empty] | 40 | 321 | 281
41 | SR | NL | Angamali-Sabarimala | 1997-98 | 2006 | 111 |  |  |  | Project was kept in abeyance in 2019 as State Govt didnot agree for cost sharing. Govt of Keralam agreed for cost sharing in 2025 and Project defreezed in Jan 2026. Govt of Keralam to acquire land utilising its 50% share of cost of the project. | Phase wise Sanctioning |  |  | PS |  |  |  | 550 | 3880 | 3330
42 | SR | NL | Tindivanam-Nagari | 2006-07-01 | 2008 | 184 |  | 2028-29 |  | The delay in execution of the Tindivanam–Nagari New BG Line Project was mainly due to prolonged land acquisition proceedings, court cases in Ranipet District (approximately 4 years), implementation of the RFCTLARR Act, 2013, and the consequent requirement for fresh administrative sanction in 2017. Further, inadequate funds for land acquisition during the initial years and delays in obtaining WRD NOC for 54.20 Ha of Water Course Poramboke land affected project progress. During execution, additional hindrances such as local objections near Pandravadu Lake, road diversion, power line shifting, NG Yard modifications and borrow area issues also contributed to delays. | [7 empty] | 460 | 3631 | 3171 | a) LAND : Additional cost due to increased land requirements and escalation under the Fair Compensation and Transparency Act. b) EARTHWORK: Excess due to revised earthwork quantities based on working sections, provision of LUS/RUBs in lieu of LCs, bridge approaches as per waterway calculations, and increase in the number of loop lines as well as site requirements. c) PERMANENT WAY: Excess is due to increase in the cost of Pway materials and increase in the cost of labour and materials,no. of crossing station increased, due to this no. of points and crossing, loop line length increased d) BRIDGE: Excess is due to increase in the cost labour and materials. Palar bridge size increased from 27x30.48m to 38x30.00m as per water way calculations. also new bridge proposed in ranipet. Additional / New ROB, RUB, & LUS are provided due to elimination of LCs. e) Station Buildings: Excess is due to increase in the cost labour and materials. As per user department's requirements service buildings are provided. Excess under other than escalation due to the requirement of user department and also increased due to additional crossing stations provided as per approved yard plan. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
43 | SR | NL | Tindivanam-Gingee-Tiruvannamalai | 2006-07-01 | 2008 | 71 |  |  |  | The project had been kept in abeyance since September 2019 and was recently defreezed in March 2026. | Phase wise Sanctioning |  |  | PS |  |  |  | 136 | 227 | 91 | "a) LAND: Land value is revised as per the LPS submitted to state government hence excess. b) FORMATION: The width of the formation is increased from 6.85m to 7.85m as per recent guide lines. Blanket layer is included as new item in RE as per RDSO guidelines. c) PERMANENT WAY:: The track structure revised to 60 kg rails, wider base sleepers and ballast cushion of 350mm as per recent guidlines. REvised P.way rates of 2024-25 adopted. d) BRIDGE: Excess is due to increase in the cost labour and materials e) Station Buildings: Excess due to considering high level platform in all stations, FOB etc., Size of Station buildings and service buildings revised as per S&T and electrical requirements as per recent plan. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
44 | SR | NL | Chennai-Cuddalore via Mahabalipuram | 2007-08-01 | 2011 | 179 |  |  |  | The project had been kept in abeyance since September 2019 and was recently defreezed in March 2026. | Phase wise Sanctioning |  |  | PS |  |  |  | 523.52 | 2670 | 2146.48 | will be finalized,subsequent to alignment re-verification | Change in Scope of Work based on Actual Field requirement
45 | SR | NL | Attipattu-Puttur | 2007-08-01 | 2011 | 88 |  |  |  | The project had been kept in abeyance since September 2019 and was recently defreezed in March 2026. Cost sharing model with Ennore Port Trust could not materialise due to ban of minining at Ballary. | Phase wise Sanctioning |  |  | PS |  |  |  | 447 | 528 | 81 | will be finalized,subsequent to alignment re-verification | Change in Scope of Work based on Actual Field requirement
46 | SR | NL | Madurai-Tuticorin via Aruppukkottai | 2010-11-01 | 2014 | 144 |  | 2030-31 |  | The project was proposed to the Railway Board for freezing in July 2023 and was subsequently defreezed by GM/S.Rly. in March 2026. | Phase wise Sanctioning |  |  | PS |  |  |  | 698 | 2053 | 1355 | a) LAND: In the PET estimate a land acquisition of 334 ha only. Where as proposed fls 734.27 ha of land require. Further increase to 850 ha due to revision in working section. Mainly due to increase in cost of land adoption with new land acquisition act 2013. b) FORMATION: Excess is due to increase in the cost labour and materials. Earth work quantity as per site condition and increase in the number of bridges and increase in Quantity of side drains c) PERMANENT WAY: Excess due to introduction of service rail to a length of 19.30 km for laying 10RP/20RP. Also escalation of Rates. Excess due to change in Points & crossings 1 in 81/2 to 1 in 12 for better opration and maintenance. d) BRIDGE: As per FLS the number of bridges increased due to the site condition. As per RB latest instructions to avoid RCC boxes for more than 3m span water way bridges. e) Station Buildings: Excess is due to increase in the cost labour and materials and also increase in quantity as per actual requirement. service buildings, Staff quarters are included as required by the OHE & S&T department. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
63 | SR | GC | Tiruchchirappali-Nagore-Karaikkal (145.33 Kms) with extn. Nagapattinam-Velankani-Tiruturaipundi (43 Kms) including new MM Karaikudi-Paralam NL(23 km) | 1995-96 | 2010, 2019 | 211 |  | 2030-31 |  | Work in progress for the balance section - Nagappattinam – Tiruturaipundi (33.5 Km) | No Delay | [5 empty] | ND | 183 | 1748 | 1565 | a) FORMATION: Due to increase in cost of labour and materials. During the investigation at site it was ascertained from local public that, during Tsunami the water level had been flows more than 2m above the exg. MG formation level being lose to coastal region. This has not been ascertained while preparing the abstract estimate. Hence, proposed formation level is increased. Lowering of roads is not feasible being the plain terrain. The depth of blanketting of 0.6m was provided in the abstract estimate whereas in the detailed estimate provided for 1.00m depth as per the site condition. To avoid land acquisition in urban areas, increaing the height and quantity of the retaining wall is essentially required as compared to abstract estimate. Also the formation of 7.850 m is made at TXR station, retaining wall is increased to that height of 7.50 m. b) SIDE DRAINS: Side drains are to be provided at all station locations and high bank locations. which was originally provided as lesser quantity. c) PERMANENT WAY: Due to the cost escalation of P.way materials and Labour charges. d) BRIDGE: Due increase in cost of labour and materials. Also to avoid level crossings, LUSs are provided. NEW ROBs has been proposed in lieu of LCs as per the latest guidlines of RB. Subway is proposed in lieu of FOB at Thirunallaru. e) Station Buildings: Due increase in cost of labour and materials. As per Department requirement additional provision of office building made for executing the project. Station building - type plan 3G is made as per the normal construction i.e. Ground Floor on GL. Later as per the approved working section and yard plan,the formation height is of 7.50m. Moreover, Tirunallaru is a one of the famous prilgrim centre in Tamilnadu. it requires the additional passenger amenities and circulating arrangements etc. Provisions made for SSP building, OHE depot, PSI depot, tower wagon shed as per the OHE department requirement. As per the requirement of CE/TMC, TM Shed, TM staff rest room, Approach roads to TM sidings were provided. Providing CC apron at Karaikkal PF.3 and Vailankanni PF.3(2X 600m) long as per the user department requirement Provision for yard arrangements at Peralam is not included in the abstract estimate, planned for take off beyond the exg. Yard. Since Peralam is a Junction additional, arrangements are as per operating department requirement for simultaneous receiption . | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
64 | SR | GC | Cuddalore-Salem (191 Km) and MM of Chinnasalem-Kallakurichi New Line © | 1999-00 | 2001, 2004, 2006, 2015 | 207 |  | 2028-29 |  | The project has been delayed due to land acquisition issues, including the acquisition of the approach road by Railways, and the delay in finalisation of the Kallakurichi station location owing to objections from the District Administration. The Chinnasalem–Porpadakurichi section (12.10 km) was completed and commissioned on 23.04.2025, while the balance Porpadakurichi–Kallakurichi section (5.10 km) is under progress. | Land Acquisition |  | LA |  |  |  |  | 230 | 261 | 31 | On account of change in station location by State Govt. a) LAND : Due to revision of guideline value, the land value is increased. b) EARTHWORK: Due to increase in formation height where ever LUS provided to maintaine minmum vehicle clearence revised workig section qty increased and cost of earth also incresed. Earthwork quantity increased from 4.94 lakh cum to 7.90 lakh cum. c) PERMANENT WAY: Due to the cost escalation of P.way materials and Labour charges. d) BRIDGE: 1. Major bridges incresed 1 importand bridge, ROB/RUB/LUS 15 nos instead of 5 Nos. e) Station Buildings: Due to the increased length of platform as per extent policy | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
77 | SR | DL | Ernakulam-Kumbalam | 2010-11-01 | 2023 | 8 |  | 2026-12-27 |  | Detailed estimate of the project sanctioned in April 2023. Delay in Land acquisition. Land acquisition is 90% completed and works are in progress. | Land Acquisition, Phase wise Sanctioning |  | LA | PS |  |  |  | 71 | 760 | 689
78 | SR | DL | Kumbalam-Thuravur Patch doubling (15.59 km) | 2011-12-01 | 2023 | 16 |  | 2026-12-27 |  | Detailed estimate of the project sanctioned in April 2023. Delay in Land acquisition. Land acquisition is 95% completed and works are in progress. | Land Acquisition, Phase wise Sanctioning |  | LA | PS |  |  |  | 136 | 802 | 666
80 | SWR | DL | Toranagallu-Ranjithpura (22.9 km) | 2011-12-01 | 2025 | 23 |  | 2026-06-28 |  | This project was sanctioned in 2011-12 and detailed estimates submitted to the Railway Board on 28.09.2012. As directed by Railway Board , possibility of execution under PPP model was explored by SWR and PCOM vide their letter dated 17.05.2019 has communicated to Railway Board that the same is not feasible. However, later on the Railway Board has included this project as Energy corridor projects. Hence, FLS was reconducted and DPR was sanctioned on 18.07.2025 Hence, No delay after sanction of DPR | Phase wise Sanctioning, No Delay | [5 empty] | ND | 445.69 | 445.69 | 0 | DPR sanctioned in 2025 based on the latest FLS conducted. Hence No varaition | No Cost overrun
[18 empty] | 84263.98 | 306508.6869 | 222244.7069
[7 empty] | No data | 32

## Active 14-19
S.N | Rly | PH | Name of Project | Sanctioned Year | DE Sanction Year | Length of project (Km) | Original TDC | Anticipated TDC as given by Rly | Time overrun (Year) | Reasons for Time overrun | TIME OVERRUN REASON | Forest Clearance & Wildlife | Land Acquisition | Phase wise Sanctioning | Law & Order issue | Utility Shifting | No delay | Original Sanctioned Cost | Anticipated Cost | Cost overrun | Reasons for Cost Over run | COST OVERRUN REASON | Remarks
1 | CR | NL | Solapur-tuljapur-Osmanabad | 2018-19 | 2019 | 84 | 2026-03-27 | 2026-03-30 | 3 | Delays were caused by land acquisition, awaiting the Revised Estimate sanction, and pending utility shifting | Land Acquisition |  | LA |  |  |  |  | 904.92 | 3258.91 | 2353.99 | 1. Land Acquisition & Preliminary Expenses (1,092.20% Increase) 1.1. Higher Compensation Rates: Price escalation and increased rates from updated land acquisition awards by competent authorities in Solapur and Osmanabad. 1.2. Increased Area Requirements: Station areas expanded from 1200×60 m in the DPR to 1600×200 m in the revised estimate, raising total land requirements from 369.19 Ha to 632.84 Ha. 1.3. New Environmental Items: Inclusion of wildlife mitigation measures and compensatory afforestation land mandated by the State and National Boards of Wildlife (SBWL/NBWL). 2. Earthwork & Structural Engineering Work (247.32% Increase) 2.1. Quantity Adjustments: Total earthwork quantities were reassessed and increased to 133,16,076" cum" . 2.2 Soil Constraints: Reduced availability of Black Cotton (BC) soil for cut-to-fill usage (dropped to ~15%) increased fresh filling requirements, alongside unconsidered removal costs for BC soil. 2.3. Rate Revision: Escalations based on the latest Award Rates (LAR) and GST. 2.4 New Drainage Policies: Introduction of S&T Cable ducts across the full section as per new Railway Board guidelines, alongside side and catch water drains. 3. Permanent Way (P-Way) & Track Enhancements (Up to 369.55% Increase) 3.1. Expanded Track Network: Operational requirements led to additional track machine sidings, tower wagon sidings, shunting necks, A&D sidings, goods lines, and loop lines (increased from 16.00" km" to 22.394" km" ). 3.2. Mainline Extension: Mainline track increased by 10.24" km" to connect existing Yedshi to the proposed Sanja station. 3.3. Fencing Policies: Comprehensive track fencing was added following Railway Board fencing policy guidelines. 3.4. RUBs and LHS Expansion: Realistic execution assessments led to a major jump in Road Under Bridges (RUBs) proposed at every 1.90" km " and Level Crossings/Limited Height Subways (LHS) for local farmers and villagers. 4. Bridges (Major & Minor) (410% to 483% Increases) 4.1 Preliminary DPR Errors: DPR documents were drafted using rudimentary drawings due to urgent instructions for early submission from the Railway Board. 4.2. Topographical Realities: The site features continuous hillocks and valley formations with heavy monsoon water discharge, requiring a robust increase in bridge counts (Major bridges increased from 12 to 16; Minor bridges from 25 to 48) based on GADs and borelog investigations. 5. Stations, Buildings, and Essential Amenities 5.1. Platform Expansion: Upgraded from 1 platform per station (500×10" m" ) to 2 platforms per station (600×12" m" ). 5.2 Omitted Amenities Added: Foot Over Bridges (FOB), Cover Over Platforms (COP), pathways, paved circulating areas, road diversions, and overhead/ underground tanks were initially omitted due to urgency/ oversight, but are now added as Minimum Essential Amenities (MEA) across all 8 stations. 5.3. Residential Quarters: Staff quarters increased from 125 units (covering only 50% essential staff) to 250 units based on actual divisional requirements. 6. Departmental & General Charges (303.40% Increase) 6.1. Dynamic Scaling: Charges scaled dynamically alongside inflated direct project costs. 6.2. Revised Guidelines: Departmental and general charge percentages were updated as per recent Railway Board letters and memorandums. | Market Inflation increase in cost of raw material, Escalation in Land Acquisition value | 1st Revised Estimate is under approval at Railway Board. 50% Cost Sharing Concent from Government of Maharashtra is obtained for Revised Cost
2 | CR | NL | Dhule (Borvihir)-Nardana | 2018-19 | 2019 | 51 | 2026-12-26 | 2026-03-28 | 1.25 | Due to delay in Land acquisition. | Land Acquisition, Law and Order Issue | [6 empty] | 492.76 | 1207.78 | 715.02 |  | Escalation in Land Acquisition value | Ist Revised Estimate cost Rs 1207.78 Cr. of Dhule - Nardana project has been sanctioned on 08.10.2026
14 | CR | DL | Wardha-Ballarshah 3rd line | 2015-16 | 2016 | 132 | March' 21 | 2026-01-27 | 5.8333 | 1. Land Acquisition: Delay in acquisition and handing over of land due to statutory procedures, reassessment of compensation under the Right to Fair Compensation and Transparency in Land Acquisition, Rehabilitation and Resettlement Act, 2013, valuation, joint measurement and declaration of awards. 2. Revision of Engineering Plans: Revision of approved Engineering Scale Plans (ESPs), involving additional yard lengths, crossovers, ballast requirements and modifications in existing railway infrastructure. 3. Tendering and Contractual Constraints: Short closure and subsequent re-invitation of tenders for earthwork and minor bridges in the Warora–Ballarshah section, resulting in staggered commencement of works. 4. Unforeseen Geological Conditions: Encountering weak sub-strata and non-availability of hard rock up to approximately 30 metres at bridge locations, necessitating adoption of pile foundations in place of originally envisaged open foundations. 5. Additional Bridge Works: Extension of minor bridges to accommodate the proposed fourth line, requiring additional planning, design and construction activities. 6. Additional Yard Remodelling: Modification and remodelling of Chandrapur and Ballarshah yards to meet operational requirements and accommodate additional railway infrastructure. 7. Electrical Infrastructure Modifications: Additional OHE, PSI, traction transformer augmentation, SCADA and EHT/EHV crossing modification works as per approved ESP. 8. Signalling and Telecommunication Works: Extensive replacement of existing signalling gears, provision of Electronic Interlocking, dual detection, IBS, OFC and associated telecom infrastructure. | Land Acquisition, Forest & Wildlife Clearance, Utility Shifting, Law and Order Issue | FC | LA |  | LO | US |  | 1272.19 | 2072.19 | 800 | 1. Increase in Land Acquisition Cost: Substantial increase in land compensation due to implementation of the Land Acquisition Act, 2013, including market-value-based compensation, applicable multiplication factor, 100% solatium and compensation for affected assets. 2. Increase in Earthwork Cost: Increase in State Revenue Royalty for murum from ₹70.66 to ₹212.01 per cum, introduction of GST and variation in earthwork quantities, including additional earthwork for Ballarshah UP yard shunting neck. 3. Increase in Ballast Cost: Increase in royalty rates, GST and additional ballast requirements arising from revised ESPs, increased yard lengths and additional crossovers. 4. Increase in Major and Important Bridge Cost: Adoption of pile foundations instead of open foundations due to weak sub-strata and non-availability of hard rock up to approximately 30 metres at several bridge locations. 5. Increase in Minor Bridge Cost: Extension of minor bridges to facilitate the proposed fourth line, considering the difficulty of constructing separate bridges with a track-centre distance of 5.3 metres. 6. Increase in Electrical Engineering Cost: Additional OHE and PSI modifications, SCADA, traction transformer augmentation, EHT/EHV crossing modifications and provision of structures compatible with the future 2×25 kV OHE system. 7. Increase in S&T Engineering Cost: Provision of Electronic Interlocking, dual detection, SSDAC, UFSBI, MSDAC, IBS, replacement of overaged signalling gears and additional OFC and telecom infrastructure. 8. Additional Operational Requirements: Additional infrastructure and yard remodelling at Chandrapur and Ballarshah, including modifications required to meet operational and safety requirements. 9. Price Escalation: Substantial increase in the prices of construction materials, labour, statutory charges and other inputs during the period between sanction of the Detailed Estimate in 2016 and execution of the works over subsequent years. 10. Material Modification: Inclusion of additional scope for augmentation of coach maintenance facilities at Ballarshah, sanctioned by Railway Board on 12.06.2020, involving an additional provision of ₹11.30 crore. | Escalation in Land Acquisition value, Change in Scope of Work based on Actual Field requirement
15 | CR | DL | Itarsi- Nagpur 3rd line. Bal. | 2016-17 | 2016 | 280 | 2026-03-23 | 2026-03-28 | 5 | Initially land acquisition was carried out by direct purchase method as per RECTLLR-2013 but there were constraints from Farmers hence LA by railway act 2008 was also initiated in Aug. 2021. further there was delay in land acquisition in MP state (188km length) which delayed the invitation of EPC Tender. earlier EPC tender progressed for 94 km are discharged due to non-availability of land due to covid pandemic the work was affected for 2 years now pvt. & Govt LA completed. In Betul & Narmadapuram District, the proposal for diversion of a total of 8.0357 hectares of forest land from Jujharpur to Bhoura is currently pending for Stage-II (Final) approval. The final Stage-II approval for forest land diversion will be granted only after obtaining Wildlife Clearance. The Wildlife Clearance proposal is proposed to be placed for consideration in the upcoming meeting of the Standing Committee of the National Board for Wildlife (NBWL). | Land Acquisition, Phase wise Sanctioning, Forest & Wildlife Clearance | FC | LA | PS |  |  |  | 2338.5 | 2509.237 | 170.737 | Price Escalation and Increase in Land Rates | Escalation in Land Acquisition value
16 | CR | DL | Wardha-Nagpur 4th line | 2017-18 | 2017 | 79 | 2026-03-22 | 2026-03-27 | 5 | 1) delay in aquisition of Land , the new land aquisition The Right to Fair Compensation and Transparency in Land Acquisition, Rehabilitation and Resettlement Act, the procedure for procurement of land was finalized by stated govt in 2018 there after land aquisition work was started. As there was in ordinate delay in aquisition, in 2021 acquistion by Railway Act 2008 was started. and complete land was aquired in 2025. 2. delay in finalization of ESP , out of total 10 ESP's last i.e wardha, Nagpur etc. was finalized in 2024. 3) As already 3rd line work was going on for updating plans for incorporating 3rd and 4th lines there was delay. | Land Acquisition, Phase wise Sanctioning |  | LA | PS |  |  |  | 913.1 | 1194.589 | 281.489 | 1) including 3rd and 4th line, total turnout increased from a) 1/12 from 136 nos to 392 nos b) 1/8.5 from 86 to 146 nos c) derailing switch from 41 to 69 nos d) total loop and siding from 22.08 km to 58.80 km e) building from 5798 sqm to 14862 sqm and corresponding increase of earthwork and bridge work due to it. | Change in Scope of Work based on Actual Field requirement
3 | ECoR | NL | Jeypore-Malkangiri © | 2017-18 | 2018 | 130 | 2026-10-22 | 2026-10-30 |  | 14 Over head elictrical lines need shifting. | Land Acquisition, Utility Shifting | [6 empty] | 2343.64 | 2343.64 | 0 | NA | No Cost overrun, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
4 | ECoR | NL | Jeypore-Nabarangpur © | 2017-18 | 2017 | 41 | July'22 | 2026-10-30 | 8.25 | Due to delay in Land acquisition. | Land Acquisition |  | LA |  |  |  |  | 747.91 | 747.91 | 0 | NA | No Cost overrun
17 | ECoR | DL | Vizianagram-Titlagarh (Sambalpur) 3rd line | 2016-17 | 2015 | 265 | Jun'2027 | 2026-03-28 | 0 | NA | No Delay | [5 empty] | ND | 2335.68 | 6669.61 | 4333.93 | Major Reasons for increase in cost due to other than price escalation (Impact INR 1594.23Cr.) The increase in project cost is mainly attributable to increased land requirements, additional earthwork, and expansion of civil, track, station, electrical and S&T works. Private land acquisition increased from 177 to 355 acres and Government land from 59 to 92 acres, Retaining walls increased from 12.20 to 28.50 km and drains from 151.23 to 190.97 km. Bypass and loop line lengths increased from 1 to 7.68 km and 30 to 54.89 km, respectively, requiring additional rails, sleepers, fastenings, points and crossings, and ballast. LHS increased from 19 to 58, along with provision of five new ROBs, eight major bridges omitted in AE/DE, and additional minor bridge works. Station works expanded to include increased building area, 11 new TM sidings, additional platform shelters, 15 new island platforms and 5,279 m of platform extensions. Further increases arose from electrical works and expanded S&T requirements, including additional cabling, dual-detection MSDAC, electronic interlocking with hot standby, HASSDAC and multiple IPS systems to accommodate enhanced yard capacity and station loads. Major Reasons for increase in cost due to price escalation (Impact INR 2734.99Cr.) Escalation in cost due to GST impacts in post GST period. Blanketing material and Earthworks as rates of these items are site specific and increased substantially as per prevailing rates in the geographical area of the project. P.way items involving supply of rails, sleepers and ballast: The cost escalation occurred due to increase in cost of rails & sleepers as per the prevailing prices of Railway/SAIL and ballast as per the prevailing increase in transportation cost over the period of time. Increase in rate of building materials especially cement and steel and labour cost over the period of time. Increase in rates of S&T and Electrical cables over the period of time. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
18 | ECoR | DL | Jarapaada- Budhapank 3rd & 4th line with flyover at Talcher. | 2015-16 | 2015 | 101 | 2026-11-18 | 2026-03-28 | 7.9167 | COVID Pandemic, Delay in land acquisition, Frequent obstruction of works by local villagers (i.e. villagers of Tukuda & Jamunda received the compensation amount for structure as well as land but not allowing the execution of work by demanding extra compensation under R&R policy, villagers of Kanyabeda, Sana Karabereni, Bada Karabereni & Bhogobereni are not allowing to execute the work due to chakka land), Delay in shifting of utilities (i.e. Water Pipelines, Electrical LT, HT, EHT lines and mast & Transformers, Shifting of S&T Cables), Unauthorized Hutments. | Land Acquisition |  | LA |  |  |  |  | 701.61 | 1671 | 969.39 | The increase in project cost is mainly due to increased in cost due to increase in cost of land, increase of cost of land, earthwork, bridges, Pway, electrical and S&T works. Change in basic prices i.e USSOR-2010 to USSOR-2021, CPWD-DSR-2010 to CPWD-DSR-2021. Escalation in cost due to GST impacts in post GST period. The cost escalation occurred due to increase in cost of rails & sleepers as per the prevailing prices of Railway/SAIL and ballast as per the prevailing increase in transportation cost over the period of time. Increase in rate of building materials especially cement and steel and labour cost over the period of time. Increase in rates of S&T and Electrical cables over the period of time. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value | -
19 | ECoR | DL | Budhapank- Salegaon via Rajatgarh 3rd & 4th line | 2015-16 | 2015 | 170 | Dec'20 | 2026-12-26 | 6 | Delay in land acquisition, Delay in forest Diversion, Delay in shifting of utilities (i.e. Water Pipelines, Electrical LT, HT, EHT lines and mast & Transformers, Shifting of S&T Cables), | Land Acquisition |  | LA |  |  |  |  | 1172.92 | 2500 | 1327.08 | The increase in project cost is mainly due to increased in cost of land. additional earthwork, and expansion of TATA LINE, station, electrical and S&T works. Increase in loop line lengths.Requiring additional rails, sleepers, fastenings, points and crossings, and ballast. LHS increased . additional minor bridge works. Increase in Circulating area. Inclusion of Animal Over pass amounting to Rs.100 Crs.Increase in H.L Plat form area, Station works expanded to include increased Station Building area, additional platform shelters, Island platforms . Further increases arose from electrical works and expanded S&T requirements, including additional cabling, dual-detection MSDAC, electronic interlocking with hot standby, HASSDAC and multiple IPS systems to accommodate enhanced yard capacity and station loads. Change in basic prices i.e USSOR-2010 to USSOR-2019, CPWD-DSR-2010 to CPWD-DSR-2021. Escalation in cost due to GST impacts in post GST period. Blanketing material and Earthworks as rates of these items are site specific and increased substantially as per prevailing rates in the geographical area of the project. P.way items involving supply of rails, sleepers and ballast: The cost escalation occurred due to increase in cost of rails & sleepers as per the prevailing prices of Railway/SAIL and ballast as per the prevailing increase in transportation cost over the period of time. Increase in rate of building materials especially cement and steel and labour cost over the period of time. Increase in rates of S&T and Electrical cables over the period of time. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value
20 | ECoR | DL | Kottavalasa-Koraput | 2015-16 | 2015 | 189 | Dec'22 | 2026-03-29 | 5.25 | 1.0 Execution of works between BDVR-KVLS section (50.87 kms) completely stopped due to forest land diversion for approach road through reserve forest area from 23.03.2025 to 31.01.2026.Again commenced after obtaining working permission on 01.02.2026. 2.0 Difficult terrain with hard rock cutting , tunnelling , major bridges over sharp curves of 8 degree, non approachable sites etc. | Forest & Wildlife Clearance | FC | [5 empty] | 2499.71 | 4378.51 | 1878.8 | Cost Overrun: Increase in scope of tunnelling between SLPM-BGHU section. | Uncertainity in Geological Condition
21 | ECoR | DL | Koraput-Singapur Rd. | 2015-16 | 2015 | 165 | Dec'27 | 2026-03-28 | 0.25 | Works in difficult geology | Forest & Wildlife Clearance, Land Acquisition |  |  | PS |  |  |  | 2361.74 | 4887.63 | 2525.89 | (i) Land Rates has increased (ii) Area of land has increased to the tune of 55.48% over the abstract estimate. (iii) Price esclation i.e. Project sanctioned 2015-16.(iv) Structural engg. works, formation, P.Way, Bridges, Station Building qty has increased.. | Change in Scope of Work based on Actual Field requirement, Escalation in Land Acquisition value, Market Inflation increase in cost of raw material | 1st revised estimate is under vetting.
22 | ECoR | DL | Jagdalpur-Koraput | 2015-16 | 2015 | 107 | Dec'22 | 2026-12-27 | 5 | 2. Difficult terrain with hard rock cutting , tunnelling , major bridges over sharp curves of 8 degree, non approachable sites etc. | Phase wise Sanctioning |  |  | PS |  |  |  | 1547.38 | 3406.16 | 1858.78 |  | Escalation in Land Acquisition value, Change in Scope of Work based on Actual Field requirement
5 | ECR | NL | Jhajha-Batia | 2018-19 | 2019 | 20 | 2026-03-29 | 2026-03-29 | 0 | Resistance in Land Acquisition | Land Acquisition | [6 empty] | 497 | 588 | 91 |  | Escalation in Land Acquisition value
23 | ECR | DL | 3rd line bet. Dhanbad-Sonnagar | 2016-17 | 2015 | 291 | Mar'26 | 2026-12-28 | 2.75 | COVID Pandemic, LWE affected areas, Delay in approval of ESPs and SIPs of Stations, Delay in removal of weigh bridge and siding line by CCL for 3rd line connectivity, Delay in declaration of PTR Diversion, Delay in shifting of utilities (i.e. Water Pipelines, Electrical LT, HT, EHT lines and mast & Transformers, Shifting of S&T Cables) | Utility Shifting |  | LA |  |  | US |  | 3406.16 | 7906.38 | 4500.22 | Increase in cost manly due to Change is specifications (intorduction of Wide base PSC sleepers & 260m panel Rail.), High level passanger platform, New FOB, Increased no of Crossing station, Converion of Block Hut to station, Provision of new Long loop and provision for diversion of existing double line & new line to a new alignment after avoiding Palamu Tiger Reserve (PTR) zone increase of no. of ATs along with increase in cable CLS panel etc. Provision of EI Alteration instead of PI Alteration, MSDAC in place of DC Track Circuit, fire alarm system (not included in DE), 03/02 nos. quad cable provided in block section insted of single quad cable provision. | Change in Scope of Work based on Actual Field requirement | 1st revised estimate is under consideration with Railway Board.
24 | ECR | DL | Rampur Dumra - Tal-Rajendra Pul-Additional bridge and doubling | 2015-16 | 2016 | 14 |  | 2026-10-26 |  | Project commissioned on 04.10.2026 | No Delay | [6 empty] | 923 | 2535 | 1612 |  | Market Inflation increase in cost of raw material
25 | ECR | DL | Sagauli-Valmikinagar | 2017-18 | 2017 | 110 | Mar' 22 | 2026-12-26 | 4.75 | 101.08 KM commissioned out of 109.7 KM. Due to delay in cosntruction of Major Bridge No. 352 between Kharpokhra-Bagaha section, one block section is due for commissioning. The bridge is under construction and due to sand blowing phenomenon developed during sinking of well, sinking of well foundation was stopped since February 2025. After troubleshooting, the work has again resumed since September 2026. | Phase wise Sanctioning |  |  | PS |  |  |  | 745 | 1558 | 813 |  | Change in Scope of Work based on Actual Field requirement
26 | ECR | DL | Gaya Bye pass for Manpur | 2016-17 | 2017 | 2 |  | 2026-12-27 |  | Kept in abeyance | Phase wise Sanctioning | [8 empty] | 0 | Project was inactive | Administrative reason
27 | ECR | DL | Muzaffarpur-Sugauli | 2017-18 | 2022 | 101 | Mar'25 | 2026-07-28 | 3.3333 | Commissioning of last block section of Muzaffarpur-Kaparpura section (6.89 Km) Only 6.89 km section is remaining. As per DPR of the said project, initially it was planned to take off the proposed doubling from MFP-SMI line (after ROB Damdarpur) due to space constraint in accommodating additional new line, hence, in order to complete doubling upto MFP as directed by higher authority, construction of new ROB Damodarpur to accommodate third line was proposed in revised estimate and got sanctioned by GM/ECR. Also ESPs of MFP and KVC revised multiple times as per requirement of operating department. Finally it has been decided by higher authority to commission doubling of MFP-KVC section (last block section) with construction of Damodar Pur ROB. The work of new ROB Damodarpur is in progress and is planned to be completed by Mar-28. However, to construct additional new line upto MFP, the existing ROB is required to be dismantled for which TDC is June-28 as dismantling of ROB over running line is to be done and hence, commissioning of MFP-KVC will be done by July-28. | Phase wise Sanctioning |  |  | PS |  |  |  | 1185.73 | 1744.84 | 559.11 | Additional work of two nos. ROB and doubling upto Muzaffarpur. | Change in Scope of Work based on Actual Field requirement
28 | ECR | DL | Gomoh- Flyover for DN trains | 2017-18 | 2018 | 42 | Mar'26 | 2026-01-27 | 0.83333 | 221.981 acre land acquisition involved. Paper possession given. Disturbance by land losers, to whom payment not disbursed so far (payment deposited in Courts) | Land Acquisition, Law and Order Issue |  | LA |  | LO |  |  | 95 | 686.03 | 591.03 | Resistance due to land acquisition compensation cost | Escalation in Land Acquisition value
29 | ER | DL | Byepass at Sainthia (5 Km), Sitarmpur (7 Km), Mughalsarai, Allahabad, Etawah (11 Km) | 2018-19 |  | 24 | 2026-03-27 | 2026-06-27 | 0.25 |  | Land Acquisition |  | LA |  |  |  |  | 548 | 798 | 250 | Change in Scope of work | Change in Scope of Work based on Actual Field requirement
30 | NCR | DL | Jhansi-Bina 3rd line | 2016-17 | 2016 | 153 | Mar'22 | 2026-12-26 | 4.5833 | Protected mounments came along the proposed alignment and necessary clearances from ASI takes time Further, delayed due to remodelling of Bina Yard (WCR) planned with 3rd line work in OCt'26. Project completed in Oct'2026 after opening of section between Agasod - Bina. | Phase wise Sanctioning |  |  | PS |  |  |  | 1212 | 2001.63 | 789.63 | Original Sanctioned Cost of Detail Estimate:- Rs. 2002 Cr, Anticipated Cost:- Rs. 2002 Cr, Cost Overrun w.r.t. Detail Estimated Cost is Nil. | No Cost overrun
31 | NCR | DL | Mathura-Jhansi 3rd line | 2016-17 | 2016 | 274 | 2026-12-23 | 2026-12-27 | 3 | Kitham-Bhandai Bypass line with Land Acquisition and tree cutting in TTZ area . | Forest & Wildlife Clearance, Land Acquisition | FC | LA |  |  |  |  | 3677.76 | 5960.76 | 2283 | Price Escallation & Land cost, Forest clearance related Cost, High embankment and increase in Bridges in Kitham-Bhandai Bypass line section. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material | The Kitham-Bhandai bypass line section had to be done with vast Land acquisition [153 Ha] in outskirt of Agra City, with removal of 5094 trees with permissioon fro Hom'ble Supreme Court, in High bank requiring huge earthwork, sevreal bridges increased durion execution on demad by public and Civil Administration, as such time and cost increase.
32 | NCR | DL | Jhansi-Khairar-Manikpur & Khirar-Bhimsen | 2017-18 | 2018 | 431 | 31/3/2026 | 2026-12-28 | 2.75 | Due to extra time being taken in construction of Important Bridge at Dhasan River due to standing water, time overrun has occurred. | Phase wise Sanctioning |  |  | PS |  |  |  | 3000 | 4330 | 1330 | Original Sanctioned Cost of Detail Estimate:- Rs. 4330 Cr, Anticipated Cost:- Rs. 4330 Cr, Cost Overrun w.r.t. Detail Estimated Cost is Nil. | No Cost overrun
33 | NCR | DL | Lalitpur-Birari with flyover at Lalitpur | 2016-17 | 2017 | 16 | Mar'24 | 2026-01-27 | 2.8333 | Land Acquisition & Non availability of speed restriction on Main line between Dailwara-Lalitpur for launching of ROR Girder. | Land Acquisition |  | LA |  |  |  |  | 260 | 304.44 | 44.44 | Original Sanctioned Cost of Detail Estimate:- Rs. 304 Cr, Anticipated Cost:- Rs. 304 Cr, Cost Overrun w.r.t. Detail Estimated Cost is Nil. | No Cost overrun
6 | NER | NL | Bahraich & Khalilabad via Binga, Shravasti, Balrampur, Utraula, Domariyaganj, Mehdawal, Bansi new BG Line | 2018-19 | 2018 | 240 | 2026-10-24 | 2026-10-30 |  | Land acquisition issues in fertile terai belt | Land Acquisition | [6 empty] | 1600 | 4939 | 3339 |  | Escalation in Land Acquisition value
34 | NER | DL | Bhatni-Aurnihar with electrification (125 Kms) excluding Indara-Mau | 2017-18 | 2018 | 117 | 31.03.2024 | 2026-03-27 | 2.6667 | 1. Delay in receiving the forest clearance. On line proposal for diversion of 162.87 hectare Land and cutting of trees 6715 nos was submiited on 31.01.2020 and stage -II approval received on 04.05.22 resulting in 16 Minth effective delay. 2. outbreak of Covid-19 and subsquent lockdown paralyse the project progress in 2020 & 21. 3. During the execution of Project, the State Bridge Construction Corporation stopped the heavy vehicle movement over the Ghagra bridge due to repair work carried out w.e.f 14.01.2022. Due to restriction imposed, Earthwork at Important Bridge-31 approach and transportation of blanketing material suffered. 4.Kumbh Mela 2025: Due to Kumbh Mela 2025, Line suspensions and Cut & Connection Works/Blocks & Pre-NI/NI works were not allowed from Nov-24 to Feb-25, resulting in delay of works by atleast 4 months. 5.Complex section due to the involvement of 13 cut and connections-This section is uniquely complex, differing from a normal doubling project due to the involvement of 13 cut and connection locations ie about 01 Cut & Connection in every block section .Due to involvement of cut & connections, continuous patches were not available in the section & many locations were isolated in section.This created difficulty in the transporting materials such as Earthwork, Blanket, Ballast , Rail etc. at the location | Forest & Wildlife Clearance | FC | [5 empty] | 1177.96 | 2529.46 | 1351.5 | Major Reasons for increase in cost due to price escalation (Impact INR 1162Cr.) Escalation in cost due to GST impacts in post GST period. Blanketing material and Earthworks as rates of these items are site specific and increased substantially as per prevailing rates in the geographical area of the project. P.way items involving supply of rails, sleepers and ballast: The cost escalation occurred due to increase in cost of rails & sleepers as per the prevailing prices of Railway/SAIL and ballast as per the prevailing increase in transportation cost over the period of time. Increase in rate of building materials especially cement and steel and labour cost over the period of time. Increase in rates of S&T and Electrical cables over the period of time. Major Reasons for increase in cost due to other than price escalation (Impact INR 188 Cr.) The increase in project cost is mainly attributable to payment to forest department, providing of 550 mm thickness blanket over 400 mm as per estimate, expansion of civil, track, station, LC building LHS , works. Further increases arose from expanded S&T requirements, including dual-detection MSDAC for 15 track section complete with 18 detection heads as per instruction of NER , Supply of SSBPAC and transfer of fund for yard remodelling of Aurnihar Yard and for Peokol and Bhatni Syard done by NER construction. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Administrative reason
35 | NFR | DL | New Bongaigaon- Goalpara-Guwahati (Kamakhaya) | 2016-17 | 2016 | 176 | 2026-03-26 | 2026-03-28 | 2 | The doubling work was stopped by the NGT, East Zone, vide order dated 18.01.2018, and the NFR was directed to include mitigation measures to prevent potential elephant- train collisions. On the request of the Chief Wildlife Warden of Assam, Dr. Bivash Pandav of WII had visited the site in January 2019 and WII had suggested realignment of the railway track or construction of a tunnel. Both were found to be unfeasible from the financial and technical point . Subsequently, NFR has proposed an elevated track for elephant movement. The plan was discussed in a meeting held by the Chief Secretary, Assam on 25th June 2021. A field visit by the WII team was subsequently carried out during 27th – 30th September 2021. The entire length of the railway track was surveyed, and the locations and structural dimensions of all proposed mitigation measures. NBWL clearance has been obtained on 28.04.2022 After NBWL clearance stage I clearance for 0.82 ha forest land has been obtained. After requisite clearances soil exploration and other works has been taken up in this portion for designa. At present the EPC tender has been awarded and work is in progress. | Forest & Wildlife Clearance | FC | [5 empty] | 1925.07 | 4983.94 | 3058.87 | Main reason for cost increase is due to introduction of 4.75km double track viaudct for the elephant corridor and 2 nos new LHS and 1LHS extension and the price escalations over the entire project. The Minor cost escalation is due to increase in track centre result in increase in earthwork qty at bridge location and track component as per latest guidelines. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material
7 | NR | NL | Ferozpur-Patti © | 2017-18 | 2017 | 26 |  | 2026-12-29 |  | Initially the project was sanctioned with proviso that Govt of Punjab will provide land free of cost. However, land acquisition was not processed by GoP. Considering strategic importance of this project, being in border area, MoR decided to take up this project at its own cost in Oct-25 | Land Acquisition | [6 empty] | 147 | 764 | 617 |  | Escalation in Land Acquisition value, Administrative reason
36 | NR | DL | Ludhiana-Kila Raipur(19 Kms) with freight line at Gill station on LDH-JHL | 2018-19 | 2019 | 19 | 2026-06-24 | 2026-02-27 | 3.6667 | Commissioning of doubling is being planned along with complete yard remodelling including EI of Ludhiana Yard. | Phase wise Sanctioning |  |  | PS |  |  |  | 237.64 | 237.64 | 0 | NI in busy Ludhiana Yard | Administrative reason | Work is in progress.
37 | NR | DL | Barabanki-Malhaur - 3rd & 4th Line(32.84 km) | 2018-19 | 2019 | 33 |  | 2026-01-27 |  | Local area disturbances | Law and Order Issue, Land Acquisition | [6 empty] | 323 | 480 | 157 |  | Escalation in Land Acquisition value
12 | NWR | NL | Nimach-Badi sadri | 2018-19 | 2025 | 48 |  | 2026-12-26 |  | Land acquisition issues in fertile terai belt | Land Acquisition | [6 empty] | 475 | 896 | 421 |  | Escalation in Land Acquisition value
13 | NWR | GC | Marwar-Mavli (GC of Nathdwara (Mavli)-Devgarh Madariya (82.542 Km) ) | 2017-18 | 2023 | 83 |  | 2026-06-28 |  | Survey of carrying alighnment in Ghat section. | Phase wise Sanctioning | [6 empty] | 1597 | 1100 | -497 |  | No Cost overrun
38 | SCR | DL | Kazipet -Ballarshah - 3rd line Excl. Mandamari-Raghavapuram | 2016-17 | 2016 | 202 | Sept 2024 | 2026-12-26 | 2.25 | Total Project commissioned: The last section of the BPQ–KZJ 3rd line project, between Asifabad and Sirpur Kagaznagar, was commissioned on 20 July 2026 Reasons for Time overrun: 1) Covid Pandemic 2) Forest and Wild life clearance 3) 03 Nos of Important Bridges crossing Perennial River. | Forest & Wildlife Clearance, Phase wise Sanctioning | FC |  | PS |  |  |  | 2063.03 | 3071.18 | 1008.15 | 1) Price escalation due to adoption of latest USSOR Rates 2) Yard modification involved at Kazipet,Bellamaplli,Mandamarri,Hasanparthy Road,Manikgarh,Recchi Road and Sirpurkagaznagar with longer duration of Pre NI & NI workings. | Market Inflation increase in cost of raw material, Change in Scope of Work based on Actual Field requirement | Total Project commissioned
39 | SCR | DL | Renigunta, Wadi & Gooty Byepass | 2016-17 | 2016 | 27 | 2020-04-01 | 2026-03-27 | 6.11 |  | Land Acquisition | [6 empty] | 302 | 850 | 548 |  | Escalation in Land Acquisition value
40 | SCR | DL | Vijayawada, Kazipet Byepass line | 2016-17 | 2016 | 47 | KZJ - Apl 2018 | 2026-12-26 | 8.6667 | Kazipet Bypass Total Project commissioned Reasons for Time overrun: 1) Covid Pandemic 2) Length of the project increased from 10.65 Kms to 21.47 Kms | Phase wise Sanctioning |  |  | PS |  |  |  | 125.14 | 292.39 | 167.25 | A) Kazipet Bypass 1) Price escalation 2) (i) Quantites incrersed due to length of the project increased from 10.65 Kms to 21.47 Kms (ii)Efforts to provide yard gradients as flat as possible to avoid grade infringements in yard resulted in increased formation levels thereby increasing bank heights and earthwork quantities. (iii) Originally, the entire section was proposed with GE-G-14. In the course of execution , both GE-G-14 and GE:IRS-0004 guidelines are adopted as prevalent during the time of earthwork. iv) Rates are considered as per latest SSR. | Market Inflation increase in cost of raw material, Change in Scope of Work based on Actual Field requirement | Kazipet Bypass: Total Project commissioned
41 | SCR | DL | Vijaywada- Gudur 3rd line | 2016-17 | - | 287 | 31.09.2022 | 2026-12-26 | 4.25 | (1) COVID Pandemic, (2) Delay in land acquisition process and limited working period due to extended monsoon period being a Coastal area (3) Delay in approval of Drawings, Extended scope due to Material modification consequent up on sanction of Krishna Canal Yard modification works. | Land Acquisition |  | LA |  |  |  |  | 2423 | 7082.81 | 4659.81 | (1) Increase in cost of Construction Material and Labour (2) Increased scope of work (3) Construction of ROR between Gudur - Venkatachalam (4) Increase in height of embankment in various sectoins (5) Imaprovement to yielding Formatoin in Appikatla - Nidupbrolu section (6) Requirement of Quad cable and OFC has increased for provision of MSDAC (7) Requirement of IPS has increased as per new guidelines of RDSO (8) Revised Enhanced power requirement schedule given by SCR for signalling Load from 10 kVA to 25 kVA, the capacity of entire CLS Panel & UG cable were upgraded to 25kVA load (9) As per APSPDCL the PLC modified with enhanced capacity/size of HTUG Cable from 3x185Sq.mm to 3x 300Sq.mm in all the PLC modification locations. (10) Addidtional service buildigns and residential buildings hav ebeen constructed to the revised estiate as per the requirement of division including provision of circulating area at stations. Also the legnth of platforms is increased and existing platforms are proposed with high level. (11) The usage of wider sleepers and points and crossings necessitated new type track fittings to revised specificatoins also TWS with SSD & CMS were used in all the yards has caused considerable excess in the cost. (12) About 70 Nos. of LCs are being taken up for eliminiation by constructing RUBs.(13)Price Escalation consequent up on increased cost of Men and Materials. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material | Out of a total length of 287.87 km tripling with OHE, 281.87 km has been commisioned till date. Only a balance of 7 km along with Krishna Canal junction yard modification is pending, however, this last section is also getting commissioned in Jan-2027.
42 | SCR | DL | Guntakal- Guntur | 2017-18 | 2017 | 401 | 30.05.2022 | 2026-12-27 | 5.7 | Forest clearance and construction of Tunnels | Forest & Wildlife Clearance | [6 empty] | 3631.08 | 4687.41 | 1056.33 |  | Change in Scope of Work based on Actual Field requirement
8 | SECR | NL | Dharamjaigarh-Korba | 2016-17 | 2017 | 63 |  | 2026-03-27 |  | • Delay in Financial closure- FC achieved in 28.08.2023 • Delay in Forest clearance- Stage I clearance-14.07.23 & Stage II clearance-13.05.2025 • Delay in Power line shifting by Utility Owners- As on date, 14 PL is still balance- TDC: 04 HT : 01 Nov’26, 03 Dec’26, 01 EHT : Dec’26, 01 EHT : Jan’27, 01 EHT : Feb’27, 01 EHT : Mar’27, 01 EHT: May’27, 05 EHT : Nov’27 • Re-alignment of RoR line – RoR line had to be re-aligned due to - Crossing of two NH 149B & NH 130A at same location - Time lost ≈ 1 Year, Decision for re-alignment on 19.04.2023, Land award for diverted alignment passed in Mar’2025. Land possession in July 2025 | Forest & Wildlife Clearance, Land Acquisition, Phase wise Sanctioning, Utility Shifting | FC | LA | PS |  | US |  | 1686 | 2439 | 753 | Introduction of EUPs & EOPs as per Wildlife requirement suggested by Forest Department Introduction of Additional Bridges as per Site Requirement Introduction of RE wall on approaches of ROBs Deposit Works (Works being executed by Railways & Other State Govt. Authorities) Increase in Cost due to Change in rate of GST (GST rate changed from 12% to 18%) Increase in Cost on account of PVC Increase in Cost due to Change in Design, Size, Type and Span of bridges as per Site requirement Cost of modification of Lenco Station (S&T works) Increase due to change in Bhaisma station (3 line to 4 line) & alteration in dharamjaigarh yard. Increase in scope of Block working (6 to 9 block sections) Introduction of 2x25 KV system of OHE as per Railway Boards Instructions Increase in cost of power line modification Increase in cost of plant and equipment | Market Inflation increase in cost of raw material, Administrative reason
9 | SECR | NL | Chirimiri-Nagpur Halt © | 2018-19 | 2025 | 17 |  | 2026-12-28 |  | Forest clearance | Forest & Wildlife Clearance | [6 empty] | 241 | 659.45 | 418.45 | 1) Price escalation due to adoption of latest USSOR and DSR Rates. | Market Inflation increase in cost of raw material
43 | SECR | DL | Jharsuguda-Bilaspur -4th line | 2016-17 | 2020 | 206 |  | 2026-11-26 |  | NI in heavy busy coal loading section | Phase wise Sanctioning | [6 empty] | 2104 | 2978 | 874 |  | Escalation in Land Acquisition value, Administrative reason
44 | SECR | DL | Gevra Rd-Pendra Rd | 2015-16 | 2018 | 135 | 01.03.2024 (as per PEA, 182 weeks from the date of approval by CERL to go ahead the award of contract, Financial closure-04.09.2020) | 2026-06-27 |  | Delay due to NGT case (2016-2019) - LOA for civil work including E/W, Major and Minor bridges from KM 98 to 135 was issued -19.07.2016. However, Case is filed in NGT court in Dec’16 due to which ongoing works were to be suspended. NGT case was disposed on 29.04.2019. • Delay in forest clearance (2014-2018) - Registration of forest proposal was completed in June 2014. However, Stage-I clearance was obtained in 26.02.2018 and Stage-II clearance was obtained in 07.06.2018 • Delay due to Introduction of Wildlife passes as per MoEF requirement (2018-21)- 7 Nos EOPs/EUPS were finalized by CCF Bilaspur in April’2018. Accordingly, L-section were revised and 7 Nos EOPs/EUPs were incorporated in Aug’2020. Further, PCCF advised to construct 22 Nos EOPs/EUPS in Oct’21. L-section has been revised and EOPs/EUPS were incorporated in Dec’21. • Non-performance of contractor- Non-performance of contractor M/s RMN (Civil work from Km 29-67) and termination of contract of Pkg 2B on 19.05.2025 • Delay in award of S&T tender- As approved by SECR on 30.04.2024, Inclusion of various signalling and telecom items in compliance to the latest policy guidelines of SECR has resulted in delayed invitation of tenders of S&T works which was further delayed S&T tenders for CEWRL was floated on 11.06.2024 but discharged on 14.12.2024 due to administrative reason. Retender for the same was floated on 08.01.2025 but delayed due to court litigation by L-2 bidders, Final verdict was awarded by Delhi High court on 08.08.2025 and LOA was awarded on 13.08.2025 resulting in delay in time line for completion of project. • Shortage of funds - During the working period from March’25 to June’25, the progress of works slowed down because of insufficient cash flow with the contractors. • Financial closure on 04.09.2020.Covid-19 Delay in handing over of hindrance free site . • Surakachar Siding - Handed over on 24.05.2024 • Removal of encroachment on SECL Land in Surakachar - Removed on 31.01.2024 • Removal of encroachments in Krishnanagar - Removed on 10.08.2024 • Non-closing of SECL Road in Urga – Kusmunda section - Closed on 09.11.2024 • Non –removal of toilet block in Urga - Kusmunda section - Removed on 06.11.2024 • Stoppage of work in Krishna Nagar area for demand of their rehabilitation & resettlement (156 Nos.) • Introduction of Elephant under passes • Modification /Shifting of overhead electrical lines. • Changes in OHE alongwith size of bridges due to site requirement & by Railways. • Changes in GSS to TSS supply of 220 KV in Jan’25 • As per MoF circular dated:29.04.2026 followed by MoR circular dated:22.05.2026, Force Majeure invoked on 27.02.2026, with repercussions of 02 -04 months of extension. | Forest & Wildlife Clearance, Land Acquisition, Phase wise Sanctioning, Law and Order Issue, Utility Shifting | FC | LA | PS | LO | US |  | 4970 | 7448 | 2478 | Introduction of EUPs & EOPs as per Wildlife requirement suggested by Forest Department Introduction of Additional Bridges as per Site Requirement Deficient Provision of Track Linking Items Deposit Works Increase in Cost on account of PVC Increase in Cost due to Change in Design, Size, Type and Span of bridges as per Site requirement Increase in Cost due to Variation in Earthwork Quantities Increase in cost of DPR due to GST rate change from 12 % to 18 % Upgradation/ Modification/ Deletion/ Change in scope of items covered in DPR like Telecom System Upgraded with IP-MPLS, IBS Upgraded with EI Communication, Traction transformer and SCADA as instructed by SECR, Change in cost of 132 KV DC Transmission line by utility Company CSPTCL based upon site conditions and surveys by the utility companies, Change in cost of Power Line Modification by Utility Companies, depending upon the site conditions, encroachments, R&R, ROW issues, forest etc. Introduction of 2x25 KV system of OHE as per Railway Boards Instructions (not covered in original DPR) Yard Electrification works of Pendra, Gevra, Urga, Korba/TSS, Pendra/TSS, TPC Control (not covered in original DPR) New Power Line Crossings not covered in DPR (not covered in original DPR) | Administrative reason
45 | SECR | DL | Jharsuguda-Bilaspur - Flyover/ Bye pass | 2015-16 | 2015 | 10 |  | 2026-12-29 |  | 25 High Tension lines passing through alignment requires shifting. | Utility Shifting, Land Acquisition, Law and Order Issue | [8 empty] | 0 | delay in shifting of utilities | Escalation in Land Acquisition value, Change in Scope of Work based on Actual Field requirement
46 | SECR | DL | Rajnandgaon-Nagpur 3rd line | 2016-17 | 2023 | 228 |  | 2026-02-27 |  | Darekasa - Salekas section of this project passes through wildlife zone. Several wild life mitigation measures including 480m viaduct for both lines were added . | Forest & Wildlife Clearance | [6 empty] | 1280 | 3544 | 2264
47 | SECR | DL | Raipur-Titlagarh (203 km) incl. NL Mandir Hasaud-Naya Raipur (20 km) & new MM for conversion of Raipur(Kendri)-Dhamtari & Abhanpur-Rajim branch (67.20 km) | 2016-17 | 2018 | 290 |  | 2026-11-26 |  | Main project of Raipur - Titlagarh DL has been completed. Additional projects sanctioned as Material Modification are under progress | Phase wise Sanctioning | [6 empty] | 2084 | 3249 | 1165
48 | SER | DL | Bondamunda-Ranchi | 2015-16 | 2016 | 159 | Jun'25 | 2026-06-27 | 2 | Delay in forest clearance/working permission in three block sections. Rock cutting 27 lakh cum in forest area in three block sections. Rock cutting in deep cuttings with precautions for safety of running trains. Compliance to blasting permission regime in naxal influenced area. Non availability of land in one block section (Link C- Dumetra). | Forest & Wildlife Clearance | FC | [5 empty] | 1724.2 | 3029.04 | 1304.84 | Assesment of hard rock quantity was less than actual and due to time over run. | Uncertainity in Geological Condition
49 | SER | DL | Kharagpur-Adityapur 3rd line | 2016-17 | 2022 | 132 | 2026-07-22 | 2026-11-26 | 4.3333 | 1. Due to frequent modification of ESPs and subsequent changes in works. 2. Late approval of alignment plan of NMP-KKQ section. 3. Lockdown due to Covid 19 pandemic. 4. Increasing of scope of work related to Yard remodeling works. 5. Introduction of wider base PSC sleeper in place Ordinary sleeper. 6. Introduction of MSDAC etc. | Phase wise Sanctioning |  |  | PS |  |  |  | 1312.44 | 3509.82 | 2197.38 | 1. Increase of E/W from 35.82 Lakh cum to 55.01 Lack CUM due to increase of yard lines, turn-outs, long loop, TM siding, change of TC from 5.3m to 7.8m and increase of formation width as per Rly BD policy circular. 2. Procurement of LD slag due to non availability of good earth /blanketing material, for imposition of banning of mining materials by civil authority. 3. Additional loop lines at NMP, RHE, ADTP and construction of concrete drain for 34 km against DPR provision of 20 km. 4.Additional material cost for increase of turnouts from 241 to 476, Yard length from 20 km 44 km, Wider base PSC sleeper. 5. Payment to Rly for 15 nos LHS against 02 (DPR), Rubberised surface of 23 nos LCs. 6. Increase of minor bridge 157 nos to 171 nos, Conversion of 1 minor bridge to major bridge and increase of barrel length of minor bridges, additional protection works as per site condition, river training work. 7. Additional FOBs and high level platforms, circulating areas at different stations, service buildings from 3861sqm to 32191.39sqm and residential buildings from 68 to 153nos (Type II) from 8 to 14nos (Type IV) from 2 to 14 nos (Type -V) and additional payment to Rly for hire charges of track machine. 8.Price Variation etc. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material
50 | SER | DL | Narayangarh-Bhadrak 3rd line | 2018-19 | 2019 | 153 | Dec'25 | 2026-02-27 | 1.1667 | Restricted supply & increase in royalty on minor minerals. Waterlogged area- difficult terrain in monsoons. Removal of encroachments in two block sections (either side of Baleshwar station). | Utility Shifting |  |  |  |  | US |  | 1866.31 | 3425.32 | 1559.01 | 1. Increase in scope due to addition of station building , circulation area development , Loop line , tower wagon shad inclusion and incorporation of track machine siding and new FOB. 2. Provision of double distance in NYA-BHC have been additionally incorporated in this estimate | Change in Scope of Work based on Actual Field requirement
10 | SR | NL | Morappur-Dharmapuri | 2018-19 | 2019 | 36 |  | 2029-30 |  | Due to delays in land acquisition, tenders have been invited for the work in the 10.221 km stretch where land has been acquired. | Land Acquisition | LA | [5 empty] | 358.95 | 359 | 0.05
51 | SR | DL | Trivandrum- Kanyakumari | 2017-18 | 2017 | 87 | 2026-12-24 | 2026-03-29 | 4.25 | 1.Dealy in Land acquisition 2.Covid-19 pandemic 3.Unfavourable working conditions due to heavy monsoon rains in Kerala and Tamil Nadu, resulting in a shorter working season and reduced availability of productive working days. 4.Delay in obtaining statutory approvals and clearances from various departments. | Land Acquisition, Phase wise Sanctioning | LA |  | PS |  |  |  | 1431.9 | 4509 | 3077.1 | 1.Price Escalation & Land cost, 2.Increase in Land acquisition in the densly populated areas in Kerala and Tamil Nadu. 3.Increase in scope of work due to addition of new buildings and other structures 4.Increase in cost of Construction Material and Labour 5.Change in basic prices i.e USSOR-2010 to USSOR-2021, CPWD-DSR-2010 to CPWD-DSR-2021. 6. | Escalation in Land Acquisition value, Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material | Out of 86.56Km, 32.63km commisiioned till now and work is in progress in all other sections
52 | SWR | DL | Bangalore-Whitefield-Bangalore City-Krishnarajapuram Quadrupling | 2017-18 | 2018 | 38 | 2026-12-24 | 2026-07-27 | 2.5833 | 1. The entire stretch falls in the Bangalore city area with heavy road traffic. The movement of construction vehicles is prohibited between 08.00AM to 11.00AM and between 04.00 P.M to 08.00 PM, therefore, the work needs to be carried out mostly during night hours. Most of the stretch has restricted access due to built up area adjacent to Railway land. 2. Railway land available for Quadrupling work is just sufficient to lay 2 additional railway tracks and around 12km of retaining wall construction was mandatory due to which shifting of amenities of railwaya sn state amenities and road closures cordination with statte govt. authorities delatyed work. 3. The entire reach between Bangalore Cantonment-Whitefield is automatic signalling territory having S&T cables at both sides of existing tracks. Earthwork and retaining wall work has to be carried out in the presence of signalling staff to avoid cable cut incidences. Further, location boxes are required to be shifted/protected. Huge bunch of cables are found during excavation for retaining wall and work has to be done very slowly. 4. Due to shifting of utilities pertaining to BWSSB (Bangalore Water supply and Sewerage Board), BESCOM (Bangalore Electric Supply Co), GGL (Gail Gas Ltd) pipeline etc. 5. Due to freeing of Railway land/soft enchroachment being used as City Roads at few locations. 6. Delay in obtaining permission from forest dept. towards felling down of trees. 7. Involvement of huge pre-NI/NI works for commissioning the 3 major yards in busy Bengaluru suburban traffic area. | Utility Shifting |  |  |  |  | US |  | 492.87 | 664.54 | 171.67 | 1. Increase of Earthwork from 2.34 lakh cum to 4.22 lakh cum for bridge formation, approaches, retaining wall construction and cut & connection. 2. Constructing RCC wall as required at site due to land constraints. 3. Due to conversion of existing 66 KV DC Hoody LILO Line to proposed 132kV Class 1000 Sqmm U.G. Cable and Stores procurements. (Electrical work) which was infringing the hoodi station on the proposed quadrupling line. 4. Due to introduction of new S&T item (MSDAC) 3 Major yard remodellings with latest EI . 5. Due to increase in quantity of P.Way materials (PSC Sleepers, ERC clips, metal lines, Rubber pads). | Change in Scope of Work based on Actual Field requirement
11 | WCR | NL | Indore-Budni (Indore-Jabalpur) | 2018-19 | - | 198 | Mar'30 | 2026-03-30 | 0 | NA | No Delay | [5 empty] | ND | 3261.82 | 11916.03 | 8654.21 | NA | No Cost overrun | -
53 | WCR | DL | Katni- Grade separator / Byepass | 2016-17 | - | 35 | 2026-03-22 | 2026-03-27 | 5 | Delay in land acquisition. Less allottment of funds during intial years delayed the project and CORONA stalled works for almost 2 years. | Land Acquisition |  | LA |  |  |  |  | 156 | 2300 | 2144 |  | Escalation in Land Acquisition value
54 | WCR | DL | Katni- Singrauli | 2015-16 | 2021 | 257 |  | 2029-30 |  | Change in alignment for two block sections due to wildlife. Evwn existing line between Joba- Beohari is being diverted outside forest area. This increased scope of work | Forest & Wildlife Clearance | FC | [5 empty] | 1739 | 4313 | 2574 |  | Escalation in Land Acquisition value
55 | WCR | DL | Satna-Rewa | 2015-16 | 2016 | 50 | 2026-03-21 | 2026-03-27 | 6 | Work stalled due to agitation by land losers demanding job against land Land acquisition and possession finally completed in 2025. Less allottment of funds during intial years delayed the project and CORONA stalled works for almost 2 years. Project will complete in Decmber 2026. | Land Acquisition, Law and Order Issue |  | LA |  | LO |  |  | 500 | 616 | 116 |  | Escalation in Land Acquisition value
56 | WR | DL | Vatwa- Ahmedabad- Sabarmati - 4th line | 2016-17 | 2016 | 15 | 2026-06-16 | 2026-12-27 | 11.5 | As the Vatva – Ahmedabad – Sabarmati 4th line project is coming in the alignment of High-Speed Corridor, WR/CON was asked to slow down the progress of this work vide NHSRCL Letter No NHSRCL/MA/CE01/DGN-TVAS-STN/26.1/636 Dtd 13.12.2017 and in meeting held on 25.01.2018 it was finally decided to forego the 4th line in this stretch. Accordingly, the Project is shelved by Railway Board. Vide Railway Board letter No. 2018/INFRA/12/05 dtd. 20.02.2020, Ahmedabad yard remodelling work is to be executed against this project. Ahmedabad yard remodelling involves coordination between NHSRCL, RLDA, Division as executing agencies and other utility shiftings. | Utility Shifting |  |  |  |  | US |  | 241.43 | 241.43 | 0 | Nil | No Cost overrun | No Cost Overrun
[18 empty] | 76658.55 | 152374.706 | 75716.156
[5 empty] | No data | 39

## Active 19-24
S.N | Rly | PH | Name of Project | Sanctioned Year | DE Sanction Year | Length of project (Km) | Original TDC | Anticipated TDC as given by Rly | Time overrun | Reasons for Time overrun | TIME OVERRUN REASON | Forest Clearance & Wildlife | Land Acquisition | Phase wise Sanctioning | Law & Order issue | Utility Shifting | No delay | Original Sanctioned Cost | Anticipated Cost | Cost overrun | Reasons for Cost Over run | COST OVERRUN REASON | Remarks
1 | CR | NL | Kalyan-Murbad via Ulhasnagar © | 2022-23 | 2023 | 28 | 2026-03-27 | 2026-03-30 | 36 Months | Delay due to Land aquisition | Land Acquisition | [6 empty] | 728 | 1627 | 899 | NA
21 | CR | GC | Pachora-Jamner with extension upto Malkapur NG to BG | 2022-23 | 2022 | 84 | 2026-03-27 | 2026-03-30 | 3 years | Delay in land acquisition | Phase wise Sanctioning, Land Acquisition | [6 empty] | 955.39 | 1983.22 | 1027.83 | The variation is due to price escalation and increase in quantity of land acquisition and earthwork due to increase in bank height since, height of RUB/ LHS proposed is 3.0m in approved DPR while State Govt (Road authority) vide L. No. ZP/ Jalgaon/ Construction/RR/466/ 2023 has demanded vertical clearance of 5.0m/ 5.50m. | Change in Scope of Work based on Actual Field requirement
108 | CR | DL | Double Chord Line between Nilje and Kopar | 2023-24 | 2023 | 4 | 2026-07-28 | 2026-03-27 | Nil | Delay in land acquisition | Land Acquisition | [6 empty] | 338 | 338 | 0 | NA
2 | ECoR | NL | Talcher & Angul with 'Y' connection at Talcher | 2019-20 | 2020 | 14 | 2028-06-01 | 2026-12-28 | 6 months | Land acquisition not completed due to public agitation at village Ghantapada. | Land Acquisition |  | LA |  |  |  |  | 278.96 | 494.67 | 215.71 | Price escalation & Increase in land cost
14 | ECoR | NL | Kodingamali Bauxite Mines to Singaram Railway Station | 2022-23 | 2022 | 9 | 2026-03-27 | 2026-03-27 | Nil | Nil | No Delay | [5 empty] | ND | 190.9 | 190.9 | 0 | No Cost over run
16 | ECoR | NL | Gandhmardan Iron Ore Mines to Goaldih Station | 2022-23 | 2022 | 13 | 2024 | 2026-06-28 | 4 year | Delay in land acquisition and Public agitation | Land Acquisition |  | LA |  |  |  |  | 189.93 | 189.93 | 0 | NA | Change in Scope of Work based on Actual Field requirement | The DPR was sanctioned in the year of 2022 with a completion period of 02 years. Subsequently on demand of the local people and asper instruction of State Govt. the alignment was modified and a fresh DPR is under preparation.
19 | ECoR | NL | New line between Puri and Konark © | 2023-24 | 2024 | 32.02 | 2026-12-26 | 2026-12-29 | 3 years | Delay in land acquisition | Land Acquisition |  | LA |  |  |  |  | 492.12 | 1038.27 | 546.15 | Price escalation & Increase in land value | Change in Scope of Work based on Actual Field requirement | As there is delay in land acquisition and the rate references of 2021 were taken while preparation of estimate
31 | ECoR | DL | 3rd line between Nergundi - Barang & Khurda Road - Vizianagaram | 2023-24 | 2023 | 385 | 2028 | Sept 29 | 1 year | Delay in land acquisition | Land Acquisition |  | LA |  |  |  |  | 4962.87 | 4962.87 | 0 | NA | Change in Scope of Work based on Actual Field requirement
32 | ECoR | DL | Baghuapal Fly over | 2019-20 | 2019 | 20 | 2026 | 2026-12-28 | 2 Year | Delay in land acquisition | Land Acquisition |  | LA |  |  |  |  | 151.42 | 257.97 | 106.55 | 1.Due to increase in land area and rate. 2.Due to increase in quantity in item like cutting,sand filling and new items like tunneling,blanketing, prepared sub-grade,retaining wall etc as per actual requirement and also increase P.way material cost and Major & Minor bridge quantity and rate. | Change in Scope of Work based on Actual Field requirement | This Project DE sanction year is 2022
84 | ECOR | DL | Doubling between Ore Exchange Complex and Simhachalam North | 2022-23 | 2023 | 5 | 07.03.2026 | 2026-08-28 | 29 months | Major modifications in existing yards of OEC, ELS and SCMN yards, Non finalisation of ESPs, change of major bridge GADs due to new sanction of multitracking of GPT Thadi line, Shifting of utilities (pipelines by GVMC), etc., | Utility Shifting |  |  |  |  | US |  | 81.22 | 135.82 | 54.6 | cost escalation, major changes in yards, etc. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material | revised estimate is being processed for approval
90 | ECoR | DL | Byepass line from Rahenbata in RV(Raipur-Vizianagram) line to Sikir in JT (Jharsuguda-Titlagarh) line byepassing Titlagarh (12.65 Km) | 2022-23 | 2023 | 13 | 2026-03-01 | 2026-12-28 | 2 years 9 months | Delay in land acquisition. | Land Acquisition |  | LA |  |  |  |  | 143.2 | 143.2 | 0 | NA |  | Work is in progress.
93 | ECoR | DL | 3rd & 4th line between Duvvada - Simhachalam North | 2023-24 | 2023 | 21 | 11.04.2026 | 2026-07-28 | 27 months | Delay in land acquisition, shifting of utilities (pipelines by GVMC/Irrigation authorities , Electric Poles & Transformer by APEPDCL, Non finalisation of ESPs, Shifting of Cables, etc., | Land Acquisition, Utility Shifting |  | LA |  |  | US |  | 302.25 | 452.13 | 149.88 | increase in cost for private land acquisition |  | revised estimate is being processed for approval
94 | ECoR | DL | 3rd & 4th line between Vadlapudi -Gate Jn. cabin including Tie line between Gangavaram Port- Visakhapatnam Steel (12.04 Km) | 2023-24 | 2023 | 12 | 11.04.2026 | 2026-12-27 | 8 months | Delay in giving land in steel plant, Limited working permissions inside Visakhapatnam Steel Plant, Taking passes for Private labour, Due to court case in finalisation of S&T tender, etc., | Land Acquisition |  | LA |  |  |  |  | 154.28 | 154.28 | 0 | NA
95 | ECoR | DL | Flyover between Pendurti & Simhachalam North to avoid surface crossing at Simhachalam | 2023-24 | 2023 | 7 | 11.04.2028 | 2026-06-28 | 2 months | Delay in land acquisition proceedings and working permission for endowment land for flyover works Non finalisation of ESPs, shifting of utilities (pipelines by GVMC, Electric Poles & Transformer by APEPDCL & APTransco, Shifting of Cables) | Land Acquisition |  | LA |  |  |  |  | 183.65 | 292.83 | 109.18 | increase in cost for endowment land |  | revised estimate is being processed for approval
98 | ECoR | DL | 3rd & 4th line of Sarla-Sason Patch of Sambalpur-Jharsuguda Section | 2023-24 | 2023 | 16 | 2026-12-25 | 2026-03-27 | 15 months | Dispute with forest department at Sarla yard | Forest & Wildlife Clearance | FC | [5 empty] | 252.18 | 252.18 | 0 | NA
99 | ECoR | DL | Flyover at Haridaspur to connect Haridaspur - Paradeep New BG Line | 2023-24 | 2023 | 5 | 2026 | 2026-06-28 | 3 year | Delay in Land acquistion | Land Acquisition |  | LA |  |  |  |  | 143.72 | 143.72 | 0 | 0 |  | Contract awarded
100 | ECoR | DL | Flyover Between Siju and Paradeep coaching yard to avoid surface crossing of trains | 2023-24 | 2023 | 7 | 2027 | 2026-12-28 | 1 year | Delay in Land acquistion | Land Acquisition |  | LA |  |  |  |  | 200.77 | 248.63 | 47.86 | Due to an increase in land area and updation of rates as per DSR-2023 and unit rates of 2026-27 for P-Way materials.
101 | ECoR | DL | 3rd & 4th Line between Visakhapatnam (VSKP) -Gopalapatnam (GPT) | 2023-24 | 2023 | 15 | 11.04.2026 | 2026-08-28 | 29 months | Delay in land acquisition (awaiting handover of land) shifting of utilities (pipelines by GVMC authorities , Electric Poles & Transformer by APEPDCL & APTRANSCO, Delay in finalisation of VSKP, GPT and Marripalem ESPs. Shifting of Cables . | Land Acquisition |  | LA |  |  |  |  | 159.47 | 231.76 | 72.29 | Increase in scope at Marripalem yard,
112 | ECoR | DL | 4th line between Kottavalasa - Vizianagram | 2023-24 | 2023 | 35 | 25.08.2026 | 2026-08-28 | 24 months | Delay in land acquisition proceedings and shifting of utilities(pipelines, Electric Poles & Transformer, Shifting of Cables) , Delay in finalisation of ESPs | Land Acquisition |  | LA |  |  |  |  | 492.93 | 536.8 | 43.87 | due to increase in cost of private land
115 | ECOR | DL | 3rd & 4th Line Paradeep - Badabandha | 2023-24 | 2023 | 19 | June'28 | 2026-06-28 | No delay |  | No Delay | [5 empty] | ND | 300.15 | 300.15 | 0 | - | No Cost overrun | Contract awarded
125 | ECoR | DL | Fly over from Sambalpur City end to connect the DN grid of Sarla to avoid surface crossing | 2023-24 | 2024 | 5 | March'2027 | 2026-12-28 | 21 months | Delay in land acquisition | Land Acquisition |  | LA |  |  |  |  | 272.64 | 272.64 | 0 | NA |  | Land acquisition in progress.
133 | ECOR | DL | MCRL Inner Corridor Phase-I Doubling | 2023-24 | 2024 | 11 | Mar'27 | 2026-02-27 | 2 Months | Delay in land acquisition | Land Acquisition |  | LA |  |  |  |  | 151.61 | 151.61 | 0 | NA |  | -
33 | ECR | DL | Permanent diversion of fire affected Dhanbad- Chandrapura line by Dhanbad- Ispatnagar line via Telulmari, Nichitpur, Matari, Telo including Y connection at Dhanbad and Ispatnagar | 2023-24 | 2023 | 28 | 2026-02-27 | 2026-02-27 |  | No delay | No Delay | [6 empty] | 526 | 478.37 | -47.63 | No Cost over run | No Cost overrun
34 | ECR | DL | Barauni- Bachwara 3rd & 4th line | 2022-23 | 2022 | 32 | 2025-04-01 | 2026-06-28 | 38 months | 1. Yard remodeling of TGA included in work 2. Major Yard remodeling at Barauni 3. Change in signalling system from Absolute to Automatic 4. Shifting of Utilities & Signal cable lying along the entire alignment hindering earthwork 5.Encroachment in land | Land Acquisition, Utility Shifting, Phase wise Sanctioning |  | LA | PS |  | US |  | 485.58 | 485.58 | 0 | NA | No Cost overrun
35 | ECR | DL | Sonenagar bye pass line from Chiralapothu to Bagha Bishunpur | 2022-23 | 2022 | 10 | Jun'27 | 2026-06-27 |  | No delay | No Delay | [6 empty] | 151 | 223.69 | 72.69 | No Cost over run | No Cost overrun
36 | ECR | DL | Doubling of Pradhan Kuntha Jn- Pathardih Bazar- Bhojudih | 2022-23 | 2022 | 20 | Dec'25 | 2026-12-26 | 12 months | Extension of FOB in PKA yard by DHN unit for construction of loop line . 83 nos. OHE mast to be removed. WIP in power block, 11+15+11+9=46 nos. removed. Balance WIP. Earth cutting work and Drain work at PKA yard stopped due to cable shifting work required. Br. no.90 cable shifting is required on UP line side. | Utility Shifting | [6 empty] | 202 | 349.22 | 147.22 |  | No Cost overrun
74 | ECR | DL | Surface Triangle Line between Bhadaura Station and Karma Station ( Dildarnagar-Tarighat Line) | 2022-23 | 2022 | 11 | Jul'27 | 2026-06-27 |  |  | No Delay | [8 empty] | 0 | No Cost over run
96 | ECR | DL | Doubling of Chandrapura - Jamuniatand section | 2023-24 | 2023 | 7 | Feb'26 | 2026-02-28 | 24 months |  | Land Acquisition | [6 empty] | 166.5 | 268 | 101.5
102 | ECR | DL | Rail over Rail (RoR) between Patratu-Tokisud | 2023-24 | 2023 | 7 | Mar'28 | 2026-03-28 |  |  | No Delay | [6 empty] | 137.46 | 137.46 | 0 | No Cost over run
103 | ECR | DL | ROR at Sasaram connecting GC to Ara-Sasaram Line | 2023-24 | 2023 | 9 | 2026-03-28 | 2026-03-28 |  |  | No Delay | [6 empty] | 470.11 | 470.11 | 0 | No Cost over run
104 | ECR | DL | Ara Byepass Line to be connected from Jagjivan Halt to existing ARA-Sasaram line through link cabin (Y-Connectivity at Ara) | 2023-24 | 2023 | 3 | Feb'26 | 2026-03-28 | 25 months | Total land required is 10.88 acre.: Paper possession given on 15.01.2025 but when Railway started the work, public agitation started, and work was stopped. Now, the work has been started. Gazette notification of 10.88 acre land 37A published on 11.07.2023. 7A published on 07.10.2023. Land Acquisition Plan (LAP) submitted on 31.08.2023. 20A published 30.11.2023. 20E published on 06.04.2024. 17.37 Cr. Paid for land on 23.08.2024, 3.03 Cr. for structures paid on 06.12.2024. Land dispute at Jagjeevan Halt: The land which was railway land as per the Cadastral Map of 1874 has been shown as Private Land in the survey of 1907. Railway has no record of relinquishment of the land. Due to public agitation, State Govt. has asked for fresh acquisition of the land. Now records are being traced from Eastern Railways to establish Railways’ ownership of the land. Last letter given for discussion of the said issue with CS Bihar on 18.08.2025. Land ownership details of Kalyanpur and Chowrae village received on 10.09.25 which is in Kaithi language which has been give to agency for translation in hindi language. Translation in hindi done. Letter given to DM/ARA on 13.09.25 for assistance in resuming the work. Reply received on 18.10.25 in which DM/ARA mentioned that revisional survey of 1970 is final and based on that Railway can work in their land. Meeting with secretary/Revenue and Land acquisition on 21.11.25 and he is telling that Railway has to acquire land for the work. Letter given to DM/ARA on 27.12.25 for documents based on which Railway land has been shown as Raiyat land in CS/RS map. Reply received on 05.03.26 and DM/ARA is telling to file civil suit to Railways for jamabandi cancellation. Details of additional land of 4.087 acre near udwant nagar link has been sent to DLAO for verification on 29.11.24. Proposal returned by DLAO for correction on 25.01.26 as railway track marked in proposed land acquisition plan based on earlier approved land acquisition plan is not matching at site. Joint verification of land near udwant nagar completed with State Govt and division. Revised L section has been prepared in which no land acquisition is required. Work for retaining wall in progress. Critical Issue: Land dispute near Jagjivan station. Overall Target Date of Commissioning: 30.11.2026 | Land Acquisition, Law and Order Issue |  | LA |  | LO |  |  | 118.94 | 118.94 | 0
111 | ECR | DL | Multi tracking of Son Nagar – Andal | 2023-24 | 2023 | 745 | 2026-03-29 | 2026-03-29 |  | Work in progress | No Delay | [5 empty] | ND | 12333.57 | 12333.57 | 0 | No Cost over run
119 | ECR | DL | Y connection between Kujju-Ranchi Road Station | 2023-24 | 2023 | 7 | Dec'25 | 2026-03-27 |  | Delay in land acquisition | Land Acquisition |  | LA |  |  |  |  | 143.01 | 143.01 | 0
37 | ER | DL | Madhupur bye-pass line | 2023-24 | 2023 | 8 | 2026-03-25 | 2026-12-27 | 2 Yrs 9 months | Delay in land acquisition | Land Acquisition |  | LA |  |  |  |  | 140 | 140 | 0
135 | ER | DL | Durgapur Coke Oven Plant (DCOP)-Durgapur 5th Line | 2023-24 | 2024 | 4 | 2026-02-26 | 2026-12-27 | 10 months | Dismantling of existing arch type utility bridge (Br No 396A) by Asansol division | Utility Shifting |  |  |  |  | US |  | 79 | 79 | 0
38 | NCR | DL | Mughalsarai-Allahabad, 3rd line | 2019-20 | 2019 | 150 | 2026-12-26 | 2026-03-28 | 15 Months | Additional land acquition required for construction of boundary wall throughout the length of project on 3rd line side as the section is envisaged for speed of 160 KMPH | Land Acquisition |  | LA |  |  |  |  | 2390 | 2649.44 | 259.44 | Due to price escalation as there was almost 4 year difference from project appeared in Pink Book to detailed estimate sanction | Market Inflation increase in cost of raw material
39 | NCR | DL | Aligarh Flyover | 2020-21 | 2020 | 22 |  | 2026-03-28 | 1 year | Delay in land acquisition | Land Acquisition |  | LA |  |  |  |  | 1179.27 | 1187.14 | 7.87 | Land acquisition |  | Delay in land acquisition
40 | NCR | DL | Agra Fort and Bandikui | 2022-23 | 2022 | 150 | 2026-07-27 | 2026-07-27 | Nil | Nil | No Delay | [5 empty] | ND | 987.87 | 987.83 | -0.04 | No Cost over run
41 | NCR | DL | Aligarh - Daud Khan 3rd line & construciton of flyover at Daud khan | 2019-20 | 2019 | 18 |  | 2026-12-27 | 1 year | Delay in land acquisition | Land Acquisition |  | LA |  |  |  |  | 447.99 | 779.49 | 331.5 | Cost of land was not taken in PB cost |  | Delay in land acquisition
42 | NCR | DL | Allahabad - Bumrauli 4th line (10 Km) with flying over atSubedarganj | 2019-20 | 2020 | 10 | Feb'25 | 2026-12-27 | 34 Months | Delay due to elevated track and crossing over Delhi-Howarah running lines. Hinderance due to movement restrictions during Kumbh, annual Magh Mela. | Phase wise Sanctioning |  |  | PS |  |  |  | 493.11 | 493.11 | 0 | NA
43 | NCR | DL | Bhandai - Flyover for etawah bound down train (10 Km) | 2019-20 | 2019-20 | 10 | Mar'26 | 2026-12-27 | 21 Months | Land acquisition | Land Acquisition |  | LA |  |  |  |  | 186.21 | 250.18 | 63.97 | Original Sanctioned Cost of Detail Estimate:- Rs. 250.18 Cr, Anticipated Cost:- Rs. 250.18 Cr, Cost Overrun w.r.t. Detail Estimated Cost is Nil.
44 | NCR | DL | Doubling of Billi- Chunar | 2023-24 | 2023 | 102 | 2026-03-28 | 2026-03-28 | Nil | NA | No Delay | [5 empty] | ND | 1423.96 | 1423.96 | 0 | No Cost over run
79 | NCR | DL | 4th line between Pankidham-GMC | 2022-23 | 2022 | 2 | 2026-10-27 | 2026-10-27 |  | Work has been commissioned on 27.10.2026. Delay occurred due to shifting of IOCL boundary required which was in alignment of proposed line. Shifting was done in Apr' 2025. Only after shifting of boundary, work could be started. Also, other sanctioned works at Panki Dham included in NI work which delayed execution of this work. | Utility Shifting | [6 empty] | 17 | 17 | 0 | NA
3 | NER | NL | Anandnagar-Ghugli | 2023-24 | 2023 | 53 | 2026-08-28 | 2026-08-28 |  |  | Forest & Wildlife Clearance, Land Acquisition | [8 empty] | 0
4 | NER | NL | Sahjanwa-Dohrighat | 2019-20 | 2019 | 81 | 2026-12-28 | 2026-12-28 |  |  | Land Acquisition | [6 empty] | 371 | 1319 | 948
5 | NER | NL | Etah-Kasganj | 2023-24 | 2024 | 29 | 2026-10-28 | 2026-10-28 |  |  | Land Acquisition | [6 empty] | 276 | 389 | 113
45 | NER | DL | Doubling of Gorakhpur- Valmikinagar | 2023-24 | 2023 | 96 | 2026-12-27 | 2026-12-27 |  | Valmikinagar Wildlife sanctuary | Forest & Wildlife Clearance | [6 empty] | 1092 | 1120 | 28
6 | NFR | NL | Construction of Mahisasan (India) - Zero Point (Bangladesh) New Line (2.7 km) | 2020-21 | 2020 | 3 |  | - |  | Working peremission in Bangladesh | Land Acquisition | [6 empty] | 38 | 49 | 11
46 | NFR | DL | Doubling of Agthori-Kamakhya section with construction of new Rail-cum-Raod Bridge at Saraighat | 2023-24 | 2024 | 7 |  | 2026-08-31 |  | Heavy encroachments in approach of Bridge | Law and Order Issue | [6 empty] | 889 | 1473 | 584
47 | NFR | DL | 3rd Line between Kamakhya - Guwahati | 2023-24 | 2023 | 6 | 2026-03-28 | 2026-03-28 |  | Removal of Encroachments along the alignment | Law and Order Issue | [6 empty] | 394.64 | 467.24 | 72.6 | In the original sanctioned estimate, the cost of Electrical (G) was not included, it has now been included in 1st RE. Cost of Electrical (TRD) and S&T has also been increased in the 1st RE. | Change in Scope of Work based on Actual Field requirement | The project was sanctioned by Railway Board on 27.04.2023. The tender for EPC work has been finalised with appointed date as 10.03.2026.
48 | NFR | DL | Doubling of Lumding-Furkating section | 2023-24 | 2024 | 140 | 2026-12-28 | 2026-12-28 |  |  | No Delay | [6 empty] | 4620 | 2123 | -2497 | No Cost over run
49 | NFR | DL | Doubling of Katihar- Kumedpur and Katihar- Mukuria | 2022-23 | 2022 | 65 | 2026-08-27 | 2026-05-27 | NIL | Mining permission delayed earthwork | Law and Order Issue | [6 empty] | 942 | 2141 | 1199 | The 1st RE has been prepared for a gross cost of ₹2,141.82 Cr against the sanctioned DE of ₹942.64 Cr, an increase of ₹1,199.17 Cr (127.21%). Of this, ₹635.29 Cr is due to Price Escalation and ₹563.88 Cr is due to other than price escalation. The resaons for cost overrun are given as below: 1. PH-1520 (Land): Land rates are as per Bihar Government guidelines, taking the lower of the MVR rate and the 3-year average sale rate, mouza-wise. Additional land of 4.78 acres is required due to change in alignment at certain locations and new cut-and-connections provided for elimination of reverse curves. 2. PH-1530 (Formation): The DE assumed a 5.3 m track centre throughout the section irrespective of the location of bridges, station yards, etc. As per the approved L-sections, the track centre varies from 5.3 m to 65.0 m at bridge approaches & bridge locations, 5.3 m to 7.2 m in station yards and up to 12.2 m in block sections; therefore, earthwork in filling has increased from 26.70 lakh cum to 49.36 lakh cum. Quantities of blanketing, retaining and toe walls, dry stone pitching and drains have also increased accordingly. 3. PH-1541/1542 (Rails & Sleepers): Track length has increased from 79.77 km to 97.48 km. Under IRPWM Paras 205(2) and 209(2a), new 60 kg R260 rails with 1,660 sleepers/km have been provided in passenger loop lines in place of second-hand 52 kg rails. Accordingly, rail quantity has increased by 2,143 MT and sleepers by 30,082 nos. 4. PH-1550 (Bridges): After approval of the GADs and detailed hydrological and geotechnical studies, the type, span and foundation of a number of bridges have been revised. These include steel-to-PSC conversions, double-line combined foundations (Br. No. 7, 8 & 20 & 21) and new minor bridges (6B, 11A, 11C), resulting in increased structural quantities. 5. PH-1560 (Buildings & Station works): The DE had no provision for staff quarters (Type II/III: 62/14, approved by AGM/NFR), pump houses, tube wells, OHTs, cabins, auto huts, trolley garages and fencing. Platform area, PP shelters, approach roads and other passenger amenities have also increased as per the approved station plans. 6. Rate revision: The DE was based on USSOR-2010/LAR, whereas RE-1 is based on USSOR-2021/LAR and DSOR-2021/LAR. There is no change in the overall scope or objective of the sanctioned work. | Change in Scope of Work based on Actual Field requirement, Market Inflation increase in cost of raw material, Escalation in Land Acquisition value | This Project DE sanction year is Aug'2022. The 1st RE has been vetted by associate finance and under process for submission to Railway Board. Sections Katihar-Sonaili (16.215 Km) and Katihar-Kuretha (11.06 km) (Total=27.275 Km) comissioned on date 19.06.2026. Balance sections work is in progress.
50 | NR | DL | Ludhiana-Mullanpur | 2020-21 | 2021 | 21 |  | 2026-02-27 |  | NI of Busy Ludhiana Yard | Phase wise Sanctioning | [6 empty] | 82 | 288 | 206
76 | NR | DL | Chipyana-Buzurg(CYZ)-Ghaziabad(GZB) | 2022-23 | 2023 | 3 | 30.06.2025 | 2026-01-27 | 19 month | To be commssioned with EI of GZB | Phase wise Sanctioning |  |  | PS |  |  |  | 34.28 | 34.28 | 0 | NA | No Cost overrun
91 | NR | DL | Doubling between Jaunpur Jn.-Zafarabad (6.28 Km) | 2022-23 | 2023 | 6 | 2026-12-28 | 2026-12-28 |  |  | No Delay | [6 empty] | 177 | 237 | 60 | No Cost over run
116 | NR | DL | Construction of 3" line between Varanasi Shivpur | 2023-24 | 2023 | 6 | 2026-03-28 | 2026-03-28 |  | Heavy built up Varanasi area | Utility Shifting | [6 empty] | 76 | 76 | 0
126 | NR | DL | Chord line connecting Muftiganj (MFJ) - Jaunpur (JNU)- MGWN bypassing Jaunpur (1.5 Km) | 2023-24 | 2024 | 2 | 2026-01-27 | 2026-01-27 |  |  | No Delay | [6 empty] | 75 | 75 | 0 | No Cost over run
127 | NR | DL | Chord line connecting Didarganj (DJD) - Shahganj (SHG)- Bilwai (BWI) bypassing Shahganj | 2023-24 | 2024 | 6 | 2026-10-27 | 2026-10-27 |  |  | No Delay | [6 empty] | 137 | 137 | 0 | No Cost over run
134 | NR | DL | Byepass line at Ayodhya | 2023-24 | 2024 | 2 |  | - |  | Stiff resistance in land acquisition | Law and Order Issue, Land Acquisition | [6 empty] | 173 | 173 | 0
136 | NR | DL | Chord line between Alal-Himmatana | 2023-24 | 2024 | 13 | 2026-12-28 | 2026-12-28 | - | - | No Delay | [6 empty] | 173.58 | 173.58 | 0 | No Cost over run | No Cost overrun | Land acquisition in progress.
7 | NWR | NL | Pushkar-Merta (Katyasani) | 2023-24 | 2024 | 51 | 2026-12-28 | 2026-12-28 |  |  | No Delay | [6 empty] | 323 | 799 | 476 | No Cost over run | No Cost overrun
8 | NWR | NL | Taranga Hill-Abu Road via Ambaji | 2022-23 | 2022 | 116 | 2026-03-29 | 2026-03-29 |  |  | No Delay | [6 empty] | 1696 | 3300 | 1604 | No Cost over run
9 | NWR | NL | Gudha-Thathana Mithri Test Track for RDSO | 2019-20 | 2020 | 25 | 2026-11-26 | 2026-11-26 |  |  | No Delay | [6 empty] | 528 | 540 | 12 | No Cost over run
10 | NWR | NL | Dedicated Test Track for RDSO (Phase-II) | 2021-22 | 2022 | 34 | 2026-11-26 | 2026-11-26 |  |  | No Delay | [6 empty] | 466 | 619 | 153 | No Cost over run
20 | NWR | NL | New BG line between Merta City-Ras (51.40 Km) & Byepass at Merta road station (4.50 Km) | 2023-24 | 2024 | 56 | 2026-03-30 | 2026-03-30 |  |  | No Delay | [6 empty] | 947 | 947 | 0 | No Cost over run
51 | NWR | DL | Sawaimadhopur-Jaipur | 2023-24 | 2024 | 130 | 2026-05-28 | 2026-05-28 |  |  | No Delay | [6 empty] | 1192 | 1203 | 11 | No Cost over run
52 | NWR | DL | Doubling between Churu-Sadulpur BG Line Doubling between Luni-Samdari-Bhildi section | 2023-24 | 2024 | 330 | Feb 29 | Feb 29 |  |  | No Delay | [8 empty] | 0 | No Cost over run
53 | NWR | DL | Doubling between Ajmer-Chanderiya section | 2023-24 | 2024 | 178 | 2026-10-28 | 2026-10-28 |  |  | No Delay | [6 empty] | 2420 | 1634 | -786 | No Cost over run
54 | NWR | DL | Byepass line at Sawaimadhopur | 2022-23 | 2022 | 14 | 2026-12-26 | 2026-12-26 |  |  | No Delay | [6 empty] | 304 | 239 | -65 | No Cost over run
81 | NWR | DL | Rewari-Khatuwas Doubling | 2022-23 | 2023 | 28 | 2026-12-26 | 2026-12-26 |  |  | No Delay | [6 empty] | 352 | 352 | 0 | No Cost over run
83 | NWR | DL | Bhiwani-Dobh-Bahali Doubling (42.30 Km) | 2022-23 | 2023 | 42 | Sept 27 | Sept 27 |  |  | No Delay | [6 empty] | 471 | 471 | 0 | No Cost over run
92 | NWR | DL | Doubling between Manheru-Bawani Khera | 2023-24 | 2023 | 32 | 2026-10-28 | 2026-10-28 |  |  | No Delay | [6 empty] | 413 | 413 | 0 | No Cost over run
55 | SCR | DL | Doubling of Guntur- Bibinagar | 2023-24 | 2023 | 235 | 2026-08-28 | 2026-06-28 | 2 months |  | No Delay | [6 empty] | 2853.23 | 2853.23 | 0 | No Cost over run
56 | SCR | DL | Doubling between Mudkhed - Medchal & Mahbubnagar - Dhone section as a Part of Doubling of Akola- Dhone via Purna, Mudhkhed, Secunderabad, Mehboobnagar excluding Purna-Mudkhed and Bolarum-Mehboobnagar including Dhone bye pass | 2023-24 | 2023 | 417 | 2026-08-29 | 2026-08-29 | 0 |  | No Delay | [6 empty] | 4689.09 | 4689.09 | 0 | No Cost over run |  | Work is in Progress
82 | SCR | DL | Multi Tracking & connectivity at Guntur Yard for 8.20 Km | 2022-23 | 2023 | 8 |  | 2026-12-26 |  |  | No Delay | [6 empty] | 125.16 | 125.16 | 0 | No Cost over run
85 | SCR | DL | Bye pass line at Latur Road Station | 2022-23 | 2023 | 4 | 2026-03-27 | 2026-02-27 | 0 | No delay, work is in progress. | No Delay | [5 empty] | ND | 46.95 | 46.95 | 0 | NA | No Cost overrun | Work is in Progress
88 | SCR | DL | Byepass line at Parli-Vaijanath Station (1.90 Km) | 2022-23 | 2023 | 2 | 2026-03-27 | 2026-12-27 | 9 months | Delay in Land aquisition. Shifting of HT (220 KV) Power line crossings at 3 locations, for which MAHATRANSO has to submit the estimate to call tender. | Land Acquisition, Utility Shifting |  | LA |  |  | US |  | 55.91 | 55.91 | 0 | NA | No Cost overrun | Work is in Progress
89 | SCR | DL | Doubling between Gooty-Pendekallu (29.225 Km) | 2022-23 | 2023 | 29 | 2026-03-26 | 2026-02-27 | 12 months | [8 empty] | 351.83 | 351.83 | 0
97 | SCR | DL | Byepass Line at Vikarabad Station for connecting Vikarabad-Parli Vaijanath & Secunderabad -Wadi section | 2023-24 | 2023 | 3 | 2026-12-27 | 2026-02-28 | 03 months | Due to delay in Land aquisition. PN issued, PD and land award are yet to be issued.Tender will be called after Land Acquisition. | Land Acquisition |  | LA |  |  |  |  | 46.37 | 46.37 | 0 | NA | No Cost overrun | Land acquisition in progress.
105 | SCR | DL | Doubling between Aurangabad - Ankai | 2023-24 | 2023 | 98 | 2026-05-27 | 2026-03-29 | 24 months | Due to delay in Land Acquisition. | Land Acquisition |  | LA |  |  |  |  | 960.64 | 960.64 | 0 |  | No Cost overrun | Work is in Progress
106 | SCR | DL | Bye pass line at Vishnupuram | 2023-24 | 2023 | 5 | 2026-12-26 | 2026-03-28 | 24 months | Due to delay in Land Acquisition. | Land Acquisition |  | LA |  |  |  |  | 110.89 | 110.89 | 0
109 | SCR | DL | Rail Over Rail (ROR) double line between Guntakal West - Mallappa Gate | 2023-24 | 2023 | 10 | 2026-07-26 | Sept 27 | 14 months | [8 empty] | 293.3 | 293.3 | 0
113 | SCR | DL | Doubling between Bhadrachalam Road - Dornakal section | 2023-24 | 2023 | 55 | 2026-08-27 | 2026-04-29 | 24 months | [8 empty] | 770.12 | 770.12 | 0
118 | SCR | DL | Byepass line at Mudkhed junction (2.527 Km) | 2023-24 | 2023 | 3 | 2026-03-24 | 2026-02-27 | 36 months | Due to delay in Land Acquisition. | Land Acquisition |  | LA |  |  |  |  | 62.22 | 62.22 | 0 |  | No Cost overrun | Work is in Progress
120 | SCR | DL | Byepass line at Purna (3.22 Km) for connecting Purna- Akola & Purna-Secunderabad Main Lines | 2023-24 | 2023 | 3 | 2026-02-26 | 2026-03-28 | 24 months | [8 empty] | 72.34 | 72.34 | 0
121 | SCR | DL | Byepass line at Ankai (2.21 Km) | 2023-24 | 2023 | 2 | 2026-03-24 | 2026-12-27 | 36 months | Due to delay in Land Acquisition. | Land Acquisition |  | LA |  |  |  |  | 28.89 | 28.89 | 0 |  | No Cost overrun | Work is in Progress
122 | SCR | DL | Doubling between Parbhani- Parli Vaijanath stations (64.71 Km) | 2023-24 | 2023 | 65 | 2026-12-26 | 2026-11-28 | 24 months | Due to delay in Land Acquisition. | Land Acquisition |  | LA |  |  |  |  | 769.93 | 769.93 | 0 |  | No Cost overrun | Work is in Progress
123 | SCR | DL | Rail Over Rail (ROR) at Pagidipalli connecting Bibi Nagar and Bommaipalli stations | 2023-24 | 2024 | 9 | 2026-01-27 | 2026-12-27 | 11 months | Due to delay in Land aquisition. PN issued | Land Acquisition |  | LA |  |  |  |  | 263.89 | 263.89 | 0
128 | SCR | DL | Doubling between Motumari-Vishnupuram section (88.81Km) & Rail over Rail (RoR) at Motumari (10.88 Km) | 2023-24 | 2024 | 100 | 2026-02-28 | 2026-03-29 | 13 months | Due to delay in Land Acquisition. | Land Acquisition |  | LA |  |  |  |  | 1595.55 | 1595.55 | 0
129 | SCR | DL | Byepass line between Guntakal-Nancherla stations | 2023-24 | 2024 | 11 | 2026-03-27 | 2026-02-27 | 1 month |  | No Delay | [6 empty] | 164.58 | 164.58 | 0
131 | SCR | DL | Bypass line at Nizamabad Junction Station for connecting Nizamabad-Secunderabad & Nizamabad-Pedapalli | 2023-24 | 2024 | 2 | 2026-02-26 | 2026-12-27 | 10 months | Due to delay in Land Acquisition. | Land Acquisition |  | LA |  |  |  |  | 121.97 | 121.97 | 0 |  | No Cost overrun | Work is in Progress
57 | SECR | DL | Doubling of Boridand- Ambikapur (Surajpur) | 2022-23 | 2022 | 80 | 2026-06-28 | 2026-06-28 | 0 |  | No Delay | [6 empty] | 1376 | 1576 | 200 | No Cost over run
66 | SECR | DL | Saragbundia and Madvarani | 2022-23 | 2022 | 6 | 2026-04-27 | 2026-04-27 | 0 |  | No Delay | [6 empty] | 167 | 167 | 0 | No Cost over run
67 | SECR | DL | Rajnand Gaon - Dongargarh 4th Line | 2022-23 | 2022 | 31 | 2026-03-27 | 2026-03-27 | 0 |  | No Delay | [6 empty] | 328 | 328 | 0 | No Cost over run
68 | SECR | DL | Dadhapara-Belha 4th Line | 2022-23 | 2022 | 9 | 2026-01-27 | 2026-01-27 | 0 |  | No Delay | [6 empty] | 169 | 169 | 0 | No Cost over run
69 | SECR | DL | Kharsia-Jharadih | 2022-23 | 2022 | 6 | 2026-12-26 | 2026-12-26 | 0 |  | No Delay | [6 empty] | 80 | 80 | 0 | No Cost over run
70 | SECR | DL | Kargi road-Salka road | 2022-23 | 2022 | 8 | 2026-12-26 | 2026-12-26 | 0 |  | No Delay | [6 empty] | 95 | 101 | 6 | No Cost over run
71 | SECR | DL | Bhilai- Bhilai Nagar 4th Line | 2022-23 | 2022 | 9 | 2026-05-27 | 2026-05-27 | 0 |  | No Delay | [6 empty] | 177 | 177 | 0 | No Cost over run
72 | SECR | DL | Bhatapara- Hathbandh 4th Line | 2022-23 | 2022 | 16 | 2026-03-27 | 2026-03-27 | 0 |  | No Delay | [6 empty] | 177 | 177 | 0 | No Cost over run
73 | SECR | DL | Shahdol-Singhpur | 2022-23 | 2022 | 6 | 2026-12-26 | 2026-12-26 | 0 |  | No Delay | [6 empty] | 1739 | 4312 | 2573 | No Cost over run
75 | SECR | DL | Belha-Dagori 4th Line | 2022-23 | 2022 | 7 | 2026-12-27 | 2026-12-27 | 0 |  | No Delay | [6 empty] | 86 | 86 | 0 | No Cost over run
77 | SECR | DL | 4th line between Bhilai Nagar-Durg Link Cabin | 2022-23 | 2022 | 3 | 2026-03-27 | 2026-03-27 | 0 |  | No Delay | [6 empty] | 55 | 55 | 0 | No Cost over run
78 | SECR | DL | 4th line between Nipania-Bhatapara | 2022-23 | 2022 | 14 | 2026-03-27 | 2026-03-27 | 0 |  | No Delay | [6 empty] | 170 | 170 | 0 | No Cost over run
58 | SER | DL | Lodhma - Piska - Link Line bypassing Hatia/Ranchi with Y connection | 2019-20 | 2021 | 17 | Jun'28 | 2026-06-28 | - | - | No Delay | [6 empty] | 472.5 | 472.5 | 0 | No Cost over run | No Cost overrun
59 | SER | DL | Doubling between Bhojudi- Talgoria in connection with permanent diversion of fire affected Dhanbad- Chandrapura line | 2021-22 | 2021 | 13 | Mar'27 | 2026-03-27 | - | - | No Delay | [6 empty] | 142.06 | 142.06 | 0 | No Cost over run | No Cost overrun
60 | SER | DL | Rourkela-Bondamunda A Cabin 5th line | 2022-23 | 2022 | 10 | Feb'26 | 2026-12-26 | 10 months | Due to Major yard remodelling at Bondamunda. | Phase wise Sanctioning | [6 empty] | 244.99 | 244.99 | 0 |  | No Cost overrun
114 | SER | DL | 3rd & 4th line between Bokaro Steel City and Bokaro 'N' cabin | 2023-24 | 2023 | 4 | Jun'27 | 2026-06-27 | No delay | No delay | No Delay | [5 empty] | ND | 75.45 | 100.2 | 24.75 | As per present site requirement.
117 | SER | DL | 4th line between Bagdehi-Jharsuguda (21.50 Km) | 2023-24 | 2023 | 22 | Jan'27 | 2026-01-27 | No delay | No delay | No Delay | [5 empty] | ND | 320.95 | 320.95 | 0 | No Cost over run | No Cost overrun
132 | SER | DL | Illoo-Silli Bypass line avoiding Muri Jn. | 2023-24 | 2024 | 6 | Mar'28 | 2026-03-28 | No delay | No delay | No Delay | [5 empty] | ND | 137.23 | 137.23 | 0 | No Cost over run | No Cost overrun
130 | SR | DL | Patch doubling of tarck between Shoranur and Vallathol Nagar including yard modifications. | 2023-24 | 2024 | 10 |  | 2026-12-29 |  | Delay in Land acquisition. LA proposals submitted in 2024. SIA study completed and 11(1) Notification is issued. Valuation is in progress. Work in progess where land is available. | Land Acquisition |  | LA |  |  |  |  | 367 | 367 | 0
11 | SWR | NL | Shimoga-Shikaripura-Ranebennur© | 2 019-20 | 2019 | 96 | 2026-12-27 | 2026-01-30 | 2 years | Delay in land acqusition - Land acqusition proposals submitted on 2019. However land for Shimoga -Shikaripur (40 Km) only handed over in stretches in the year 2023 & 2024 in stages. Accordingly, work is in progress for the section. However, land to the tune of 545.32 A out of 669.9 A is yet to be handed over in Shikaripura - Ranebennur (56 Km) . Hence delay in execution | Land Acquisition |  | LA |  |  |  |  | 956 | 994.47 | 38.47 | Rs994.47 is detailed estimate cost based on the FLS conducted whic is as per actaul requirement.
12 | SWR | NL | Hassan-Belur© | 2019-20 | 2022 | 32 | Not fixed as land was not handed over | Feb 30 | - | Delay in land acquisition – The land acquisition proposals were submitted in 2022, and the same is yet to be handed over. | Land Acquisition |  | LA |  |  |  |  | 462.93 | 748.84 | 285.91 | Rs.748.84 Cr is detailed estimate cost based on the FLS conducted whic is as per actaul requirement.
13 | SWR | NL | Dharwad to Belgaum via Kittur © | 2020-21 | 2020 | 73 | Not fixed as land was not handed over | 2026-12-27 | - | Delay in land acquisition – The proposals were submitted in 2022 however, land acquisition has yet to be initiated by the GoK. | Land Acquisition |  | LA |  |  |  |  | 988 | 927.42 | -60.58 | Rs 927.42is detailed estimate cost based on the FLS conducted whic is as per actaul requirement.
15 | SWR | NL | Malugur - Palasamudram | 2022-23 | 2022 | 18 | 2026-03-24 | 2026-05-28 | 4 years | Forest land is yet to be handed over | Forest & Wildlife Clearance | FC | [5 empty] | 323.14 | 342.14 | 19 | land cost increased and Hence land sub estimate sanctioned
61 | SWR | DL | Baiyapannahalli to Hosur © | 2019-20 | 2018 | 48 |  | 2026-06-27 |  | Resistance during Land Acquisition in built up area | Land Acquisition | [6 empty] | 375 | 498.73 | 123.73
62 | SWR | DL | Yeshwantpur to Channasandra © | 2019-20 | 2018 | 25 |  | 2026-12-27 |  | Resistance during Land Acquisition in built up area | Land Acquisition | [6 empty] | 169 | 314.11 | 145.11
63 | WCR | DL | Ruthiyai-Bye Pass line | 2019-20 | 2020 | 3 | 2026-03-27 | 2026-12-26 | 06 months | Land acquisition completed in June 2026.Land acquisition delayed by 6 months. | Land Acquisition |  | LA |  |  |  |  | 49.44 | 77.2 | 27.76 | Land cost increased and additional scope as per site condition. Revised estimate sanctioned. | Escalation in Land Acquisition value, Change in Scope of Work based on Actual Field requirement | Work is in progress (10%)
64 | WCR | DL | Guna- Bye Pass line | 2019-20 | 2020 | 2 | 2026-03-27 | - | 12 months | Land acquisition completed in Oct 2026.Land acquisition delayed by 10 months. Major bridge is to be built for crossing existing 6 nos. GAIL pipe lines. | Land Acquisition |  | LA |  |  |  |  | 51.71 | 81.57 | 29.86 | Land cost increased and additional scope as per site condition. Revised estimate sanctioned. | Escalation in Land Acquisition value, Change in Scope of Work based on Actual Field requirement | Work is in progress (35%)
17 | WR | NL | Geratpur-Sanand and Botad-Ahmedabad | 2022-23 | 2022 | 17 | Sept-27 | 2026-07-28 | 10 Months | There is heavy resistance for land acquisition from stakeholders. Land acquisition is major problem since project is located just outside Ahmedabad city and town planning scheme is rapidly spreading. | Land Acquisition |  | LA |  |  |  |  | 437.21 | 1067.4524 | 630.2424 | Increase in cost for private land acquisition. Revised estimate already sent to Rly bd for sanction. |  | Intersection No. 5 (0.9 Km) commissioned. work is in progress.
18 | WR | NL | New BG Line between Naliya-Jakhau Port | 2022-23 | 2023 | 25 | 2026-02-27 | 2026-02-28 | 12 Month | Due to review of goods traffic at Jakhau Port by Operating department, alignment beyond Jakhau village is being revised. | Phase wise Sanctioning |  |  | PS |  |  |  | 410.46 | 410.46 | 0 | Nil | No Cost overrun | work is in progress between Naliya to Jakhau village.
22 | WR | GC | Khijadiya-Amreli MG | 2023-24 | 2023 | 17 | 2026-10-25 | 2026-12-26 | 1 Year 2 Months | 03 Nos Temple at Amreli YARD coming in the alignment of MG Track and BG Loop Line No.3 LHS in lieu of LC 16 :- Approach balance due to land issues raised by adjoining land owners. LHS in lieu of LC-18:- Pipe Line shifting by State Govt is balance on approaches and land owners issues on approaches. | Land Acquisition, Utility Shifting |  | LA |  |  | US |  | 178.07 | 198.07 | 20 | Extra underpasses and pedestrain subways demanded by locals and state Govt. | Extra underpasses and pedestrain subways demanded by locals and state Govt. | Commissioned on 27.10.2026
23 | WR | GC | Samni-Jambusar MG | 2022-23 | 2022 | 24 | May'24 | 2026-06-27 | 3 years 2 months | Overall Delay is due to delay in earthwork royalty permissions, existing Canal dismantling permission and MoRTH's approval for GAD of RUB at LC 28. | Land Acquisition |  | LA |  |  |  |  | 349.93 | 349.93 | 0 | Not Applicable |  | work is in progress.
24 | WR | GC | Samlaya-Timba Rd NG | 2022-23 | 2023 | 49 | Feb.'26 | 2026-06-27 | 1 years 4 months | Due to delay in land acquisition. | Land Acquisition |  | LA |  |  |  |  | 670.17 | 670.17 | 0 | Not Applicable |  | work is in progress.
25 | WR | GC | Nadiad-Petlad NG | 2022-23 | 2022 | 37 | May'26 | 2026-06-27 | 1 years 2 months | Initially, Land acquisition and forest tree cutting clearance. Currently, NIL | Land Acquisition, Forest & Wildlife Clearance | FC | LA |  |  |  |  | 461.91 | 461.91 | 0 | Not Applicable | Not Applicable | Social forestry tree cutting permission from the forest department was delayed. Currently, trees cut . EPC tender awarded. Work is in progress.
26 | WR | GC | Petlad-Bhadran NG | 2022-23 | 2022 | 23 | May'26 | 2026-06-27 | 1 years 2 months | Initially, Land acquisition and forest tree cutting clearance. Currently, NIL | Land Acquisition, Forest & Wildlife Clearance | FC | LA |  |  |  |  | 307.1161 | 307.1161 | 0 | Not Applicable | Not Applicable | Social forestry tree cutting permission from the forest department was delayed. Currently, trees cut . EPC tender awarded. Work is in progress.
27 | WR | GC | Choranda - Motikoral NG | 2023-24 | 2023 | 18 | Aug.'26 | 2026-12-29 | 3 years 5 months | land acquisition is in progress & regular meeting and follow up is done for early land acquisition. | Land Acquisition |  | LA |  |  |  |  | 246.43 | 246.43 | 0 | Not Applicable | Not Applicable | Land acquisition is in process. Bridge work awarded & EPC tender under preparation.
28 | WR | GC | Miyagam-Karjan-Choranda-Malsar NG | 2023-24 | 2023 | 37 | June'27 | 2026-03-30 | 2 years 10 months | land acquisition is in progress & regular meeting and follow up is done for early land acquisition. | Land Acquisition |  | LA |  |  |  |  | 449.91 | 449.91 | 0 | Not Applicable | Not Applicable | Land acquisition is in process. Bridge work awarded & EPC tender under preparation.
29 | WR | GC | Jambusar-Kavi NG | 2023-24 | 2023 | 26 | June'26 | 2026-12-28 | 2 years 7 months | Due to delay in land acquisition. | Land Acquisition |  | LA |  |  |  |  | 318.44 | 318.44 | 0 | Not Applicable | Not Applicable | Land acquisition is in process. 20A issued. JMS completed and JMS sheets submitted. Tender will be invited after land acquisition. TDC for NIT: Dec'26
30 | WR | GC | Kosamba-Umarpada NG | 2023-24 | 2023 | 70 | July'27 | 2026-03-29 | 1 years 9 months | Due to delay in land acquisition and delay in sanction of 9.2 kms ROR which got sanctioned in March 2026. | Land Acquisition |  | LA |  |  |  |  | 467.58 | 467.58 | 0 | Not Applicable | Not Applicable | Land acquisition is in process. For Kosamba-Valechha (9.2 kms) section a new rail line work "Kosamba Rail over Rail flyover" sanctioned in March-26. EPC will be processed after land acquisition. For Valechha-Zankavan (38.9 Km) section EPC tender awarded and work is in progress. For balance Zankavan-Umarpada (22 kms) section EPC will be processed after land acquisition. New 20A published for Mangrol taluka on 23.09.26 in gazette.
65 | WR | DL | Rajkot - Kanalus | 2021-22 | 2021 | 111 | 2026-04-26 | 2026-12-26 | 8 months | Delay in land acquisition | Land Acquisition |  | LA |  |  |  |  | 1080.57 | 1205.17 | 124.6 | Increase in cost of land and increase in scope of yard modification due to conversion of D class station to B class. |  | Work is in progress.
80 | WR | DL | 4th Line Between Barejadi-Nandej (Geratpur)- Sanand (38.20 Km) (Ahmedabad Bypass) | 2022-23 | 2023 | 38 | 2026-03-27 | 2026-07-28 | 1 Year 4 Months | There is heavy resistance for land acquisition from stakeholders. Land acquisition is major problem since project is located just outside Ahmedabad city and town planning scheme is rapidly spreading. | Land Acquisition |  | LA |  |  |  |  | 961.67 | 2402.7126 | 1441.0426 | Increase in cost for private land acquisition. Revised estimate already sent to Rly bd for sanction. | No Cost overrun | Work is in progress.
86 | WR | DL | Provision of 'Y' connectivity between Sabarmati A and Asarva (0.9 Km) | 2022-23 | 2023 | 1 | 2026-03-26 | 2026-12-26 | 9 months | Delay in land acquisition by NHSRCL. Site vacated by NHSRCL in May-26. Work started after this. | Land Acquisition |  | LA |  |  |  |  | 15.25 | 15.25 | 0 | NA | No Cost overrun | Commissioned on 28.10.2026
87 | WR | DL | Multi Tracking between Chhayapuri-Bajva (2.0 Km) | 2022-23 | 2024 | 2 | 2026-11-26 | 2026-11-27 | NIL | Work was with Gatishakti initially. Transferred to CAO© in Sept'24 | Phase wise Sanctioning | [6 empty] | 42.9175 | 42.9175 | 0 | Not applicable. | No Cost overrun | Work is in progress.
107 | WR | DL | Vasai byepass double line between Naigaon and Juchandra | 2023-24 | 2023 | 6 | July'26 | 2026-03-29 | 2 year 8 months | Due to delay in land acquisition. Regular meeting and follow up is being done for early land acquisition. | Land Acquisition |  | LA |  |  |  |  | 175.99 | 175.99 | 0 | NA |  | Land acquisition is in process. Tenders for execution of site works will be floated commensurate to approval of ESP, Land acquisition & mangrove clearance.
110 | WR | DL | Quadrupling between Samakhiali and Gandhidham | 2023-24 | 2023 | 53 | July’ 27 | 2026-12-27 | 5 Months | Due to delay in land acquisition. | Land Acquisition |  | LA |  |  |  |  | 1429.56 | 1429.56 | 0 | NA | No Cost overrun | SIOB-BCOB (16 TKm) Section Commissioned on 11.08.2026 and in remaining section work is in progress
124 | WR | DL | Doubling between Vishvamitri-Dabhoi including 'Y' connection at Vishvamitri | 2023-24 | 2024 | 33 | Dec.'27 | 2026-12-28 | 12 month | Due to delay in land acquisition. Regular meeting and follow up is being done for early land acquisition. | Land Acquisition |  | LA |  |  |  |  | 394.14 | 394.14 | 0 | NA | Not Applicable | Land acquisition in progress. 20A issued on 28.08.2026. Tender will be invited after land acquisition.
[18 empty] | 83401.3236 | 95369.2586 | 11967.935
[5 empty] | No data | 93